## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-201 | 2026-06-01 | Open Phase 02 and fix its boundary: an inventory and a record-level applicability determination, with no risk assessment, no validation status, no control implementation and no scoring of any kind — and align the evidence series to the phase's document-ID block, superseding the continuation at EV-129 stated in Phase 01's evidence index | Lydia Marchetti-Nwosu | — | Steering Committee, EV-201
DEC-202 | 2026-06-05 | Authorise a physical walk of the estate — both sites, both on-premise data centres, the disaster-recovery site and the three vendor-hosted systems — and fix the counting rules before the walk begins | Amara Sissoko | — | GOV-06
DEC-203 | 2026-06-12 | The inventory is the estate, not the register. Reconcile the register to the walk and never the walk to the register; adopt the corrected inventory SYS-001 to SYS-222 | Amara Sissoko | ADR-0009 | GOV-07
DEC-204 | 2026-06-16 | Adopt the three-limb GxP-relevance test and require the limb satisfied and its evidence to be recorded on every entry | Terrence Abbatiello | — | Steering Committee, EV-208
DEC-205 | 2026-06-19 | A record type is the unit of determination, and a system inherits its scope from the record types it holds | Priyanka Venkataraman | ADR-0013 | Steering Committee, EV-209
DEC-206 | 2026-06-23 | Adopt the record-type definition and the four bounding rules; open the series RT-01 to RT-58 and fix the order in which the narrow interpretation's questions are asked | Priyanka Venkataraman | — | CSV Working Group, EV-210
DEC-207 | 2026-06-26 | Adopt the GxP determination across the corrected inventory, with the basis recorded per entry and the borderline cases argued rather than asserted | Terrence Abbatiello | — | Steering Committee, EV-211
DEC-208 | 2026-06-30 | Publish the out-of-scope record types with the reason each is out, because an unexplained exclusion is indistinguishable from an oversight | Priyanka Venkataraman | ADR-0014 | GOV-08
DEC-209 | 2026-07-03 | Re-open the eleven record types Helix had treated as out of scope on the ground that they were printed, and test each against all three conditions of the paper-printout route on a separate sheet | Dr Sunita Raghunathan | — | CSV Working Group, EV-214
DEC-210 | 2026-07-07 | The paper-printout route is tested against all three of its conditions and never asserted. Seven of the eleven fail the first condition and are Part 11 records; four pass all three and are out of scope | Dr Sunita Raghunathan | ADR-0010 | Steering Committee, EV-215
DEC-211 | 2026-07-10 | Raise IS-08; record that three of the seven are chromatography data system record types and bear on OBS-2, and draw no conclusion from it | Priyanka Venkataraman | — | Steering Committee, EV-216
DEC-212 | 2026-07-14 | Open and closed are determined on who controls access under 21 CFR 11.3(b)(4), not on network position or hosting. All 61 systems holding a Part 11 record are closed systems | Joachim Reuter | ADR-0011 | Steering Committee, EV-218
DEC-213 | 2026-07-17 | Retain the encryption and digital-signature measures deployed for the three vendor-hosted systems, and raise IS-09: 21 CFR 11.30's additional measures sit on top of 21 CFR 11.10's requirements, and 21 CFR 11.10 has never been assessed for those three | Joachim Reuter | — | Steering Committee, EV-219
DEC-214 | 2026-07-21 | Adopt the record-type register RT-01 to RT-58 and the systems register SYS-001 to SYS-222, with the Part 11 determination derived per system from the record types it holds and never entered directly | Amara Sissoko | — | Steering Committee, EV-221
DEC-215 | 2026-07-24 | The determination is a controlled document with a named owner and a review trigger, because a determination nobody maintains is a determination that was true once | Terrence Abbatiello | ADR-0015 | GOV-09
DEC-216 | 2026-07-28 | Record the outcome of the quality system search — no written Part 11 applicability determination existed anywhere, and no procedure required one to exist. Close IS-02 on release of the approved determination and open IS-10 in its place | Terrence Abbatiello | — | Steering Committee, EV-226; ratified at GOV-10
DEC-217 | 2026-07-30 | Establishing a candidate explanation's premise does not promote the candidate to the answer. IS-01 stays open and stays unweighted, and is returned to in Phase 08 | Gideon Halvorsen | ADR-0012 | GOV-10
DEC-218 | 2026-07-31 | Publish Phase 02 at MS-06; hand the determination to Phase 03 as its assessment population and record that nobody has assessed whether the data in any of the 34 record types is any good — IS-11 | Lydia Marchetti-Nwosu | — | Steering Committee, EV-232