## Issues
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
IS-01 | Four internal audits between 2023-06 and 2025-09 covered all three systems between them, each falling inside the scope of at least two, and none raised a finding on the subject matter of OBS-2, OBS-4 or OBS-6. Why is not established. Four candidate explanations are recorded at 01.09 §6 and the programme has chosen none | Gideon Halvorsen | 2026-05-19 | Open, and unweighted by decision. Phase 02 established the premise of the fourth candidate and did not promote it — ADR-0012, DEC-217, GOV-10, 02.11. No ranking, probability, confidence or ordering attaches to the four. Returned to in Phase 08
IS-02 | No written record exists of which Helix records are Part 11 records. No determination has been made, at any point, by anybody | Priyanka Venkataraman | 2026-03-13 | CLOSED 2026-07-28. DEC-216, ratified at GOV-10 on 2026-07-30. Closure evidence: EV-226 the quality system search record · EV-227 the determination as approved · GOV-09 the approval. IS-10 opens in its place
IS-03 | The register of computerised systems carries no attribute identifying which systems hold records required by a predicate rule | Amara Sissoko | 2026-04-24 | Open, and narrowed. The systems register now carries the record types held and the Part 11 determination derived from them — 02.09 §2. It stays open because the attribute lives in a register the quality system does not yet require to be maintained — IS-10
IS-04 | CAL-06's cadence is undefined where CGMP does not specify a review frequency for the underlying data | Terrence Abbatiello | 2026-05-29 | Open — deliberately unresolved. The frequency is set from knowledge of the processes and from risk assessment, and the data integrity risk assessment is Phase 03's
IS-05 | Helix cannot state, for any system, how long audit trail data is retained relative to the retention period of the underlying record | Joachim Reuter | 2026-05-01 | Open, unchanged. Phase 02 determined which records are in scope and recorded no retention period — IS-14, DP-14
IS-06 | The laboratory record review procedure does not state whether the audit trail associated with a result forms part of the original record reviewed under 21 CFR 211.194(a)(8) | Dr Sunita Raghunathan | 2026-05-15 | Open, unchanged. Phase 02 assessed no procedure and no audit trail
IS-07 | Seven of the twelve calendar entries outlive the programme and none has a named owner after close-out on 2027-04-30 | Lydia Marchetti-Nwosu | 2026-05-27 | Open — deliberately unresolved. IS-10 is the same shape of problem for the determination, and 02.09 §6 says so

## Assumptions
Col 1 | Col 2 | Col 3 | Col 4
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage: no GxP-relevant system was introduced, removed or materially reconfigured between the walk and 2026-07-31 | Amara Sissoko | The inventory of 222 is out of date on the day it is published, and every determination made across it is made across the wrong population
AS-14 | Load-bearing on four out-of-scope record types. The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable electronic record and have no export capability, as verified at the walk and evidenced at EV-223 | Dr Sunita Raghunathan | Condition 3 of the paper-printout route stops holding for the affected record type, which becomes a Part 11 record. The failure is silent unless ADR-0015's trigger catches an instrument replacement — PR-16
AS-15 | Helix continues to administer every account on the three vendor-hosted systems, so their classification continues to turn on the access test at 21 CFR 11.3(b)(4) rather than on where they are hosted. Extends AS-05 | Joachim Reuter | The closed determination for those three has to be re-made, and 21 CFR 11.30's additional measures acquire a different footing — IS-09, 02.07
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories, and no product introduction or laboratory change before MS-09 introduces a record type the enumeration does not carry. Extends AS-07 | Priyanka Venkataraman | The determination is incomplete, OBJ-01 cannot be closed on it, and Phase 05 scopes controls against a population that is missing rows
AS-17 | The vendors of the chromatography data system, the dissolution workstations and the environmental and warehouse monitoring systems supply technical documentation sufficient to describe how the seven newly in-scope record types are created, retained and exported. Extends AS-04 | Joachim Reuter | The seven have to be characterised by testing rather than from documentation, which Phase 05 does not size for
AS-18 | The 58 record types remain a stable unit through Phase 05, so control selection can be specified against RT identifiers rather than against systems | Priyanka Venkataraman | Controls have to be re-specified, and the repository loses the ability to say which control protects which record
AS-19 | The review trigger at ADR-0015 is operated by its named owner in the absence of any procedure requiring it, until Phase 04 supplies one | Terrence Abbatiello | The determination ages without anybody noticing, which is the failure mode ADR-0015 exists to prevent — IS-10, PR-13
AS-01 | The Steering Committee continues monthly to close-out with authority over scope, budget and contingency | Lydia Marchetti-Nwosu | Open, holding. Every Phase 02 sitting is minuted and indexed in evidence-index.md
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Open, holding
AS-03 | Load-bearing. The record-level determination can be completed in Phase 02 from the existing estate documentation plus targeted technical review, inside the window to MS-06 on 2026-07-31 | Priyanka Venkataraman | Tested. Held on its date and failed on its method. MS-06 is met at the vantage, but the determination could not be made from the existing documentation: the register was wrong by twenty-six entries in both directions and a physical walk was required — 02.02, GOV-06. Closed. The method clause is recorded as falsified, and it is why ADR-0009 exists
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open. Extended by AS-17 for the seven
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open. Extended by AS-15 to all three vendor-hosted systems
AS-06 | No new GxP-critical platform is introduced before MS-06 on 2026-07-31 | Amara Sissoko | Tested and held to the vantage — the walk of 2026-06-08 to 2026-06-11 found none, EV-204 to EV-206. Closed, and continues as AS-13 in a wider form
AS-07 | The 41 marketed products and the two QC laboratories remain the basis on which record types are enumerated | Dr Sunita Raghunathan | Open. Extended by AS-16
AS-08 | The commitments in Helix's written response of 2026-03-06 are not varied by Helix during the programme | Rebekah Sandquist | Open, holding
AS-09 | Thorne Delacroix Consulting's design and drafting work is complete before the third-party audit opens at CAL-10 | Lydia Marchetti-Nwosu | Open. Nothing in Phase 02 has moved it
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding. Nothing in this repository cites a draft as a requirement
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding. 02.06 relies on it and says so
AS-12 | Internal audit capacity is available for CAL-09 without displacing the approved annual audit plan | Gideon Halvorsen | Open

## Dependencies
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
DP-01 | The record-level Part 11 determination, for control selection in Phase 05 | Phase 02 | Priyanka Venkataraman | Delivered. Approved 2026-07-24, GOV-09. Carried open until Phase 05 consumes it
DP-02 | The data integrity risk assessment, for the validation framework's rigour | Phase 03 | Priyanka Venkataraman | Open
DP-03 | Technical cooperation from IT and Automation — system access, configuration detail and audit trail behaviour | Amara Sissoko; Joachim Reuter | Priyanka Venkataraman | Open, and exercised. The walk and the determination both ran on it. The price of ADR-0002 was paid and is recorded — PR-05
DP-04 | Vendor technical documentation on audit trail generation, retention and export | Meridian; Calderon Vega; Brightpath | Joachim Reuter | Open. Extended by DP-10
DP-05 | Validation execution resource contracted and available from the opening of Phase 04 | External resource | Colm Ó Braonáin | Open
DP-06 | Vashti Okonjo & Partners' availability for the audit window opening 2027-03-29 | Vashti Okonjo & Partners | Gideon Halvorsen | Open — can move MS-12, and Helix cannot move it
DP-07 | Quality unit review and approval capacity for the two record review procedure revisions | The quality unit | Terrence Abbatiello | Open. Now competing with DP-11 for the same capacity
DP-08 | The statement of what the January 2011 Annex 11 route requires of O12 | The EU authorisation holder, through its Qualified Person | Rebekah Sandquist | Open

## Programme risks
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
PR-11 | The seven newly in-scope record types are read inside Helix as a criticism of the laboratory rather than as a correction of scope, and the determination becomes something people argue with instead of use | Dr Sunita Raghunathan | The finding is published with its test, its four survivals and its reasoning, so that it reads as a method applied rather than a verdict delivered — 02.06. Briefed at the CSV Working Group and at the Quality Council | IS-08, ADR-0010
PR-12 | The determination is cited as though it were an integrity statement — a system described as compliant, or a record described as reliable, because it appears in the register | Priyanka Venkataraman | Every register and chapter states what it does not carry; GOV-09 records the condition expressly; IS-11 is published as the phase's open question | IS-11, 02.09 §3
PR-13 | The determination drifts, because no procedure requires it to be maintained and the trigger is held by a programme decision | Terrence Abbatiello | ADR-0015's named owner and six trigger events, with an annual floor; IS-10 open and assigned; DP-11 carried for the procedure that would close it | IS-10, AS-19, DP-11
PR-14 | Phase 03's assessment population is larger than the plan assumed, because seven record types entered scope after the plan was written | Lydia Marchetti-Nwosu | The population is handed over in full and named at 02.13 §8. No milestone is moved and none is forecast | IS-08, AS-03
PR-15 | The phrase "a Part 11 system" re-enters use, and a system is scoped without naming the record types that make it in scope | Priyanka Venkataraman | ADR-0001 is standing framing; the systems register derives the determination rather than accepting it as an entry, and carries the RT identifiers that produce it — 02.09 §2 | ADR-0001, ADR-0013
PR-16 | An instrument behind one of the four surviving printout record types is replaced with one that retains or exports data, and the determination stops being true without anybody deciding anything | Dr Sunita Raghunathan | ADR-0015 trigger events on a system entering the estate and on a record type changing the form it is maintained in; instrument capability restated on each review; AS-14 records the assumption | AS-14, ADR-0015, 02.06 §7
PR-17 | The seventeen systems with no validation lifecycle behind them absorb Phase 04 effort that was sized against systems with documentation to build on | Colm Ó Braonáin | Sequenced early inside Phase 04 so that the size of the gap is known while the phase still has room; reported monthly at CAL-01. The procurement and commissioning routes that produced them are closed as policy work in the same phase | IS-13, 02.02 §2.1, 02.12 §4
PR-18 | The first assessment of the three vendor-hosted systems against 21 CFR 11.10 stalls on documentation held by a vendor, inside a window that also carries the rest of Phase 05 | Joachim Reuter | The documentation request opens at the start of Phase 03 rather than at the point of assessment; the dependency is carried at DP-12 and the assumption at AS-15 | IS-09, DP-12, AS-15, 02.12 §3