## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-301 | 2026-08-03 | Open Phase 03 and fix its boundary: an assessment of the integrity of the records Phase 02 determined to be in scope, with no validation status, no control position, no audit trail configuration, no review frequency and no retention period, and with the Part 11 control assessment reserved to Phase 05 | Lydia Marchetti-Nwosu | — | Steering Committee, EV-301
DEC-302 | 2026-08-06 | Record that no FDA regulation and no FDA guidance requires a data integrity risk assessment, that FDA invokes risk in one general statement in the December 2018 drug CGMP questions and answers' Introduction and in three bounded invocations in its answers, all of them nonbinding, and that the method is anchored on 21 CFR 211.68(b) — a shall — rather than on a guidance. The assessment is Helix's own decision and the phase says so on its first page | Priyanka Venkataraman | — | Steering Committee, EV-302
DEC-303 | 2026-08-12 | The unit of assessment is the record-type/system pair, because the same record type is not at the same risk on every system that holds it. Never the system alone; never the record type alone | Priyanka Venkataraman | ADR-0016 | GOV-11
DEC-304 | 2026-08-14 | Derive the assessment population by joining Phase 02's two registers — the 34 in-scope record types to the 61 systems that hold them — rather than re-enumerating it, and refuse to re-open the Part 11 determination: a record type's status changes on ADR-0015's trigger and through change control, not because an assessment would prefer a different scope | Amara Sissoko | — | Steering Committee, EV-304
DEC-305 | 2026-08-19 | ALCOA is not a control set, and the mapping Helix uses is FDA's own footnote 5 to the predicate rules — not a crosswalk onto 21 CFR 11.10. An ALCOA assessment and a Part 11 control assessment are two different assessments of the same records, and Phase 05 performs the second | Priyanka Venkataraman | ADR-0019 | GOV-11
DEC-306 | 2026-08-21 | Adopt FDA's five attributes in FDA's own words — *"attributable, legible, contemporaneously recorded, original or a true copy, and accurate"* — attribute the four additional attributes to the bodies that set them out — MHRA, PIC/S and WHO — name no originator for either set, and state MHRA's own position on the acronym at every citation rather than characterising it | Dr Sunita Raghunathan | — | CSV Working Group, EV-306
DEC-307 | 2026-08-26 | The five attributes are assessed separately and are never averaged, weighted or traded off. A mean of five attributes is a number that describes nothing; the pair carries a profile and its worst attribute governs | Dr Sunita Raghunathan | ADR-0017 | GOV-12
DEC-308 | 2026-08-28 | Adopt the attribute determination record as the instrument, with three determinations — Met, Not met, Not determinable — and the evidence actually examined named on every determination, including every determination of Met | Priyanka Venkataraman | — | CSV Working Group, EV-308
DEC-309 | 2026-09-01 | Adopt MHRA's and PIC/S's risk formulations voluntarily, labelled as adopted at every citation, and record that neither body regulates Helix and that neither formulation is a requirement Helix is under | Colm Ó Braonáin | — | CSV Working Group, EV-309
DEC-310 | 2026-09-04 | Not determinable is a determination in its own right, and a pair carrying one is not scored. An absence of evidence scores nothing; it is a gap, not a low number. The unscorable pairs are carried as a distinct population and handed forward | Terrence Abbatiello | ADR-0018 | GOV-12
DEC-311 | 2026-09-08 | Open two registers that never merge — DR-nn for a scored pair and ND-nn for a pair that cannot be scored — and record that neither identifier converts into the other: a pair that later becomes determinable enters the scored register as a new entry with a new identifier and a date | Priyanka Venkataraman | — | Steering Committee, EV-311
DEC-312 | 2026-09-10 | Record the likelihood basis and the consequence basis separately on every scored pair. A single sentence covering both is not a basis for either, and a rating whose two halves cannot be inspected separately cannot be argued with | Joachim Reuter | — | CSV Working Group, EV-312
DEC-313 | 2026-09-11 | The scale is Helix's own, is kept small, and is published — because under 21 CFR 211.22(d) the quality control unit's written procedures *"shall be followed"*, and the moment Helix writes a scale, its own procedure is enforceable against it. Raise IS-19 | Terrence Abbatiello | ADR-0020 | GOV-12
DEC-314 | 2026-09-15 | Record IS-15: "original or a true copy" fails or cannot be determined on 75 of the 121 pairs, which is the most-failed and the most-undeterminable attribute and was not the attribute the assessment expected. Record the OBS-4 and OBS-2 links and draw no conclusion from either — OBS-4 is Phase 06's subject matter only as to the chromatography data system, and the closure position on any observation is Phase 08's | Priyanka Venkataraman | — | Steering Committee, EV-314
DEC-315 | 2026-09-17 | Close AS-17 as failed on test. The vendor documentation received does not describe how the seven newly in-scope record types are created, retained and exported in terms that permit a determination to be made. Raise IS-17 — the 24 pairs those seven produce have no assessment history at all. Escalate DP-10 and open DP-16 | Joachim Reuter | — | Steering Committee, EV-315
DEC-316 | 2026-09-22 | Likelihood is of the *undetected* alteration, not of the alteration — an attribute recorded Not met is a fact, not a likelihood — and a rating moves on likelihood unless the consequence changed. Raise IS-18: the pair is an IT-shaped unit and the transfer of a record between systems is assessed nowhere | Joachim Reuter | ADR-0021 | GOV-12
DEC-317 | 2026-09-24 | Approve the attribute determination register and the risk register at the vantage, and close IS-11: the assessment has been made across the whole population, and a determination of Not determinable is a result of assessment rather than an absence of one | Priyanka Venkataraman | — | GOV-13
DEC-318 | 2026-09-25 | Accept the 47 unscorable pairs as a population and refuse to score them low. A pair Helix cannot assess is not a pair Helix has assessed favourably. Open IS-16 in IS-11's place, and hand the population forward with a closure condition stated for every row | Terrence Abbatiello | — | GOV-14
DEC-319 | 2026-09-29 | The assessment is re-run on a trigger and not on a calendar, because a calendar re-assessment finds a change up to a year after it happened and reports success by being silent in between. Raise IS-20 | Gideon Halvorsen | ADR-0022 | GOV-15
DEC-320 | 2026-09-30 | Publish Phase 03 at MS-07; hand the two registers to Phase 04 as the input that sets the validation framework's rigour, and record IS-21 — the assessment says where the data is weak, and nothing in the quality system yet says what Helix must do about it | Lydia Marchetti-Nwosu | — | Steering Committee, EV-336