## Issues
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
IS-15 | "Original or a true copy" fails or cannot be determined on 75 of the 121 pairs. Helix cannot say, for most record types, which instance is the original and whether a copy is a true copy. 34 pairs are recorded Not met and 41 Not determinable; 34 + 41 = 75. It is both the most-failed and the most-undeterminable of the five attributes, and it was not the attribute the assessment expected to find at the top of either list. The four routes by which it fails are a record that can be reprocessed and therefore has no single original in the way a weighing ticket does; an archive holding copies whose trueness nobody has demonstrated; a record rendered from a query rather than retrieved; and the same record held in several places with no rule saying which one Helix relies on — the route carrying most of the 34 recorded Not met. The OBS-4 and OBS-2 links are recorded and no conclusion is drawn from either | Priyanka Venkataraman | 2026-09-15 | Open — the closure condition is stated per pair in risk-register.md §4; DP-17 and DP-18 are the routes | DEC-314, ../03.07-the-attribute-that-fails-most.md, IS-14, DP-17, DP-18, PR-25
IS-16 | 47 pairs cannot be scored, and the programme has refused to score them low. Each carries at least one attribute Helix cannot determine at all. A pair Helix cannot assess is not a pair Helix has assessed favourably, and an absence of evidence scores nothing. The 47 are carried as a population at risk-register.md §4, each row with the attribute that could not be determined and what would be needed to determine it. They are handed forward as a population and not as a low score | Priyanka Venkataraman | 2026-09-25 | Open — opened in IS-11's place at DEC-318, accepted as a population at GOV-14. Phase 04 for what must be done about it; Phase 05 and Phase 07 for the evidence that would determine most of it | DEC-310, DEC-318, ADR-0018, GOV-14, ../03.08-what-cannot-be-determined.md, IS-11, PR-19, DP-16, DP-20
IS-17 | The 24 pairs from the seven have no assessment history at all. Phase 02's seven newly in-scope record types — RT-13, RT-14, RT-15, RT-16, RT-26, RT-27 and RT-33 — produce 24 pairs across 18 systems, and every one of the 24 is Not determinable on at least one attribute. They were treated as outside Part 11 for the whole of the period in which they were Part 11 records, so nothing was ever retained about which instance is the original, when capture happens relative to the act, or what the record is to be compared against — the three attributes that carry 64 of the 74 undetermined determinations on these pairs, with *original or a true copy* undetermined on every one of the 24. They are not low risk; they are unassessed. All 24 sit inside the 47 | Dr Sunita Raghunathan | 2026-09-17 | Open — AS-17 closed as failed against it; DP-10 escalated and DP-16 opened | DEC-315, IS-08, AS-17, DP-10, DP-16, ../03.09-the-seven-assessed-for-the-first-time.md
IS-18 | The unit is IT-shaped and the transfer between systems is assessed nowhere. 31 of the 34 in-scope record types are held on more than one system. The pair assesses the record on each system and assesses the movement between them on none of them. The gap is not only a departure from good practice; it sits on a shall. 21 CFR 211.68(b) provides, in the sentence immediately before the one this phase is anchored on, that *"Input to and output from the computer or related system of formulas or other records or data shall be checked for accuracy"* — and the object of that requirement is exactly the movement the unit cannot see: the record entering a system and the record leaving it. The assessment is anchored on that paragraph's third sentence and is blind to its second. Nothing here states whether any such check exists at Helix, whether it works or whether it is adequate — that is Phase 04's and Phase 05's, and this phase states no control position for anything. PIC/S PI 041-1 §5.5.4 carries the good-practice half: *"Risk assessments should focus on a business process (e.g. production, QC), evaluate data flows and the methods of generating and processing data, and not just consider information technology (IT) system functionality or complexity."* That is good practice, not a requirement, and PIC/S is not a US regulator — and its final clause names the frame 21 CFR 211.68(b) itself uses, so Helix holds a regulation and a guidance pointing in opposite directions on the same question and has followed the regulation. By either standard the unit Helix chose sees the endpoints and not the journey. ../03.11-the-flow-the-unit-does-not-see.md §2 and §6 own both arguments | Joachim Reuter | 2026-09-22 | Open — the method's own criticism, published rather than discovered. The transfer is not assessed at this vantage and no substitute assessment is claimed | DEC-316, ADR-0016, ../03.11-the-flow-the-unit-does-not-see.md, DP-16, PR-24
IS-19 | The scale is now a written procedure Helix will be held to under 21 CFR 211.22(d). The quality control unit's responsibilities and procedures shall be in writing and *"such written procedures shall be followed."* No regulator prescribes a scale; the moment Helix writes one, its own procedure is enforceable against it. The scale is published deliberately and is kept small for that reason, and nothing in Helix's quality system yet requires it to be applied, maintained or followed | Terrence Abbatiello | 2026-09-11 | Open — Phase 04, MS-08. DP-19 is the only route by which it closes | DEC-313, ADR-0020, ../03.05-the-method-and-the-scale.md, IS-10, DP-19, PR-22
IS-20 | A rating is not a control position, and nothing in this phase says whether any control works. The registers record what the records are like. They do not record whether access is limited to authorised individuals, whether an audit trail exists or is reviewed, whether an electronic signature is deployed, or whether any paragraph of 21 CFR 11.10 is met for any system. A pair rated Low is not a pair with a working control, and a pair rated High is not a pair with a broken one | Gideon Halvorsen | 2026-09-29 | Open — Phase 05, MS-09, owns the control position. Carried so that no later document can read a rating as one | DEC-319, ../03.12-what-this-does-not-establish.md, IS-09, PR-20
IS-21 | The assessment says where the data is weak. Nothing in the quality system yet says what Helix must do about it. There is no procedure requiring the assessment to exist, no procedure requiring a determination of Not met or Not determinable to produce an action, no threshold at which a rating obliges anybody to do anything, and no owner for the consequence of a row. The registers are a description, and a description nobody is required to act on is a description | Priyanka Venkataraman | 2026-09-30 | Open — Phase 04 owns it, MS-08, 2026-11-30. DP-19 carries the quality unit capacity | DEC-320, IS-10, IS-19, DP-19, ../03.13-phase-summary-and-transition.md

## Assumptions
Col 1 | Col 2 | Col 3 | Col 4
AS-20 | The 121 pairs derived on 2026-08-14 remain the population to MS-08: no ADR-0015 trigger fires between the Phase 02 vantage and 2026-11-30 that adds a pair, removes one, or changes which system holds a record type | Priyanka Venkataraman | The assessment is made across the wrong population, and Phase 04 sets the validation framework's rigour against a register that does not describe the estate
AS-21 | Load-bearing on every consequence value. The consequence recorded for a record type reflects what is lost if the record is wrong, and that is a property of the class which does not vary with the system holding it except where the instance's role in the process differs — in which case the difference is recorded in the basis column | Terrence Abbatiello | Consequence stops being comparable across pairs, the register cannot be read down a column, and a rating that moves on likelihood alone stops being a meaningful statement — ADR-0021
AS-22 | The individuals who supplied the facts each determination rests on — record owners, system owners and administrators — described the position as it is rather than as procedure says it should be | Priyanka Venkataraman | Determinations recorded Met rest on a description rather than on the position, and the register is a record of what people believe
AS-23 | A determination of Not determinable records the absence of evidence and not the absence of a search. Every such determination names what was looked for, where, and by whom, on the record at EV-316 | Gideon Halvorsen | The 47 become a place where difficult pairs are put rather than a population with a closure condition, and IS-16 stops being answerable
AS-24 | FDA's five attributes are sufficient to describe the integrity position of a Helix record type, so that a pair whose five attributes are all Met has no material integrity question left unasked by this instrument | Priyanka Venkataraman | A question the instrument does not ask goes unasked across the whole population, and the four additional attributes MHRA defines have to be brought into the instrument and the assessment re-run
AS-25 | The scale published at ../03.05-the-method-and-the-scale.md is applied unchanged to MS-13, so that a rating taken in Phase 03 is comparable with a rating taken later | Terrence Abbatiello | Ratings across phases stop being comparable, and a scale varied after publication is a written procedure that was not followed — 21 CFR 211.22(d), IS-19
AS-26 | Many of the 35 GxP-relevant systems that hold no Part 11 record are reached by 21 CFR 211.68, which applies to computers and related systems used in the manufacture, processing, packing and holding of a drug product whatever the Part 11 answer is; others are reached by different provisions of Part 211 according to what they do, and this phase has not determined which provision reaches which system. None of the 35 is reached by this assessment, and no later phase reads their absence from the 121 as an assessment of them | Colm Ó Braonáin | "Not in the assessment" is read as "assessed and satisfactory" for thirty-five systems, which is the same error 02.08 was written to prevent in the other direction
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage | Amara Sissoko | Open, holding. Extended to the assessment population by AS-20
AS-14 | The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable electronic record and have no export capability | Dr Sunita Raghunathan | Open, unchanged. Those four record types are outside the 34 and outside the 121; nothing in Phase 03 tested them
AS-15 | Helix continues to administer every account on the three vendor-hosted systems | Joachim Reuter | Open, holding. Nine pairs sit on the three, and no control position is stated for any of them — IS-09
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories | Priyanka Venkataraman | Open, and now under test. Phase 03 introduced no record type. It did record one gap in the correspondence between FDA's footnote 5 and Phase 02's anchors: 21 CFR 211.122, which footnote 5 names for *attributable*, is cited against no record type in the register — ../03.04-footnote-five.md §8. Whether a record type is missing or the anchor is carried elsewhere is the determination owner's to establish, on ADR-0015's review trigger, and it is not established here
AS-17 | The vendors of the chromatography data system, the dissolution workstations and the environmental and warehouse monitoring systems supply technical documentation sufficient to describe how the seven newly in-scope record types are created, retained and exported | Joachim Reuter | Tested and FAILED. Closed 2026-09-17, DEC-315, evidence EV-327. The documentation received describes the products and does not answer the question the assessment had to ask, so the seven had to be assessed from what Helix itself holds, and what Helix holds reaches only the attributes that are properties of the system rather than of a decision somebody recorded. The failure is why all 24 of their pairs are Not determinable on at least one attribute — IS-17. DP-10 is escalated and DP-16 opened in consequence
AS-18 | The 58 record types remain a stable unit through Phase 05 | Priyanka Venkataraman | Open, holding. The assessment is specified against RT identifiers on SYS identifiers and depends on it
AS-19 | The review trigger at ADR-0015 is operated by its named owner in the absence of any procedure requiring it | Terrence Abbatiello | Open. AS-25 and ADR-0022 add a second trigger set in the same condition
AS-01 | The Steering Committee continues monthly to close-out | Lydia Marchetti-Nwosu | Open, holding. Every Phase 03 sitting is minuted and indexed
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Open, holding
AS-03 | The record-level determination can be completed in Phase 02 from the existing estate documentation plus targeted technical review | Priyanka Venkataraman | CLOSED at the MS-06 gate. Held on its date and failed on its method — unchanged by this phase
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open, and now doubtful. AS-17, which extended it for the seven, has been tested and failed
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open. Extended by AS-15
AS-06 | No new GxP-critical platform is introduced before MS-06 | Amara Sissoko | CLOSED, tested and held. Continues as AS-13
AS-07 | The 41 marketed products and the two QC laboratories remain the basis on which record types are enumerated | Dr Sunita Raghunathan | Open. Extended by AS-16
AS-08 | The commitments in Helix's written response of 2026-03-06 are not varied by Helix during the programme | Rebekah Sandquist | Open, holding
AS-09 | Thorne Delacroix Consulting's design and drafting work is complete before the third-party audit opens at CAL-10 | Lydia Marchetti-Nwosu | Open. Nothing in Phase 03 has moved it
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding
AS-12 | Internal audit capacity is available for CAL-09 without displacing the approved annual audit plan | Gideon Halvorsen | Open

## Dependencies
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
DP-15 | The two registers as an input to the validation framework's rigour. The risk-basing of validation extent is FDA's guidance, not FDA's regulation — December 2018 Q&A, Q3, a nonbinding *should*: *"The extent of validation studies should be commensurate with the risk posed by the automated system."* 21 CFR 211.68(b)'s *shall* graduates input/output verification and is cited only for that — ../03.01-nothing-required-this.md §5. Neither axis of this scale is the axis 21 CFR 211.68(b) names: the regulation grades on *"the complexity and reliability of the computer or related system"*, and this assessment grades on what the record decides and on whether an alteration would be noticed. Phase 04 must state how the two axes relate to complexity and reliability, or assess those separately, before relying on this assessment to size input/output verification. That statement does not exist at this vantage | Phase 04, MS-08, 2026-11-30 | Phase 03, delivered at the vantage | Colm Ó Braonáin | Open — delivered, and carried until Phase 04 consumes it. MS-07 before MS-08 exists for this reason: building the framework first sets the rigour by habit
DP-16 | Audit trail behaviour statements for the systems on which contemporaneity or attribution could not be determined — what is captured, when, and against which identity | Closure of the corresponding rows in risk-register.md §4 | The system vendors, and Helix's own IT and Automation functions | Joachim Reuter | Open — opened at DEC-315 when AS-17 failed; overlaps DP-10 and does not replace it
DP-17 | A statement, per record type, of which instance Helix relies on as the original, and of the method by which a copy of it is shown to be a true copy | Closure of the "original or a true copy" rows — 41 Not determinable and 34 Not met | The quality unit, with the record owners | Priyanka Venkataraman | Open — the single largest closure route in the phase, IS-15
DP-18 | A retention period for each of the 34 Part 11 record types, without which there is no rule a copy can be tested against. Extends DP-14 | Closure of part of IS-15, and the 21 CFR 11.10(e) comparison at IS-05 and IS-14 | The quality unit's records retention schedule | Priyanka Venkataraman | Open — DP-14 has not moved since 2026-07-24
DP-19 | Quality unit capacity to write the procedure that requires the assessment to exist, to be maintained and to be acted on | Closure of IS-19 and IS-21, in Phase 04 | The quality unit | Terrence Abbatiello | Open — the only route by which IS-21 closes, and it competes with DP-07 and DP-11 for the same capacity
DP-20 | Account administration records sufficient to say which named individual held the credential in use, for the systems on which attribution could not be determined | Closure of the attributable rows — 15 Not determinable | The IT organisation's access administration function | Amara Sissoko | Open — ADR-0002 and 01.07 §6 keep the Data Integrity Lead out of account administration, so this is a request and not an act the role can perform

## Programme risks
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
PR-19 | The 47 unscorable pairs are read as low risk because they carry no rating, and a population created to make a gap visible becomes the place the gap is hidden | Priyanka Venkataraman | The ND register is published in the same file as the DR register with the refusal stated at its head; every ND row carries what would be needed to determine it; GOV-14 accepts the population expressly and records the refusal; IS-16 is open and assigned | IS-16, ADR-0018, GOV-14
PR-20 | A rating is cited as a compliance position — a pair described as compliant because it rated Low, or a system described as controlled because its pairs did | Terrence Abbatiello | Every register and chapter states what a rating is not; IS-20 is published as an issue rather than as a caveat; ../03.12-what-this-does-not-establish.md owns the refusal and is a numbered chapter rather than a footnote | IS-20, PR-12
PR-21 | The five attributes are averaged, or a single number per pair is produced for an audience that asks for one | Priyanka Venkataraman | ADR-0017 is standing framing; the register has no summing column and the instrument has no summing field; the profile is published in full so that the question "what is the number" has an answer that is five determinations long | ADR-0017, DEC-307
PR-22 | The published scale is elaborated under pressure to discriminate more finely, and Helix acquires a written procedure it cannot follow consistently — which is the failure mode 21 CFR 211.22(d) makes expensive | Terrence Abbatiello | The scale is kept to two axes of five values and three bands; ADR-0020 records the refusal of the elaborate alternative with the argument for it stated fairly; AS-25 carries the assumption that it is applied unchanged to MS-13 | IS-19, ADR-0020, AS-25
PR-23 | The assessment becomes an annual exercise nobody acts on, because a calendar is easier to administer than a trigger | Lydia Marchetti-Nwosu | ADR-0022 sets re-assessment on named trigger events with an annual floor, and each firing is recorded on the form at ../templates/re-assessment-trigger-record-template.md, including firings that change nothing | ADR-0022, DEC-319
PR-24 | Phase 04 sets the validation framework's rigour from the 74 scored pairs alone and sizes nothing for the 47, because the 47 carry no number to size against | Colm Ó Braonáin | Both registers are handed over at DP-15, not the scored one; GOV-14 accepts the 47 as a population that is handed forward; 03.13 §6 states expressly that Phase 04 receives 121 pairs and not 74 | IS-16, IS-18, DP-15
PR-25 | The "original or a true copy" finding is read inside the laboratory as a criticism of the laboratory, rather than as a property of how records are copied and relied on across the whole estate | Dr Sunita Raghunathan | The finding is published with its four routes and with the distribution across all five owners; the expectation the assessment carried and the correction of it are both recorded at EV-325; briefed at the CSV Working Group and at the Quality Council | IS-15, PR-11
PR-26 | A Not determinable determination is treated as a task that closes when somebody writes a document, rather than when the evidence that would determine the attribute exists | Gideon Halvorsen | Every ND row states the evidence that would determine it and not the document that would describe it; AS-23 records the assumption that the determination reflects an absence of evidence and not an absence of a search | IS-16, AS-23