## Scored - DR-01 to DR-74
ID | Record type | System | Owner | L | Likelihood basis | C | Consequence basis | Product | Rating | Attributes Not met
DR-01 | RT-01 Electronic batch production and control record | SYS-001 — Manufacturing execution system with electronic batch record | Joachim Reuter | 2 | The same content is held at SYS-059; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 5 | Because the batch production and control record is the evidence the quality control unit reviews and approves under 21 CFR 211.192 before the batch is released, exercising the authority 21 CFR 211.22(a) gives it to approve or reject. An undetected alteration would change a disposition decision directly. | 10 | Moderate | — none; all five Met
DR-02 | RT-02 Electronic master production and control record | SYS-001 — Manufacturing execution system with electronic batch record | Joachim Reuter | 2 | The same content is held at SYS-059; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 5 | Because the master record is what every batch is made against, so an undetected alteration propagates to every batch made after it. An undetected alteration would change a disposition decision directly. | 10 | Moderate | — none; all five Met
DR-03 | RT-03 Component dispensing and charge-in record | SYS-001 — Manufacturing execution system with electronic batch record | Joachim Reuter | 2 | The same content is held at SYS-018, SYS-019, SYS-043; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the dispensing and charge-in record evidences the identity and quantity of every component that entered the batch. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | — none; all five Met
DR-04 | RT-04 In-process control result record | SYS-001 — Manufacturing execution system with electronic batch record | Joachim Reuter | 3 | A comparison with the instance at SYS-002, SYS-012, SYS-013 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Original or a true copy
DR-05 | RT-05 Equipment cleaning and use log | SYS-001 — Manufacturing execution system with electronic batch record | Joachim Reuter | 5 | Nothing in the ordinary course compares this record with another instance or with the event it records; there is no act an alteration would have to survive. | 3 | Because the cleaning and use log is the evidence that the equipment was clean and that its use is traceable to a batch. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 15 | High | Contemporaneously recorded, Original or a true copy
DR-06 | RT-04 In-process control result record | SYS-002 — Process historian | Joachim Reuter | 4 | No routine act brings this instance together with another and no second person reads it as a matter of course; an alteration would wait on whatever prompted somebody to look. | 4 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change the evidence a quality decision rests on. | 16 | High | Original or a true copy, Accurate
DR-07 | RT-06 Line clearance and packaging set-up record | SYS-003 — Blister packaging line 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-004, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the line clearance record is the evidence that no material or label from the preceding run remained on the line. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-08 | RT-07 Labelling issuance, use and reconciliation record | SYS-003 — Blister packaging line 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-004, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Original or a true copy
DR-09 | RT-08 Automated packaging inspection and rejection record | SYS-003 — Blister packaging line 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-004, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-10 | RT-06 Line clearance and packaging set-up record | SYS-004 — Blister packaging line 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the line clearance record is the evidence that no material or label from the preceding run remained on the line. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-11 | RT-07 Labelling issuance, use and reconciliation record | SYS-004 — Blister packaging line 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Original or a true copy
DR-12 | RT-08 Automated packaging inspection and rejection record | SYS-004 — Blister packaging line 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-005, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-13 | RT-06 Line clearance and packaging set-up record | SYS-005 — Bottling line 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the line clearance record is the evidence that no material or label from the preceding run remained on the line. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-14 | RT-07 Labelling issuance, use and reconciliation record | SYS-005 — Bottling line 1 control and data system | Joachim Reuter | 3 | A comparison with the instance at SYS-003, SYS-004, SYS-006 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Original or a true copy
DR-15 | RT-08 Automated packaging inspection and rejection record | SYS-005 — Bottling line 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-006; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-16 | RT-06 Line clearance and packaging set-up record | SYS-006 — Bottling line 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the line clearance record is the evidence that no material or label from the preceding run remained on the line. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-17 | RT-07 Labelling issuance, use and reconciliation record | SYS-006 — Bottling line 2 control and data system | Joachim Reuter | 3 | A comparison with the instance at SYS-003, SYS-004, SYS-005 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Original or a true copy
DR-18 | RT-08 Automated packaging inspection and rejection record | SYS-006 — Bottling line 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-19 | RT-06 Line clearance and packaging set-up record | SYS-007 — Cartoning line 3 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the line clearance record is the evidence that no material or label from the preceding run remained on the line. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-20 | RT-07 Labelling issuance, use and reconciliation record | SYS-007 — Cartoning line 3 control and data system | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Original or a true copy
DR-21 | RT-07 Labelling issuance, use and reconciliation record | SYS-008 — Serialisation and aggregation system | Joachim Reuter | 3 | A comparison with the instance at SYS-003, SYS-004, SYS-005 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Original or a true copy
DR-22 | RT-35 Finished product distribution record | SYS-008 — Serialisation and aggregation system | Joachim Reuter | 4 | No routine act brings this instance together with another and no second person reads it as a matter of course; an alteration would wait on whatever prompted somebody to look. | 4 | Because the distribution record is what a recall would be executed from. An undetected alteration would change the evidence a quality decision rests on. | 16 | High | Original or a true copy
DR-23 | RT-08 Automated packaging inspection and rejection record | SYS-009 — Vision inspection system, blister line 1 | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 2 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would degrade a supporting or periodic activity and would not by itself change a disposition. | 4 | Low | Original or a true copy
DR-24 | RT-08 Automated packaging inspection and rejection record | SYS-010 — Vision inspection system, blister line 2 | Joachim Reuter | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 2 | Because the inspection and rejection record is the evidence of what the automated examination found and what it removed. An undetected alteration would degrade a supporting or periodic activity and would not by itself change a disposition. | 4 | Low | Original or a true copy
DR-25 | RT-04 In-process control result record | SYS-012 — Tablet press 1 control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-013; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-26 | RT-04 In-process control result record | SYS-013 — Tablet press 2 control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-27 | RT-04 In-process control result record | SYS-014 — Tablet press 3 control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-28 | RT-04 In-process control result record | SYS-015 — Fluid bed dryer control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-29 | RT-04 In-process control result record | SYS-016 — High-shear granulator control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-30 | RT-04 In-process control result record | SYS-017 — Tablet coater control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-31 | RT-03 Component dispensing and charge-in record | SYS-018 — Blender control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-019, SYS-043; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the dispensing and charge-in record evidences the identity and quantity of every component that entered the batch. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | — none; all five Met
DR-32 | RT-04 In-process control result record | SYS-018 — Blender control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-33 | RT-03 Component dispensing and charge-in record | SYS-019 — Dispensary weighing and dispensing system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-018, SYS-043; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the dispensing and charge-in record evidences the identity and quantity of every component that entered the batch. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | — none; all five Met
DR-34 | RT-04 In-process control result record | SYS-020 — Capsule filler control and data system | Joachim Reuter | 2 | The same content is held at SYS-001, SYS-002, SYS-012; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the in-process control result is one of the acceptance criteria the batch is judged against at review. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-35 | RT-11 Analytical result record | SYS-025 — LIMS, QC laboratory | Dr Sunita Raghunathan | 2 | The same content is held at SYS-026, SYS-027, SYS-029; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 5 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change a disposition decision directly. | 10 | Moderate | — none; all five Met
DR-36 | RT-18 Specification, standard, analytical method and reference standard control record | SYS-025 — LIMS, QC laboratory | Dr Sunita Raghunathan | 2 | The same content is held at SYS-026, SYS-041, SYS-047; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the specification and method record is what every result in the laboratory is compared against. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-37 | RT-20 Stability protocol and time-point result record | SYS-025 — LIMS, QC laboratory | Dr Sunita Raghunathan | 3 | A comparison with the instance at SYS-026, SYS-034, SYS-035 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the stability record is the evidence on which the expiry period and the storage statement rest. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Attributable
DR-38 | RT-11 Analytical result record | SYS-026 — LIMS, QC laboratory | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-027, SYS-029; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 5 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change a disposition decision directly. | 10 | Moderate | — none; all five Met
DR-39 | RT-18 Specification, standard, analytical method and reference standard control record | SYS-026 — LIMS, QC laboratory | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-041, SYS-047; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the specification and method record is what every result in the laboratory is compared against. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-40 | RT-20 Stability protocol and time-point result record | SYS-026 — LIMS, QC laboratory | Dr Sunita Raghunathan | 3 | A comparison with the instance at SYS-025, SYS-034, SYS-035 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the stability record is the evidence on which the expiry period and the storage statement rest. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Attributable
DR-41 | RT-11 Analytical result record | SYS-027 — Dissolution workstation and data system | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-026, SYS-029; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-42 | RT-11 Analytical result record | SYS-029 — UV-visible spectrophotometer data system | Dr Sunita Raghunathan | 3 | A comparison with the instance at SYS-025, SYS-026, SYS-027 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Attributable
DR-43 | RT-11 Analytical result record | SYS-030 — UV-visible spectrophotometer data system | Dr Sunita Raghunathan | 3 | A comparison with the instance at SYS-025, SYS-026, SYS-027 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Attributable
DR-44 | RT-11 Analytical result record | SYS-031 — FTIR spectrometer data system | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-026, SYS-027; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-45 | RT-11 Analytical result record | SYS-032 — Karl Fischer titrator data system | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-026, SYS-027; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the analytical result is the evidence on which conformance to specification is judged. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-46 | RT-20 Stability protocol and time-point result record | SYS-034 — Stability chamber monitoring system | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-026, SYS-035; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the stability record is the evidence on which the expiry period and the storage statement rest. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | — none; all five Met
DR-47 | RT-20 Stability protocol and time-point result record | SYS-035 — Stability chamber monitoring system | Dr Sunita Raghunathan | 2 | The same content is held at SYS-025, SYS-026, SYS-034; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the stability record is the evidence on which the expiry period and the storage statement rest. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | — none; all five Met
DR-48 | RT-28 Purified water quality monitoring and release record | SYS-038 — Purified water online TOC and conductivity analyser | Dr Sunita Raghunathan | 2 | The same content is held at SYS-054; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 4 | Because purified water is a component, and this record is the evidence that the component conformed. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-49 | RT-18 Specification, standard, analytical method and reference standard control record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 2 | The same content is held at SYS-025, SYS-026, SYS-047; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 4 | Because the specification and method record is what every result in the laboratory is compared against. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | — none; all five Met
DR-50 | RT-21 Out-of-specification investigation record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 3 | A second reading of this record is performed but not on every occasion; an alteration would be visible to an act that happens rather than to one that is routine. | 5 | Because the out-of-specification investigation record is the evidence for the conclusion reached about a failing result. An undetected alteration would change a disposition decision directly. | 15 | High | Legible
DR-51 | RT-38 Deviation, investigation and corrective and preventive action record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 4 | No routine act brings this instance together with another and no second person reads it as a matter of course; an alteration would wait on whatever prompted somebody to look. | 4 | Because the deviation and CAPA record is the evidence of what went wrong and what was done about it. An undetected alteration would change the evidence a quality decision rests on. | 16 | High | Accurate
DR-52 | RT-39 Change control record for GxP systems, equipment and processes | SYS-041 — Electronic quality management system | Terrence Abbatiello | 2 | The same content is held at SYS-047; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 3 | Because the change control record is the evidence that a change to a system, a process or a method was assessed and approved. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | — none; all five Met
DR-53 | RT-40 Annual product review record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 2 | The same content is held at SYS-049; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 2 | Because the annual product review is the periodic evaluation 21 CFR 211.180(e) requires the records be maintained to support. An undetected alteration would degrade a supporting or periodic activity and would not by itself change a disposition. | 4 | Low | Accurate
DR-54 | RT-41 Product complaint record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 3 | A comparison with the instance at SYS-048 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 3 | Because the complaint record is the evidence of what was reported about the product and what was concluded. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 9 | Moderate | Accurate
DR-55 | RT-43 Batch disposition and release record | SYS-041 — Electronic quality management system | Terrence Abbatiello | 2 | The same content is held at SYS-043; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 5 | Because the disposition record is the release decision itself. An undetected alteration would change a disposition decision directly. | 10 | Moderate | — none; all five Met
DR-56 | RT-42 GxP training and qualification record | SYS-042 — Learning management system | Amara Sissoko | 2 | The record is read against the act it records by a second person in the ordinary course of the work; an alteration would not survive that reading. | 2 | Because the training record is the evidence Helix relies on to demonstrate the qualification obligation is met. An undetected alteration would degrade a supporting or periodic activity and would not by itself change a disposition. | 4 | Low | Legible
DR-57 | RT-03 Component dispensing and charge-in record | SYS-043 — Enterprise resource planning system | Amara Sissoko | 2 | The same content is held at SYS-001, SYS-018, SYS-019; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the dispensing and charge-in record evidences the identity and quantity of every component that entered the batch. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | — none; all five Met
DR-58 | RT-07 Labelling issuance, use and reconciliation record | SYS-043 — Enterprise resource planning system | Amara Sissoko | 2 | The same content is held at SYS-003, SYS-004, SYS-005; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the labelling issuance and reconciliation record is the evidence that no unaccounted label left the packaging hall. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-59 | RT-34 Component receipt, quarantine and release status record | SYS-043 — Enterprise resource planning system | Amara Sissoko | 4 | No routine act brings this instance together with another and no second person reads it as a matter of course; an alteration would wait on whatever prompted somebody to look. | 4 | Because the receipt and release status record is the evidence that a component was tested and released before use. An undetected alteration would change the evidence a quality decision rests on. | 16 | High | Original or a true copy
DR-60 | RT-35 Finished product distribution record | SYS-043 — Enterprise resource planning system | Amara Sissoko | 4 | No routine act brings this instance together with another and no second person reads it as a matter of course; an alteration would wait on whatever prompted somebody to look. | 4 | Because the distribution record is what a recall would be executed from. An undetected alteration would change the evidence a quality decision rests on. | 16 | High | Original or a true copy
DR-61 | RT-43 Batch disposition and release record | SYS-043 — Enterprise resource planning system | Amara Sissoko | 3 | A comparison with the instance at SYS-041 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 5 | Because the disposition record is the release decision itself. An undetected alteration would change a disposition decision directly. | 15 | High | Accurate
DR-62 | RT-32 Warehouse continuous temperature and humidity monitoring record | SYS-044 — Warehouse management system | Bernard Kwiatkowski | 2 | The same content is held at SYS-045, SYS-046, SYS-052; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the monitoring record is the evidence that the storage conditions required for the material were held. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Attributable
DR-63 | RT-34 Component receipt, quarantine and release status record | SYS-044 — Warehouse management system | Bernard Kwiatkowski | 2 | The same content is held at SYS-043; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 3 | Because the receipt and release status record is the evidence that a component was tested and released before use. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | — none; all five Met
DR-64 | RT-35 Finished product distribution record | SYS-044 — Warehouse management system | Bernard Kwiatkowski | 2 | The same content is held at SYS-008, SYS-043, SYS-056; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the distribution record is what a recall would be executed from. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy
DR-65 | RT-44 Reserve sample inventory and inspection record | SYS-044 — Warehouse management system | Bernard Kwiatkowski | 2 | The same content is held at SYS-058; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 3 | Because the reserve sample record is the evidence that the retained samples exist and were inspected. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Contemporaneously recorded
DR-66 | RT-18 Specification, standard, analytical method and reference standard control record | SYS-047 — Document management system, controlled procedures and specifications | Terrence Abbatiello | 2 | The same content is held at SYS-025, SYS-026, SYS-041; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the specification and method record is what every result in the laboratory is compared against. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Legible
DR-67 | RT-39 Change control record for GxP systems, equipment and processes | SYS-047 — Document management system, controlled procedures and specifications | Terrence Abbatiello | 2 | The same content is held at SYS-041; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 3 | Because the change control record is the evidence that a change to a system, a process or a method was assessed and approved. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Legible
DR-68 | RT-41 Product complaint record | SYS-048 — Complaint intake and medical information system | Terrence Abbatiello | 3 | A comparison with the instance at SYS-041 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 3 | Because the complaint record is the evidence of what was reported about the product and what was concluded. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 9 | Moderate | Accurate
DR-69 | RT-40 Annual product review record | SYS-049 — Annual product review reporting and analytics system | Terrence Abbatiello | 2 | The same content is held at SYS-041; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 2 | Because the annual product review is the periodic evaluation 21 CFR 211.180(e) requires the records be maintained to support. An undetected alteration would degrade a supporting or periodic activity and would not by itself change a disposition. | 4 | Low | Accurate
DR-70 | RT-05 Equipment cleaning and use log | SYS-050 — Computerised maintenance management system | Bernard Kwiatkowski | 5 | Nothing in the ordinary course compares this record with another instance or with the event it records; there is no act an alteration would have to survive. | 3 | Because the cleaning and use log is the evidence that the equipment was clean and that its use is traceable to a batch. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 15 | High | Contemporaneously recorded, Original or a true copy
DR-71 | RT-19 Analytical instrument calibration record | SYS-050 — Computerised maintenance management system | Bernard Kwiatkowski | 2 | The same content is held at SYS-040; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 3 | Because the calibration record is the evidence that the instrument was reading correctly when the result was taken. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Attributable
DR-72 | RT-25 Environmental monitoring viable-count result record | SYS-053 — Environmental monitoring system, manufacturing | Joachim Reuter | 3 | A comparison with the instance at SYS-037, SYS-039 exists but is not made on every occasion; an alteration would be visible to an act that is performed rather than to one that is routine. | 4 | Because the viable-count result is the evidence of the microbiological state of the area at the time of manufacture. An undetected alteration would change the evidence a quality decision rests on. | 12 | Moderate | Attributable
DR-73 | RT-28 Purified water quality monitoring and release record | SYS-054 — Purified water system control and monitoring | Joachim Reuter | 2 | The same content is held at SYS-038; the two instances are brought together in the ordinary course of the work and an alteration to either would not survive the comparison. | 4 | Because purified water is a component, and this record is the evidence that the component conformed. An undetected alteration would change the evidence a quality decision rests on. | 8 | Moderate | Attributable
DR-74 | RT-35 Finished product distribution record | SYS-057 — Distribution and shipping execution system | Bernard Kwiatkowski | 2 | The same content is held at SYS-008, SYS-043, SYS-044; the instances are brought together in the ordinary course of the work and an alteration to any one of them would not survive the comparison. | 3 | Because the distribution record is what a recall would be executed from. An undetected alteration would change what a reviewer sees of a controlled step without by itself changing a disposition. | 6 | Low | Original or a true copy

## Not scored - ND-01 to ND-47
ID | Record type | System | Owner | Attributes Not determinable | Attributes Not met | What would be needed to determine it
ND-01 | RT-08 Automated packaging inspection and rejection record | SYS-011 — Checkweigher network, packaging hall | Joachim Reuter | Attributable | Accurate | An account administration record showing which named individual held the credential in use at the time of each entry
ND-02 | RT-05 Equipment cleaning and use log | SYS-021 — Clean-in-place skid control system | Joachim Reuter | Contemporaneously recorded | Original or a true copy, Accurate | A record of when the entry was captured as against when the act or measurement it records was performed
ND-03 | RT-05 Equipment cleaning and use log | SYS-022 — Parts washer cycle record system | Joachim Reuter | Contemporaneously recorded | Original or a true copy, Accurate | A record of when the entry was captured as against when the act or measurement it records was performed
ND-04 | RT-12 Chromatographic raw data file and acquisition metadata | SYS-023 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Original or a true copy | Legible | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-05 | RT-13 Chromatographic integration and reprocessing record | SYS-023 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Attributable, Legible, Contemporaneously recorded, Original or a true copy, Accurate | — | An account administration record showing which named individual held the credential in use at the time of each entry; a demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-06 | RT-14 Chromatographic detector spectral and peak-purity record | SYS-023 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-07 | RT-15 Chromatographic calibration curve and result recalculation record | SYS-023 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-08 | RT-17 System suitability test record | SYS-023 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Original or a true copy, Accurate | Legible | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-09 | RT-12 Chromatographic raw data file and acquisition metadata | SYS-024 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Original or a true copy | Legible | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-10 | RT-13 Chromatographic integration and reprocessing record | SYS-024 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Attributable, Legible, Contemporaneously recorded, Original or a true copy, Accurate | — | An account administration record showing which named individual held the credential in use at the time of each entry; a demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-11 | RT-14 Chromatographic detector spectral and peak-purity record | SYS-024 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-12 | RT-15 Chromatographic calibration curve and result recalculation record | SYS-024 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-13 | RT-17 System suitability test record | SYS-024 — Chromatography data system, QC laboratory | Dr Sunita Raghunathan | Accurate | Legible, Original or a true copy | A comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-14 | RT-16 Dissolution profile data set | SYS-027 — Dissolution workstation and data system | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-15 | RT-16 Dissolution profile data set | SYS-028 — Dissolution workstation and data system | Dr Sunita Raghunathan | Attributable, Contemporaneously recorded, Original or a true copy, Accurate | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-16 | RT-11 Analytical result record | SYS-033 — Particle size analyser data system | Dr Sunita Raghunathan | Attributable | Accurate | An account administration record showing which named individual held the credential in use at the time of each entry
ND-17 | RT-27 Differential pressure, temperature and humidity trend record | SYS-034 — Stability chamber monitoring system | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-18 | RT-27 Differential pressure, temperature and humidity trend record | SYS-035 — Stability chamber monitoring system | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-19 | RT-11 Analytical result record | SYS-036 — Laboratory data archive and long-term retention store | Dr Sunita Raghunathan | Legible, Original or a true copy, Accurate | Attributable | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-20 | RT-12 Chromatographic raw data file and acquisition metadata | SYS-036 — Laboratory data archive and long-term retention store | Dr Sunita Raghunathan | Legible, Original or a true copy, Accurate | Attributable | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-21 | RT-13 Chromatographic integration and reprocessing record | SYS-036 — Laboratory data archive and long-term retention store | Dr Sunita Raghunathan | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-22 | RT-25 Environmental monitoring viable-count result record | SYS-037 — Microbiology incubator and plate-count data system | Dr Sunita Raghunathan | Contemporaneously recorded | Original or a true copy, Accurate | A record of when the entry was captured as against when the act or measurement it records was performed
ND-23 | RT-26 Environmental monitoring viable-count trend record | SYS-037 — Microbiology incubator and plate-count data system | Dr Sunita Raghunathan | Attributable, Contemporaneously recorded, Original or a true copy | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-24 | RT-25 Environmental monitoring viable-count result record | SYS-039 — Laboratory environmental monitoring data system | Dr Sunita Raghunathan | Attributable, Contemporaneously recorded, Original or a true copy | Accurate | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-25 | RT-26 Environmental monitoring viable-count trend record | SYS-039 — Laboratory environmental monitoring data system | Dr Sunita Raghunathan | Attributable, Contemporaneously recorded, Original or a true copy | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-26 | RT-19 Analytical instrument calibration record | SYS-040 — Analytical instrument calibration management system | Dr Sunita Raghunathan | Attributable, Original or a true copy, Accurate | Contemporaneously recorded | An account administration record showing which named individual held the credential in use at the time of each entry; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-27 | RT-27 Differential pressure, temperature and humidity trend record | SYS-045 — Warehouse environmental monitoring and mapping system | Bernard Kwiatkowski | Original or a true copy, Accurate | Contemporaneously recorded | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-28 | RT-32 Warehouse continuous temperature and humidity monitoring record | SYS-045 — Warehouse environmental monitoring and mapping system | Bernard Kwiatkowski | Original or a true copy, Accurate | — | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-29 | RT-33 Warehouse temperature excursion search result | SYS-045 — Warehouse environmental monitoring and mapping system | Bernard Kwiatkowski | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-30 | RT-32 Warehouse continuous temperature and humidity monitoring record | SYS-046 — Cold-chain monitoring system, controlled-temperature storage | Bernard Kwiatkowski | Attributable, Original or a true copy, Accurate | Contemporaneously recorded | An account administration record showing which named individual held the credential in use at the time of each entry; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-31 | RT-33 Warehouse temperature excursion search result | SYS-046 — Cold-chain monitoring system, controlled-temperature storage | Bernard Kwiatkowski | Attributable, Contemporaneously recorded, Original or a true copy, Accurate | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-32 | RT-27 Differential pressure, temperature and humidity trend record | SYS-051 — Building management system, manufacturing suites | Joachim Reuter | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-33 | RT-27 Differential pressure, temperature and humidity trend record | SYS-052 — Building management system, warehouse | Joachim Reuter | Contemporaneously recorded, Original or a true copy, Accurate | — | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-34 | RT-32 Warehouse continuous temperature and humidity monitoring record | SYS-052 — Building management system, warehouse | Joachim Reuter | Original or a true copy | Legible | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-35 | RT-26 Environmental monitoring viable-count trend record | SYS-053 — Environmental monitoring system, manufacturing | Joachim Reuter | Original or a true copy, Accurate | Contemporaneously recorded | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-36 | RT-27 Differential pressure, temperature and humidity trend record | SYS-053 — Environmental monitoring system, manufacturing | Joachim Reuter | Original or a true copy, Accurate | Contemporaneously recorded | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-37 | RT-27 Differential pressure, temperature and humidity trend record | SYS-055 — Compressed air and nitrogen quality monitoring system | Joachim Reuter | Attributable, Contemporaneously recorded, Original or a true copy | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-38 | RT-35 Finished product distribution record | SYS-056 — Serialisation repository and reporting system | Bernard Kwiatkowski | Attributable, Original or a true copy, Accurate | — | An account administration record showing which named individual held the credential in use at the time of each entry; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-39 | RT-27 Differential pressure, temperature and humidity trend record | SYS-058 — Reserve sample store monitoring and inventory system | Bernard Kwiatkowski | Attributable, Contemporaneously recorded, Original or a true copy | — | An account administration record showing which named individual held the credential in use at the time of each entry; a record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-40 | RT-44 Reserve sample inventory and inspection record | SYS-058 — Reserve sample store monitoring and inventory system | Bernard Kwiatkowski | Attributable, Original or a true copy, Accurate | Contemporaneously recorded | An account administration record showing which named individual held the credential in use at the time of each entry; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-41 | RT-01 Electronic batch production and control record | SYS-059 — Batch record archive and retention platform | Amara Sissoko | Legible, Original or a true copy | — | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-42 | RT-02 Electronic master production and control record | SYS-059 — Batch record archive and retention platform | Amara Sissoko | Legible, Original or a true copy | — | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy
ND-43 | RT-12 Chromatographic raw data file and acquisition metadata | SYS-060 — Analytical data backup and restore platform, QC laboratories | Amara Sissoko | Legible, Original or a true copy, Accurate | Contemporaneously recorded | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-44 | RT-13 Chromatographic integration and reprocessing record | SYS-060 — Analytical data backup and restore platform, QC laboratories | Amara Sissoko | Original or a true copy, Accurate | Attributable | A statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-45 | RT-11 Analytical result record | SYS-061 — Laboratory data archive and retention store | Amara Sissoko | Legible, Original or a true copy, Accurate | Contemporaneously recorded | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-46 | RT-12 Chromatographic raw data file and acquisition metadata | SYS-061 — Laboratory data archive and retention store | Amara Sissoko | Legible, Original or a true copy, Accurate | Contemporaneously recorded | A demonstration that the record can be rendered from the store that holds it in complete and readable form, with the context needed to understand it; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content
ND-47 | RT-13 Chromatographic integration and reprocessing record | SYS-061 — Laboratory data archive and retention store | Amara Sissoko | Contemporaneously recorded, Original or a true copy, Accurate | Attributable | A record of when the entry was captured as against when the act or measurement it records was performed; a statement of which instance Helix relies on as the original, and a demonstrated method by which a copy of it is shown to be a true copy; a comparison of the record as held against the event or measurement it records, or against an independent instance of the same content