## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-601 | 2027-02-01 | Open Phase 06 and fix its boundary: a depth assessment of SYS-023 and SYS-024 and of nothing else, taking Phase 02's inventory, Phase 03's attribute determinations and Phase 05's control positions as inputs that are read and never re-determined, with no disposition of OBS-2 or OBS-4, no CAPA, no deviation, no remediation plan, no remediation cost, no validation outcome and no retention, backup or archive rule | Lydia Marchetti-Nwosu | — | Steering Committee, EV-601
DEC-602 | 2027-02-03 | Record, before any examination opens, that a depth assessment is an examination and not a disposition. Phase 06 may establish what OBS-2's subject matter consists of and may not draw a disposition from it; the same holds for OBS-4. An examination that concludes is a phase that has taken Phase 08's decision for it | Colm Ó Braonáin | — | EV-602, GOV-26
DEC-603 | 2027-02-05 | SYS-023 and SYS-024 are assessed separately and are never assessed as "the CDS". They are the same product at the same version in two laboratories, and every determination in this phase is made twice or it is not made. No register in this phase carries a column that spans the two | Dr Sunita Raghunathan | ADR-0037 | GOV-26
DEC-604 | 2027-02-05 | Authorise the depth assessment method, fixed before either instance was looked at: what would be read, in what order, and the rule that the enumeration of acts capable of changing a reportable result is completed and recorded before any configuration is read. A cut drawn after the configuration is known is a cut drawn around the configuration | Priyanka Venkataraman | — | GOV-26, EV-603, EV-605
DEC-605 | 2027-02-10 | The audit trail is assessed against the acts that change a reportable result, not against the vendor's event list. A configuration review that ticks off the vendor's classes measures the product; what Helix needs to know is whether the record shows what somebody did to the number that leaves the laboratory | Priyanka Venkataraman | ADR-0038 | GOV-27
DEC-606 | 2027-02-11 | Record the audit trail configuration as read on each instance on 2027-02-10 and recorded on 2027-02-11, as two configurations and not as one, and open AS-41 against the date the reads speak as at | Joachim Reuter | — | EV-608, EV-609, EV-610
DEC-607 | 2027-02-12 | Approve the auditable event register — AE-01 to AE-34 — and accept the configuration finding it computes. Three of the eleven classes recording an act capable of changing a reportable result are enabled on neither instance, and two of those three cannot be enabled at all on this product version. Raise IS-36; open DP-33 for the vendor route on the two | Terrence Abbatiello | — | GOV-27, EV-611, EV-613
DEC-608 | 2027-02-15 | A reprocessed result is compared against the value the first integration produced, and where the record cannot show both, that is recorded against 21 CFR 11.10(e)'s requirement that record changes not obscure previously recorded information. The comparison is the examination; the characterisation of any individual reprocessing is not part of it | Dr Sunita Raghunathan | ADR-0039 | GOV-28
DEC-609 | 2027-02-16 | Fix the examined population and its window: the twelve months to 2027-01-31, 142 reportable results released across the two instances, Ridgemont 86 and Cary 56, with the reprocessed subset identified before any row was examined. The window closes four weeks before the vantage, and the reason is recorded | Dr Sunita Raghunathan | — | EV-614, EV-615
DEC-610 | 2027-02-17 | Approve the reintegration register — RR-01 to RR-38 — and record its counts: 9 of the 38 carry a reported value that differs from the value the first integration produced, and on none of the 38 does the record show both values. Raise IS-38; open DP-34 for the vendor route on retaining the previous value | Priyanka Venkataraman | — | GOV-28, EV-617, EV-619
DEC-611 | 2027-02-18 | The depth of an assessment is stated, and a finding made at depth is never generalised to systems not assessed at that depth. Two of sixty-one systems were assessed at a depth not available for the other fifty-nine, and everything this phase found was invisible to the estate-wide method — so the estate-wide position understates, by an amount nobody can state. Raise IS-41 | Colm Ó Braonáin | ADR-0040 | CSV Working Group, EV-625; ratified at GOV-30
DEC-612 | 2027-02-19 | Record the transfer path on each instance: on SYS-023 the reportable result is transferred to the LIMS electronically; on SYS-024 it is transcribed by hand. Phase 03's IS-18 — the transfer between systems assessed nowhere — lands here, and the provision it lands on is 21 CFR 211.68(b)'s second sentence. Raise IS-39. No corrective action is stated and none is implied | Joachim Reuter | — | EV-622, EV-623
DEC-613 | 2027-02-23 | Phase 06 records what OBS-2's subject matter is and disposes of nothing. The observation stands exactly as written and is not softened, qualified or reduced by anything in this phase; what Phase 06 adds is that beginning to review the audit trail would not, by itself, have reached the act that changes the reportable result. The disposition is Phase 08's | Terrence Abbatiello | ADR-0041 | EV-629; ratified at GOV-30
DEC-614 | 2027-02-24 | Record, from Phase 02's published register and from nothing else, that RT-12 and RT-13 are also held on SYS-036, SYS-060 and SYS-061; that SYS-060 and SYS-061 are owned by Amara Sissoko and not by Dr Sunita Raghunathan; and that none of the three was assessed at depth. Raise IS-40 and hand the three to Phase 07. Establish nothing about any of them, and state no retention, backup or archive rule | Amara Sissoko | — | EV-624; ratified at GOV-30
DEC-615 | 2027-02-25 | A difference between two instances is a finding about the estate, not about either instance. A determination made at one site and reported for both is not false about that site while being false about the estate. Approve the instance comparison register — 24 points, 20 agreements and 4 disagreements — and raise IS-37: the two instances differ in two published registers and were compared in neither | Amara Sissoko | ADR-0042 | GOV-29, EV-621
DEC-616 | 2027-02-25 | Approve the three Phase 06 registers — the auditable event register, the reintegration register and the instance comparison register. IS-35 closes: the position is now known at depth for the two systems where depth was owed, and the closure names its evidence. IS-01 confirmed open and unweighted at the MS-10 gate; nothing in this phase bears on any of its four candidate explanations | Dr Marguerite Oyelaran | — | GOV-30, EV-611, EV-617, EV-621, EV-630
DEC-617 | 2027-02-25 | No reintegration examined in this phase is characterised as proper, improper, justified or unjustified. What is recorded is whether the record can show what happened, and on none of the thirty-eight can it. A record that shows one value cannot distinguish a justified reintegration from an unjustified one, and a characterisation drawn from such a record would be an assertion dressed as a finding | Gideon Halvorsen | ADR-0043 | GOV-30, EV-628
DEC-618 | 2027-02-26 | Publish Phase 06 at MS-10; hand the three registers, the three systems at DEC-614 and the open question to Phase 07, and record IS-42 — the record cannot show what happened, and the data it cannot show it about is retained somewhere. Nobody has established for how long, in what form, or whether the copy that survives is a true one | Lydia Marchetti-Nwosu | — | Steering Committee, EV-634