## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-701 | 2027-03-01 | Open Phase 07 and fix its boundary: the retention position, the backup and restore position and the paper position for the populations Phases 02, 03, 05 and 06 published, taking those registers as inputs that are read and never re-determined, with no retention policy, no retention schedule, no archive design, no migration plan, no period set or proposed for any record type nothing sets one for, no re-opening of the printout route, no disposition of OBS-2 or OBS-4, no CAPA, no deviation, no remediation plan and no remediation cost | Lydia Marchetti-Nwosu | — | Steering Committee, EV-701
DEC-702 | 2027-03-02 | Authorise the derivation method, fixed before any record type was looked at: for each of the 34, read the predicate rule the determination cites, then ask which provision sets a retention period for a record of that kind, and record the answer or its absence. The practice is described after the provision is read and never before, because a period read out of what a system currently does is a description of a configuration wearing the clothes of a requirement | Priyanka Venkataraman | — | GOV-31, EV-703, EV-704
DEC-703 | 2027-03-02 | A retention period is derived from the predicate rule, never chosen. Where the regulation sets the period Helix reads it and records that it read it; where no predicate rule sets one, a named individual decides and the decision is recorded as a decision. Helix has done neither, and the difference between the two failures is the difference between a reading and a decision | Terrence Abbatiello | ADR-0044 | GOV-31, EV-702
DEC-704 | 2027-03-03 | Adopt the source pack for the provisions this phase cites, each retrieved and checked at its primary source: 21 CFR 211.180(a), (b), (c) whole, all three sentences, (d) and (e); 21 CFR 211.186; 21 CFR 211.198(b) whole, including its exempt-OTC fourth sentence; 21 CFR 211.68(b)'s backup limb with its carve-out and the sentence that follows it; 21 CFR 11.10(c) whole; and 21 CFR 11.10(e)'s third sentence. Renew the standing framing for this phase: 21 CFR Part 11 sets no retention period of its own, Part 11 does not define the word *archive*, enforcement discretion is not an exemption, and there is no Part 11 certification | Rebekah Sandquist | — | EV-705, EV-704
DEC-705 | 2027-03-05 | A record not specifically associated with a batch is not reached by 21 CFR 211.180(a)'s period, and the programme records that rather than applying the period by analogy. The operative words are the regulation's and they do the whole job: a record that spans batches is not brought inside (a) by resembling a record that does not | Dr Marguerite Oyelaran | ADR-0045 | GOV-31, EV-702
DEC-706 | 2027-03-08 | Record the 34 derivations one record type at a time, on 34 separate derivation records, each naming the predicate rule read, the provision that sets a period or the absence of one, and — where none does — a reason specific to that record type and not a formula. Fix the group labels A, B and C as labels for three positions and not as a grading | Priyanka Venkataraman | — | EV-706, EV-709
DEC-707 | 2027-03-09 | Approve the retention derivation register — RD-01 to RD-34 — and accept the partition it computes: 17 record types take their period from 21 CFR 211.180(a), 3 from another predicate-rule provision, and 14 from nothing. 17 + 3 + 14 = 34, reconciling across the systems column to Phase 03's 121 pairs. IS-14 closes and splits: for 20 record types the period is set by regulation and Helix never wrote it down; for 14 a decision is owed and nobody has taken it. Raise IS-44 and IS-45; open DP-38, AS-48; set no period for any of the 14 | Terrence Abbatiello | — | GOV-32, EV-707, EV-708, EV-710
DEC-708 | 2027-03-09 | A determination that a record is not a Part 11 record is not a determination that it is unregulated. Phase 02's printout route holds for RT-09, RT-22, RT-23 and RT-29, was correctly applied and is not disturbed. What the route did was move those four out of 21 CFR Part 11 and into 21 CFR 211.180, where the paper is the record required under Part 211 — and the four are followed there | Priyanka Venkataraman | ADR-0046 | GOV-32, EV-726
DEC-709 | 2027-03-10 | Record the retention estate from Phase 02's published register and from nothing else: SYS-036, SYS-059, SYS-060 and SYS-061, with their sites, their named individual owners and their route into the inventory. Three of the four are owned by the Chief Information Officer, none by the quality unit, and SYS-061 entered the inventory by walk. 21 CFR 211.180(c) requires records to be readily available for authorised inspection during the retention period, and no individual is named as accountable for that availability on any of the four. Raise IS-47 | Amara Sissoko | — | EV-711, EV-712
DEC-710 | 2027-03-11 | Record the 21 CFR 211.180(c) location position: SYS-060 sits in the Ridgemont data centre and holds RT-12 and RT-13, which are generated at both sites — Ridgemont on SYS-023 and Cary on SYS-024. The saving in (c)'s final sentence applies to records that "can be immediately retrieved from another location by computer or other electronic means", and no retrieval from Cary has been demonstrated, timed or recorded. Raise IS-48; open DP-39, AS-51. No corrective action is stated and none is implied | Joachim Reuter | — | EV-713, EV-714, EV-715
DEC-711 | 2027-03-12 | A backup that has never been restored is recorded as a backup and never as a control. A file whose readability, completeness and correspondence to the record it was taken from have never been established is a claim about a file. Recording it as a control over a record asserts a property nobody has tested | Amara Sissoko | ADR-0047 | GOV-33, EV-722
DEC-712 | 2027-03-12 | Approve the backup and restore register — BR-01 to BR-61 — and accept its counts: a backup file is maintained on 54 of the 61 and 7 have none; a restore has been performed on 4, every one of them incident recovery rather than a test; on none of the 4 was what came back compared with what went in; and on 0 of the 61 has the 21 CFR 211.68(b) carve-out determination been made. Raise IS-46; open DP-40, AS-49, AS-50 | Colm Ó Braonáin | — | GOV-33, EV-717, EV-718, EV-720
DEC-713 | 2027-03-16 | 21 CFR 211.68(b)'s backup requirement is conditional, and the condition is determined per record type rather than assumed. The paragraph requires a backup file *"except where certain data, such as calculations performed in connection with laboratory analysis, are eliminated by computerization or other automated processes"*, and in those instances requires instead a written record of the program with appropriate validation data. Which limb reaches which Helix record type is a determination nobody has made, and it is owed by the holder of the obligation | Colm Ó Braonáin | ADR-0048 | EV-721; ratified at GOV-35
DEC-714 | 2027-03-17 | Approve the paper record register — PP-01 to PP-04 — and accept its counts: on none of the four is a retention location stated, an individual accountable named, a period derived or a reproduction made under 21 CFR 211.180(d); the medium is thermal on three of the four; and Helix holds a statement of the medium's archival life from no source. Record that RT-09 is an in-process control result specifically associated with a batch, so 21 CFR 211.180(a)'s period attaches to the paper. Raise IS-49; open DP-42. Phase 02's route is not re-opened | Priyanka Venkataraman | — | GOV-34, EV-725, EV-727
DEC-715 | 2027-03-18 | Where a Phase 05 determination was made against an obligation with no endpoint, that is recorded and the cell stands. 21 CFR 11.10(c) is *"Protection of records to enable their accurate and ready retrieval throughout the records retention period."* 24 of the 61 systems hold at least one record type for which no predicate rule sets a period; Phase 05 recorded (c) as Met on 44 of the 61; and 13 of those 44 are among the 24. Raise IS-43. Phase 07 re-determines nothing: the thirteen cells stand exactly as Phase 05 published them, each having been made on the published method against the facts then established | Terrence Abbatiello | ADR-0049 | GOV-35, EV-728, EV-729
DEC-716 | 2027-03-18 | Record the audit trail retention position read across the 61 on 2027-03-10: a fixed retention window is configured on 26 systems; on 11 of those the window is shorter than the longest derived period of a record type the system holds; and on 16 systems every in-scope record type held falls in Group C, so 21 CFR 11.10(e)'s relation has no second term at all. IS-05 closes on the limb that is now derivable, and the remainder is IS-44's. 21 CFR Part 11 sets no period of its own and none is stated here | Joachim Reuter | — | GOV-35, EV-730, EV-731
DEC-717 | 2027-03-18 | Phase 07 states no retention policy and no archive design. It establishes what the regulation requires and what Helix holds, and stops there. IS-42 closes — the question of for how long, in what form and whether the copy that survives is a true one is answered in part and its unexamined limb becomes IS-50. IS-01 confirmed open and confirmed unweighted at the MS-11 gate, and no candidate explanation is named, by number or by content | Dr Marguerite Oyelaran | ADR-0050 | GOV-35, EV-732, EV-733
DEC-718 | 2027-03-19 | Publish Phase 07 at MS-11; hand the three registers, the three closures and the standing dispositions of OBS-2 and OBS-4 to Phase 08, and record IS-50 — everything now has a period, an owner or an explicit gap where one of those is missing, and not one of the arrangements has ever been examined by anybody at Helix whose job it was to look | Lydia Marchetti-Nwosu | — | Steering Committee, EV-736