## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-101 | 2026-03-02 | Establish the Helix Pharma, Inc. Data Integrity Programme; appoint Lydia Marchetti-Nwosu Programme Manager; open Phase 01 | Dr Marguerite Oyelaran | — | Sponsor authorisation, EV-101
DEC-102 | 2026-03-06 | Approve the programme charter — scope, OBJ-01 to OBJ-08, the $3,600,000 envelope with $3,412,000 committed across ten lines, 9.2 FTE-equivalents, close-out 2027-04-30 — and create the Data Integrity Lead post reporting to Quality and not to IT | Dr Marguerite Oyelaran | ADR-0002 | GOV-01
DEC-103 | 2026-03-06 | Review and release Helix's written response to the Form FDA 483 of 2026-02-13, and adopt the fifteen-business-day response undertaking as Helix's own procedural commitment | Rebekah Sandquist | — | GOV-03
DEC-104 | 2026-03-13 | Determine Part 11 applicability record by record, not system by system | Priyanka Venkataraman | ADR-0001 | GOV-02
DEC-105 | 2026-03-13 | Constitute the four governance bodies with their cadences and chairs; hold the inaugural Data Integrity Steering Committee | Dr Marguerite Oyelaran | — | GOV-02
DEC-106 | 2026-03-20 | Assign named individual owners to OBJ-01 to OBJ-08 and fix each measure so that it is readable from an artefact | Lydia Marchetti-Nwosu | — | Steering Committee action, EV-107
DEC-107 | 2026-03-27 | Record enforcement discretion as a fact about FDA's stated intentions and never use it as a reason to do less; work to the predicate rule obligation at 21 CFR 211.68 | Terrence Abbatiello | ADR-0003 | Quality Council, EV-110
DEC-108 | 2026-04-03 | Engage Thorne Delacroix Consulting, LLC for data integrity and CSV advisory, with audit and assessment of its own work expressly excluded from scope | Dr Marguerite Oyelaran | — | EV-118
DEC-109 | 2026-04-10 | Adopt the three-way separation — the party that designs remediation, the party that executes it and the party that audits it are three different parties, and no party audits its own work | Gideon Halvorsen | ADR-0004 | Steering Committee, EV-111
DEC-110 | 2026-04-17 | Engage Vashti Okonjo & Partners for the independent third-party audit, with design, drafting and implementation excluded from its scope | Gideon Halvorsen | — | EV-119
DEC-111 | 2026-04-24 | Adopt the regulatory scoping determination: Parts 210 and 211 apply; Part 11 applies to a subset of records; Part 820 does not apply; EU GMP Annex 11, January 2011, reaches the EU-facing products through the Qualified Person and not through FDA | Dr Marguerite Oyelaran | — | GOV-04
DEC-112 | 2026-04-24 | Adopt FDA's Computer Software Assurance guidance voluntarily as good practice, and label it as adopted rather than required every time it is cited | Colm Ó Braonáin | ADR-0005 | GOV-04
DEC-113 | 2026-05-01 | Adopt NIST SP 800-53 Revision 5 as a control catalogue Helix chose — with no FIPS 199 categorization, no baseline and no authorization, because Helix is not a federal system | Amara Sissoko | — | Steering Committee, EV-112
DEC-114 | 2026-05-08 | Report the inspectional observations in the 483's own numbering, OBS-1 to OBS-7, and never renumber them | Rebekah Sandquist | ADR-0006 | Steering Committee, EV-113
DEC-115 | 2026-05-08 | Record the link between an inspectional observation and any deviation raised in response, keeping both identifiers distinct; a 483 observation never becomes a deviation | Terrence Abbatiello | — | Quality system procedure change, EV-114
DEC-116 | 2026-05-15 | Adopt the obligations register O1 to O12 with named owners and evidence, and record O2, O4 and O8 as open gaps on Helix's own assessment | Rebekah Sandquist | — | Steering Committee, EV-115
DEC-117 | 2026-05-19 | Publish the internal audit history in full. Four internal audits between 2023-06 and 2025-09 covered all three systems between them — each system falling inside the scope of at least two — and none raised a finding on the subject matter of OBS-2, OBS-4 or OBS-6 | Gideon Halvorsen | ADR-0007 | GOV-05
DEC-118 | 2026-05-19 | Raise IS-01, set out the candidate explanations without choosing between them, and defer the question to Phase 08 | Gideon Halvorsen | — | GOV-05
DEC-119 | 2026-05-27 | No control, procedure or record is owned by a team; every one has a named individual owner | Lydia Marchetti-Nwosu | ADR-0008 | Steering Committee, EV-116
DEC-120 | 2026-05-29 | Adopt the programme calendar CAL-01 to CAL-12 and the milestone set MS-01 to MS-13; record IS-04 against CAL-06 rather than assign it a cadence | Lydia Marchetti-Nwosu | — | Steering Committee, EV-117