## RAID
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
PR-01 | Committed scope exceeds the envelope because remediation reveals work the estimate did not carry | Lydia Marchetti-Nwosu | $56,000 contingency, drawn by the programme manager and reported; $188,000 headroom, released only by the sponsor | OBJ-07, GOV-01
PR-02 | The 9.2 FTE-equivalents are funded but not released, because every named owner holds a substantive role alongside the programme | Dr Marguerite Oyelaran | Monthly review at CAL-01; no team is accepted as a substitute for a named owner — ADR-0008 | AS-02
PR-03 | The Phase 02 determination overruns, because the estate carries no attribute identifying which systems hold predicate-rule records | Priyanka Venkataraman | Targeted technical review sequenced ahead of enumeration; AS-03 reviewed at the MS-06 gate | IS-03, AS-03
PR-04 | The assurance tail compresses — a slip in MS-11 or in CAL-10 pushes MS-12 into close-out, where there are 21 days | Lydia Marchetti-Nwosu | Sequence fixed at 01.11 §7; the audit window sits after the remediation it audits and is booked well in advance of it | DP-06, AS-12
PR-05 | Determinations require technical cooperation the Data Integrity Lead cannot compel, and requests queue behind operational work | Priyanka Venkataraman | Escalation directly to the sponsor without passing through IT — 01.07 §7 | DP-03, ADR-0002
PR-06 | Advisory scope drifts into work the independent third-party auditor must later audit | Gideon Halvorsen | Scope fixed at DEC-108 with audit excluded, and at DEC-110 with design and drafting excluded; the boundary is reviewed at CAL-01 | ADR-0004, AS-09
PR-07 | A vendor is treated as supplying compliance rather than features that support it, and a validation obligation is assumed to have been discharged by procurement | Colm Ó Braonáin | Every validation package states Helix's intended use and Helix's evidence. There is no Part 11 certification and no vendor claim is evidence of Helix's validated state | O1, OBJ-02
PR-08 | Enforcement discretion is read inside Helix as permission to defer validation | Terrence Abbatiello | ADR-0003 is standing framing; every validation package cites the obligation at 21 CFR 211.68(b) and not Part 11 | DEC-107, O1
PR-09 | A cadence, threshold or control is adopted because a guidance document suggests it, and is then reported internally as a requirement | Rebekah Sandquist | CAL-12 quarterly horizon scan; GAMP 5 and FDA's Computer Software Assurance guidance are labelled adopted, never required | ADR-0005, 01.05
PR-10 | Key-person concentration. The Data Integrity Lead and the CSV Lead are each a single holder on the critical path, and one of the two posts was created by this programme | Dr Marguerite Oyelaran | None agreed at the vantage. Proposal action open, no date set | AS-02, 01.07 §1