## Regulatory obligations
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
O1 | Exercise appropriate controls over computer or related systems so that changes in master production and control records or other records are instituted only by authorised personnel; check input and output for accuracy at a degree and frequency based on the complexity and reliability of the system; maintain backup data that are exact, complete and secure from alteration, inadvertent erasure or loss | 21 CFR 211.68(b) | Colm Ó Braonáin | Approved validation package per GxP-critical platform with an intended-use statement; change control evidence; a documented input/output verification basis; backup and restore evidence | In force — OBJ-02, Phase 04
O2 | Use secure, computer-generated, time-stamped audit trails that independently record the date and time of operator entries and actions that create, modify or delete electronic records; record changes shall not obscure previously recorded information; retain such audit trail documentation for a period at least as long as that required for the subject electronic records, and keep it available for agency review and copying | 21 CFR 11.10(e) | Joachim Reuter | Per-system configuration record; a dated retrieval demonstration; a retention statement expressed against the retention period of the underlying record | Open gap — IS-05, OBJ-04
O3 | Review and approve all production and control records by the quality unit | 21 CFR 211.192 | Terrence Abbatiello | Approved review procedure stating what the reviewer must examine, including the position on the associated audit trail; completed review records | In force — procedure revision is OBJ-06
O4 | Record the initials or signature of a second person showing that the original laboratory records have been reviewed for accuracy, completeness and compliance with established standards | 21 CFR 211.194(a)(8) | Dr Sunita Raghunathan | Approved laboratory record review procedure stating the audit trail position expressly; completed second-person review records | Open gap — IS-06, OBJ-06
O5 | Prepare batch production and control records for each batch, including documentation that each significant step was accomplished and identification of the persons performing, supervising or checking each significant step | 21 CFR 211.188 | Bernard Kwiatkowski | Master and executed batch records; the record of who performed, supervised or checked each significant step | In force — the electronic batch record's contribution is assessed in Phase 02
O6 | Maintain written records so that the data in them can be used for evaluating, at least annually, the quality standards of each drug product | 21 CFR 211.180(e) | Terrence Abbatiello | The annual evaluation procedure and the completed evaluations, with the data source identified per input | In force
O7 | Maintain a quality unit with the responsibility and authority the section confers, and keep its responsibilities and procedures in writing and follow them | 21 CFR 211.22 | Dr Marguerite Oyelaran | The quality unit's written responsibilities and procedures, current and under document control | In force
O8 | Limit system access to authorised individuals | 21 CFR 11.10(d) | Amara Sissoko | Account register; periodic access review records; joiner, mover and leaver evidence; for any account that cannot be individualised, a documented technical constraint and a named compensating-control owner | Open gap — related to the subject matter of OBS-4; OBJ-05
O9 | Determine that persons who develop, maintain or use electronic record and electronic signature systems have the education, training and experience to perform their assigned tasks | 21 CFR 11.10(i) | Priyanka Venkataraman | Role-based training matrix; completion records held against named individuals | In force, scope pending — CAL-08
O10 | Establish and adhere to written policies that hold individuals accountable and responsible for actions initiated under their electronic signatures | 21 CFR 11.10(j) | Terrence Abbatiello | The approved policy and individual acknowledgements | In force, scope pending
O11 | Ensure that signed electronic records carry the printed name of the signer, the date and time the signature was executed, and the meaning associated with the signature, and that all three appear in any human readable form of the record | 21 CFR 11.50 | Colm Ó Braonáin | Per-system evidence that a human readable form of a signed record carries all three elements | In force, scope pending
O12 | Support the EU authorisation holder's Qualified Person in meeting the Annex 11 expectations that reach Helix's EU-facing products. Helix holds no EU manufacturing or import authorisation and has no Qualified Person of its own; Dr Anselm Ferrão acts for the authorisation holder and not for Helix | EU GMP Annex 11, January 2011 version. Not an FDA obligation, not a predicate rule, and not a direct obligation on Helix | Rebekah Sandquist | The information and access Helix supplied, and the authorisation holder's record of satisfaction for the EU-facing products | In force — DP-08; route and version at ../01.05-what-does-not-apply.md §6