## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-401 | 2026-10-01 | Open Phase 04 and fix its boundary: a framework that states what evidence every system must produce, with no validation outcome, no control position, no access design, no audit trail configuration and no retention rule, and with Phase 03's two registers taken as an input that is never re-scored | Lydia Marchetti-Nwosu | — | Steering Committee, EV-401
DEC-402 | 2026-10-06 | Record that no regulation and no FDA guidance requires a validation framework, a validation master plan or a validation policy. What is required is written procedures — 21 CFR 211.100(a), 21 CFR 211.22(d) and 21 CFR 211.68(a)'s written program designed to assure proper performance. The framework is the instrument Helix chose | Colm Ó Braonáin | — | Steering Committee, EV-402
DEC-403 | 2026-10-09 | The framework document states in its own first section that nothing requires it to exist. A policy that opens by implying it is compelled has misdescribed its own authority before it says anything else, and under 21 CFR 211.22(d) a chosen procedure is enforceable against Helix exactly as a required one would be | Colm Ó Braonáin | ADR-0023 | GOV-16
DEC-404 | 2026-10-13 | Adopt the system as the unit of the framework, while the record type on the system remains the unit of assessment — ADR-0016. A validation plan is written for a thing that can be validated, and that is a system; the records it holds determine what the plan must evidence | Colm Ó Braonáin | — | CSV Working Group, EV-404
DEC-405 | 2026-10-16 | 21 CFR 11.10(a)'s four clauses are specified and evidenced separately, and the fourth — the ability to discern invalid or altered records — is specified explicitly rather than assumed to follow from the first three. A validation package proving a system calculates correctly and behaves consistently has addressed three of the four | Colm Ó Braonáin | ADR-0024 | GOV-17
DEC-406 | 2026-10-16 | Authorise the reading of the 44 validation packages against the four clauses, with the reading rule fixed before the first package was opened: a package addresses a clause where it carries a specified requirement, a test directed at it and a recorded result. Two of the three is not enough, and a summary report's conclusion is not evidence of anything | Colm Ó Braonáin | — | GOV-17, CSV Working Group, EV-406
DEC-407 | 2026-10-22 | Assess complexity and reliability on three observable features — configuration, interfaces and failure history — and record the basis on every determination. Refuse a determination made from a system's name, its cost or its vendor | Amara Sissoko | — | CSV Working Group, EV-407
DEC-408 | 2026-10-27 | Two graduations, never merged and never averaged. Data integrity risk sets the depth at which each of 21 CFR 11.10's eleven paragraphs is evidenced in respect of the record and removes no paragraph; system complexity and reliability sets the degree and frequency of input/output verification under 21 CFR 211.68(b), and nothing else under that provision, Helix's further use of the same band as one of two inputs to evidence depth being its own method choice and not made under 21 CFR 211.68(b). Neither is derived from the other and where they disagree the higher governs. DP-15 closes | Joachim Reuter | ADR-0025 | GOV-18
DEC-409 | 2026-10-29 | Record the data integrity position as *Not established* where a system carries at least one pair in the unscored register, and refuse to assign it a provisional band for framework purposes. Rigour on those systems is set by complexity and reliability alone. Raise IS-27 | Priyanka Venkataraman | — | Steering Committee, EV-409
DEC-410 | 2026-11-02 | Approve the system rigour register — 61 rows, two grading columns, and no mean, weighted mean, index, tier or score taken anywhere; neither determination is edited by the other. The sixth column, the resulting rigour, is a derived value and not a third determination. Record that the two grading columns use different band vocabularies so that a merge is not available to somebody working quickly. Raise IS-26 | Colm Ó Braonáin | — | GOV-18, EV-412
DEC-411 | 2026-11-04 | FDA's Computer Software Assurance guidance and GAMP 5 Second Edition are adopted voluntarily and labelled as adopted at every citation, and neither is ever cited as a requirement. CSA is device guidance under 21 CFR Part 820, as amended by the Quality Management System Regulation, and does not apply to Helix; GAMP 5 is ISPE good-practice guidance. No software-category count is published | Terrence Abbatiello | ADR-0026 | GOV-16
DEC-412 | 2026-11-06 | Record IS-22 — no validation package Helix holds evidences 21 CFR 11.10(a)'s fourth clause — and IS-23 — 17 of the 61 systems have no validation package at all. Record that both are statements about coverage and neither is a control position | Colm Ó Braonáin | — | Steering Committee, EV-422
DEC-413 | 2026-11-09 | Authorise the reading of the 63 procedures in scope against the 38 obligations, performed by the quality unit and reviewed by the Data Integrity Lead, with the three-way classification fixed before the reading opened. Neither of the two owns the validation framework, which is why they were asked | Terrence Abbatiello | — | EV-417
DEC-414 | 2026-11-11 | Every obligation lands in a named procedure, or is recorded as landing nowhere. An obligation with no home is published, not absorbed, and a register row whose landing column is empty is a defective row | Priyanka Venkataraman | ADR-0027 | GOV-19
DEC-415 | 2026-11-13 | Approve the obligation register — OB-01 to OB-38, 14 from the 74 scored pairs, 19 from the 47 unscored and 5 from the method's own recorded gaps — and record that the pairs Helix could not assess generate more obligations than the pairs it could, because determining an attribute is work | Priyanka Venkataraman | — | GOV-19, EV-413
DEC-416 | 2026-11-17 | Record IS-24 — 12 obligations land in a procedure that exists and does not require the act — and IS-25 — 5 obligations land in no procedure at all | Terrence Abbatiello | — | Steering Committee, EV-418, EV-419
DEC-417 | 2026-11-19 | A procedure that exists and does not require the act is recorded as a distinct class of gap from a procedure that does not exist, because only the second is visible to the question *"is there a procedure?"* An auditor asked that question gets a yes on all twelve | Terrence Abbatiello | ADR-0028 | GOV-19
DEC-418 | 2026-11-20 | Approve the validation policy, the framework document and the SOP set of nine — four new and five amendments — and record that not one of the nine has been applied to anything at this vantage | Dr Marguerite Oyelaran | — | GOV-19, EV-426 to EV-428
DEC-419 | 2026-11-24 | Refuse a fourth documentary level of work instructions. Every level Helix writes is a level Helix is held to — under 21 CFR 211.22(d) for the quality control unit's own procedures, 21 CFR 211.100(b) for production and process control procedures and 21 CFR 211.160(a) for laboratory control mechanisms, and which of the three bites depends on which procedure it is — and a level existing to restate the level above it doubles the surface without adding an act | Terrence Abbatiello | — | CSV Working Group, EV-429
DEC-420 | 2026-11-25 | The framework states what evidence is required and states no control position. Whether any paragraph of 21 CFR 11.10 is met, for any system, is Phase 05's. IS-21 closes — the quality system now says what Helix must do | Colm Ó Braonáin | ADR-0029 | GOV-20
DEC-421 | 2026-11-26 | Confirm IS-01 open and unweighted at the MS-08 gate, and record that this phase's general argument about a procedure that does not require an act bears on none of the four candidate explanations and may not be cited in support of any of them | Gideon Halvorsen | — | GOV-20, EV-437
DEC-422 | 2026-11-30 | Publish Phase 04 at MS-08; hand the framework, the obligation register and the system rigour register to Phase 05, and record IS-28 — the framework says what evidence every system must produce, nothing has produced any of it yet, and the first paragraph of 21 CFR 11.10 a system will be measured against is the one nobody has ever evidenced | Lydia Marchetti-Nwosu | — | Steering Committee, EV-440