## Issues
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
IS-22 | Not one of the forty-four packages contains a requirement stated in the terms of 21 CFR 11.10(a)'s fourth clause, with a test directed at it and a recorded result. Helix holds 44 validation packages. All 44 address accuracy, all 44 address reliability, 41 address consistent intended performance, and none addresses the ability to discern invalid or altered records. The reading rule required a specified requirement, a test directed at it and a recorded result, and two of the three was not enough. Some of the forty-four contain audit trail functional testing that could be attributed to the fourth clause; none attributes it, and an evidence set in which no item is attributed to the clause cannot be reported as addressing it — ADR-0024. Whether such an item, once attributed, satisfies the clause is Phase 05's. This is a statement about what the packages cover and it is not a control position: nothing here says that 21 CFR 11.10(a), or any paragraph of 21 CFR 11.10, is or is not met for any system. A package that does not address a clause is not a package that fails it — it is a package whose scope did not extend there, and no package is withdrawn, invalidated or superseded. The clause is also exactly the property whose absence made *original or a true copy* undeterminable on 41 pairs in Phase 03, and the two findings are the same finding seen from two ends | Colm Ó Braonáin | 2026-11-06 | Open — OB-37 and OB-38 are the acts; SOP-DI-01 is the document; the evidence does not exist and Phase 05 assesses the control position | DEC-406, DEC-412, ADR-0024, GOV-17, ../04.03-the-fourth-clause.md, ../04.07-the-packages-helix-already-holds.md, IS-15, IS-28, PR-27
IS-23 | 17 of the 61 systems have no validation package at all. 44 + 17 = 61. Eleven of the seventeen are the eleven systems the physical walk found inside the 61, none of which had ever entered a validation lifecycle — IS-13. The other six were in the register and nobody had to find them: they entered the estate as storage, as backup, as instrumentation on a utility or as a facilities control system, and the question *is this a computerised system holding a GxP record* was never asked of any of them. Sixteen of the seventeen also have no established data integrity position, so on those sixteen Helix holds neither a package nor a determined position about the records. This is a statement about the absence of a package and not about the condition of any system. Unassessed is not adverse | Colm Ó Braonáin | 2026-11-06 | Open — every one of the seventeen carries a rigour band and a place in the obligation register, and the plans that would produce evidence for them open after this vantage on DP-05 | DEC-412, IS-13, IS-27, PR-17, PR-27, ../04.07-the-packages-helix-already-holds.md, DP-05, DP-21
IS-24 | 12 obligations land in a procedure that exists and does not require the act. Each of the twelve arrives at a document that exists, is controlled, is current, has a named owner and covers the subject matter — and does not contain the sentence obliging anybody to perform the act. A procedure that exists and does not require the act is worse than a procedure that does not exist, because an auditor who asks "is there a procedure?" gets a yes, and the yes is accurate and is the end of the enquiry. Only the five at IS-25 are visible to that question. The mechanism has operated once at Helix already and the record is published: IA-2025-01/F3 raised what the procedure that existed allowed to be raised and closed it there, and IS-03 re-raised the same gap against the determination that did not exist. Nothing in this entry says that any past audit should have found any of the twelve, and nothing in it bears on IS-01 | Terrence Abbatiello | 2026-11-17 | Open — SOP-DI-01, SOP-DI-02, SOP-DI-04, SOP-DI-07 and SOP-DI-08 are the routes, worked from ../04.09-the-policy-architecture.md §3, and none has been applied to anything | DEC-416, DEC-417, ADR-0028, GOV-19, ../04.08-where-the-obligations-land.md, IS-03, IS-25, DP-22, PR-30
IS-25 | 5 obligations land in no procedure at all. OB-11, OB-18, OB-25, OB-29 and OB-35. Four of the five concern a record whose existence is not the same thing as its retrievability — a record in an archive, a record produced by reprocessing, a record rendered from a query — and Helix's procedure estate is built around records that a person enters and files, with no vocabulary for a record a system produces on demand. The fifth, OB-35, is the only obligation in the register that arises from a shall and lands nowhere: 21 CFR 211.68(b) requires the degree and frequency of input/output verification to be based on the complexity and reliability of the system, OB-34 now produces that band, and nothing requires anybody to size anything from it | Priyanka Venkataraman | 2026-11-17 | Open — SOP-DI-01, SOP-DI-03, SOP-DI-08 and SOP-DI-09 are the routes, worked from ../04.09-the-policy-architecture.md §3; none has been applied | DEC-416, ADR-0027, ADR-0028, GOV-19, ../04.08-where-the-obligations-land.md, IS-24, IS-08, DP-22, PR-30
IS-26 | The two graduations disagree on 17 of the 36 systems where they can be compared. They agree on 19. 19 + 17 = 36, and the comparison is possible only on the 36 with an established data integrity position. Where they disagree the framework requires the higher of the two rather than a mean — ADR-0025. Complexity and reliability is the higher on twelve and data integrity risk on five, and the five are the ones to notice: on SYS-029 to SYS-032 and on SYS-050 the record is graver than the system, and a framework that graded systems and not records would have set the lowest rigour in the estate on precisely those five. This entry does not close by the disagreement being resolved. The two columns stay two, the disagreement is retained on the register row, and the higher governs | Joachim Reuter | 2026-11-02 | Open, and open by design — it is a standing property of keeping two graduations, not a defect awaiting correction | DEC-408, DEC-410, ADR-0025, GOV-18, ../04.04-two-graduations.md, system-rigour-register.md, IS-27, PR-29
IS-27 | 25 systems have no established data integrity position, so their rigour is set by complexity and reliability alone until they are determined. A system's position is *Not established* exactly when at least one of its pairs carries an ND identifier, and for no other reason. 36 + 25 = 61. The 47 unscored pairs sit on exactly these 25. They were not given a provisional band for the framework's convenience, and a sentence assigning them one was available and was refused at DEC-409: it would have reversed ADR-0018 in a phase not entitled to reverse it, and would have given twenty-five systems a position derived from nothing. Setting rigour from complexity and reliability alone is a lawful basis and an incomplete one — 21 CFR 211.68(b) graduates input/output verification and says nothing about the record, so the column that is missing is the one that would say what evidence is required about the record | Priyanka Venkataraman | 2026-10-29 | Open — the nineteen obligations at OB-15 to OB-33 are the acts; DP-16, DP-17 and DP-20 are the evidence routes, and they run through Phases 05, 06 and 07 | DEC-409, ADR-0018, ADR-0025, ../04.04-two-graduations.md, system-rigour-register.md, IS-16, IS-23, IS-26, DP-16, DP-17, DP-20, PR-28
IS-28 | The question Phase 04 leaves open, and it is Phase 05's: the framework says what evidence every system must produce. Nothing has produced any of it yet, and the first paragraph of 21 CFR 11.10 a system will be measured against is the one nobody has ever evidenced. The framework requires a system validation plan for each of the 61 systems and not one has been written. Every plan must specify the evidence for each of the eleven paragraphs (a) to (k), and the first of those is (a), whose fourth clause requires the ability to discern invalid or altered records — which not one of the 44 packages addresses, on systems that in seventeen cases hold no package at all. The framework did not create that position; it made it legible, which is the most a framework can do. Not one of the 38 obligations has been performed and not one of the nine SOPs has been applied to anything | Colm Ó Braonáin | 2026-11-30 | Open — Phase 05 owns the first half, MS-09, 2027-01-29. DP-05 is the resource on which the plans open | DEC-422, ADR-0029, GOV-20, ../04.13-phase-summary-and-transition.md, IS-21, IS-22, IS-23, DP-05, DP-21, PR-34

## Assumptions
Col 1 | Col 2 | Col 3 | Col 4
AS-27 | Load-bearing on every complexity-and-reliability band. The three features the determination reads — configuration, interfaces and failure history — are sufficient to grade a system on the axis 21 CFR 211.68(b) names, so that two systems in the same band call for input/output verification of the same degree and frequency | Colm Ó Braonáin | The second graduation grades something other than what the regulation names, and the shall at 21 CFR 211.68(b) is discharged against the wrong property on all 61 systems
AS-28 | The 61 systems and the 121 pairs remain the population to MS-09: no ADR-0015 trigger and no ADR-0022 trigger fires between this vantage and 2027-01-29 that adds a system, removes one, or changes which system holds a record type | Amara Sissoko | The rigour register describes an estate that no longer exists, and 61 validation plans are sized against it
AS-29 | The 63 procedures read at EV-417 are the whole of the procedure estate that bears on the 38 obligations, so that a landing of *nowhere* reflects the absence of a procedure rather than the absence of a search | Terrence Abbatiello | The five at IS-25 become a place difficult obligations were put rather than a population with a closure condition, which is the failure mode AS-23 guards against for the 47
AS-30 | The 44 validation packages read at EV-421 are the whole of what Helix holds, and no package exists outside the controlled repository that addresses the fourth clause | Colm Ó Braonáin | IS-22 is wrong in Helix's favour, and a coverage statement published as a finding turns out to be a statement about where somebody looked
AS-31 | The nine SOPs, the policy and the framework are issued into the quality system under document control with their named owners, and are not varied outside change control | Terrence Abbatiello | Nine written procedures Helix can be found not to have followed become nine written procedures Helix cannot say the content of — under 21 CFR 211.22(d) for the quality control unit's own procedures, 21 CFR 211.100(b) for production and process control procedures and 21 CFR 211.160(a) for laboratory control mechanisms, and which of the three bites depends on which procedure it is — PR-32
AS-32 | The validation execution resource at DP-05 is available from the opening of the work that follows this vantage, at the scale 61 system validation plans require | Colm Ó Braonáin | The plans queue behind one named individual, and PR-10's key-person concentration becomes the programme's critical path rather than a risk on it
AS-33 | An obligation recorded as landing in a procedure that requires the act is an obligation whose remaining gap is evidence or practice, and not a further gap in the sentence itself | Priyanka Venkataraman | Twenty-one obligations are recorded as housed when they are not, and the 21 · 12 · 5 division misstates the estate in the direction that looks better
AS-20 | The 121 pairs derived on 2026-08-14 remain the population to MS-08 | Priyanka Venkataraman | Tested and holding. No trigger fired, and the 121 were consumed unchanged. Continues in a wider form as AS-28
AS-21 | Consequence is a property of the record type and travels with the class | Terrence Abbatiello | Open, holding, and untouched. No consequence value has been read, moved or re-derived in this phase
AS-22 | Those who supplied the facts described the position as it is rather than as procedure says it should be | Priyanka Venkataraman | Open, and now extended. The same assumption underlies the interface and failure-history statements behind 61 complexity-and-reliability determinations — AS-27
AS-23 | A determination of Not determinable records the absence of evidence and not the absence of a search | Gideon Halvorsen | Open, holding, and mirrored. AS-29 is the same assumption for a landing of *nowhere*
AS-24 | FDA's five attributes are sufficient to describe the integrity position of a Helix record type | Priyanka Venkataraman | Open, unchanged. Phase 04 introduced no attribute and re-ran no assessment
AS-25 | The scale published in Phase 03 is applied unchanged to MS-13 | Terrence Abbatiello | Open, and now required by a procedure. SOP-DI-01 requires the assessment's output as the input to rigour, which makes the assumption enforceable rather than merely held
AS-26 | Many of the 35 GxP-relevant systems holding no Part 11 record are reached by 21 CFR 211.68, and others by different provisions of Part 211 according to what they do | Colm Ó Braonáin | Open, and untested. The framework covers the 61 and not the 96, and no phase has yet determined which provision reaches which of the 35. "Not in the framework" does not mean "assessed and satisfactory"
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage | Amara Sissoko | Open, holding. Extended to MS-09 by AS-28
AS-14 | The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable electronic record and have no export capability | Dr Sunita Raghunathan | Open, unchanged. Those four record types are outside the 34, outside the 121 and outside the framework
AS-15 | Helix continues to administer every account on the three vendor-hosted systems | Joachim Reuter | Open, holding. All three are inside the 61 and carry rigour bands; no control position is stated for any of them — IS-09
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories | Priyanka Venkataraman | Open, and still under test. Phase 04 introduced no record type. The 21 CFR 211.122 question recorded at 03.04 §8 is unresolved and is the determination owner's on ADR-0015's trigger
AS-17 | Vendors supply technical documentation sufficient to describe how the seven newly in-scope record types are created, retained and exported | Joachim Reuter | CLOSED 2026-09-17, tested and FAILED. Unchanged by this phase; DP-10 and DP-16 are still open in consequence
AS-18 | The 58 record types remain a stable unit through Phase 05 | Priyanka Venkataraman | Open, holding. The obligation register is specified against RT and SYS identifiers and depends on it
AS-19 | The review trigger at ADR-0015 is operated by its named owner in the absence of any procedure requiring it | Terrence Abbatiello | Open, and narrowed. SOP-DI-05 now requires the trigger to fire on a change. It has not fired, and the assumption still carries the interval between approval and first application
AS-01 | The Steering Committee continues monthly to close-out | Lydia Marchetti-Nwosu | Open, holding. Every Phase 04 sitting is minuted and indexed
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Open, holding, and now load-bearing on 61 validation plans — AS-32
AS-03 | The record-level determination can be completed in Phase 02 from the existing estate documentation | Priyanka Venkataraman | CLOSED at the MS-06 gate. Held on its date and failed on its method — unchanged
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open, and doubtful. AS-17 failed; DP-16 and DP-12 carry it into Phase 05
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open. Extended by AS-15
AS-06 | No new GxP-critical platform is introduced before MS-06 | Amara Sissoko | CLOSED, tested and held. Continues as AS-13 and now AS-28
AS-07 | The 41 marketed products and the two QC laboratories remain the basis on which record types are enumerated | Dr Sunita Raghunathan | Open. Extended by AS-16
AS-08 | The commitments in Helix's written response of 2026-03-06 are not varied by Helix during the programme | Rebekah Sandquist | Open, holding
AS-09 | Thorne Delacroix Consulting's design and drafting work is complete before the third-party audit opens at CAL-10 | Lydia Marchetti-Nwosu | Open, and now exercised. The advisory line contributed to the framework, and ADR-0004 keeps the party that designed it apart from the party that will audit it — PR-06
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding. CAL-12's quarterly horizon scan is what would detect otherwise
AS-12 | Internal audit capacity is available for CAL-09 without displacing the approved annual audit plan | Gideon Halvorsen | Open

## Dependencies
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
DP-21 | Validation execution capacity sized against 61 system validation plans, seventeen of which have no existing package to build on | The plans, which open after MS-08 | The external validation execution resource behind DP-05, and the CSV function | Colm Ó Braonáin | Open — the largest single work item the framework creates, and IS-28 is what it discharges
DP-22 | Quality unit drafting and approval capacity to take the nine SOPs from approved to applied, including training and first application | Closure of IS-24 and IS-25 | The quality unit | Terrence Abbatiello | Open — competes with DP-07 and DP-11 for the same capacity, exactly as DP-19 did
DP-23 | The evidence named on each obligation record, for all 38 obligations, from the seven named individual owners who hold them | Discharge of any obligation | Record owners, system owners, IT and Automation, and three vendors | Priyanka Venkataraman | Open — not one obligation is discharged at this vantage, and several are requests the Data Integrity Lead cannot perform — ADR-0002, 01.07 §6
DP-24 | A change control route that fires the framework's re-plan trigger, ADR-0015's review trigger and ADR-0022's re-assessment trigger from one change record | The rigour register and the two Phase 03 registers staying true | The quality system, through SOP-DI-05 | Terrence Abbatiello | Open — the amendment is approved; no change has fired it
DP-25 | Interface and failure-history statements for each system, on which the complexity-and-reliability band rests and on which AS-27 depends | Re-determination on a trigger, and defence of the existing 61 | The IT organisation and the Automation function | Amara Sissoko | Open — supplied once for this phase; the dependency is on it continuing to be supplied
DP-26 | A statement, per system, of what its validation package covers against each of 21 CFR 11.10's eleven paragraphs, extending the four-clause read to the whole section | Each system validation plan | The CSV function, against the controlled validation repository | Colm Ó Braonáin | Open — the four-clause read at EV-421 is the first eleventh of it

## Programme risks
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
PR-27 | The coverage finding at IS-22 is reported as a control position — a system described as failing 21 CFR 11.10(a) because its package does not address the fourth clause | Colm Ó Braonáin | ADR-0029 is standing framing; ../04.07-the-packages-helix-already-holds.md §1 states the boundary before the finding rather than after it; 04.12 is a numbered chapter rather than a caveat; the approved reading rule and the completed sheets are published at EV-406 and EV-421, with EV-420 recording that the read was performed under it, so that the claim can be tested as a claim about documents | IS-22, IS-20, ADR-0029
PR-28 | The 25 systems with no established data integrity position acquire one by drift — a provisional band assigned for a plan, a report or a slide, and never removed | Priyanka Venkataraman | The register records Not established as a value rather than a blank, on all 25 rows; DEC-409 records the refusal and the alternative that was available; the resulting-rigour column names the axis that set it on every row, so a band with only one source is visible as such | IS-27, IS-16, ADR-0018, DEC-409
PR-29 | The two graduations are merged, averaged or reduced to one number for an audience that asks for one | Joachim Reuter | ADR-0025 is standing framing; the register has two grading columns in two different band vocabularies, and no mean, weighted mean, index, tier or score is taken anywhere; neither determination is edited by the other, and the sixth column is a derived value and not a third determination; the seventeen disagreements are published individually with the direction each runs; IS-26 is an open issue rather than a footnote | IS-26, ADR-0025, PR-21
PR-30 | The twelve at IS-24 are folded back into a single count of procedural gaps, and a class created to make a gap visible becomes the place the gap is hidden | Terrence Abbatiello | The two classes carry separate identifiers and separate closure routes; the procedure gap record has a field that cannot be left blank distinguishing them — ../templates/procedure-gap-record-template.md; ADR-0028 records the merged alternative and refuses it | IS-24, IS-25, ADR-0028
PR-31 | A later re-read of the procedure estate is scoped to look only where something is expected, so that the class of finding whose product is a well-founded negative stops being produced | Terrence Abbatiello | The reading rule and the three-way classification are published at EV-417; SOP-DI-06 requires the evidence set to be re-confirmed at each periodic review including where it confirms nothing has changed; AS-29 records the assumption the negative rests on | IS-24, AS-29
PR-32 | The nine SOPs are approved and never applied, and Helix acquires nine more written procedures it can be found not to have followed. Which provision bites depends on which procedure it is: 21 CFR 211.22(d) for the quality control unit's own procedures; 21 CFR 211.100(b) for written production and process control procedures, which *"shall be followed in the execution of the various production and process control functions and shall be documented at the time of performance"*; 21 CFR 211.160(a) for laboratory control mechanisms. SOP-DI-03, SOP-DI-04, SOP-DI-07 and SOP-DI-08 are not quality control unit procedures | Terrence Abbatiello | AS-31 records the assumption; DP-22 names the capacity and its competition; ../04.11-what-a-framework-cannot-fix.md §4 publishes the exposure as a chapter rather than as a caveat; IS-19 closed against the procedure and not against its application, and this entry is where the exposure it described now sits | IS-19, IS-24, IS-28, DP-22, AS-31
PR-33 | A requirement is read as a description of the world — the framework's evidence set reported as evidence that exists, because a requirement reported as progress is what a steering committee wants to hear | Gideon Halvorsen | IS-28 is published as the phase's open question rather than as a limitation; every register carries a *not yet discharged* row; ../04.12-what-this-does-not-establish.md is owned by internal audit, which built none of it | IS-28, IS-20, ADR-0029
PR-34 | The framework's 61 validation plans are sized against the 44 systems with a package and the seventeen without one absorb effort nobody planned for | Colm Ó Braonáin | PR-17 recorded this in Phase 02 against the seventeen systems the walk found; the population Phase 04 measures is a different seventeen — the systems inside the 61 holding no validation package — and the two overlap by eleven; DP-21 names the capacity; the seventeen are sequenced with the other 44 and not after them, so that the shortfall appears early rather than at the end | IS-23, IS-13, PR-17, DP-21