## Control gaps
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8
CG-01 | 21 CFR 11.10(a) | 11 | SYS-011, SYS-021, SYS-022, SYS-028, SYS-033, SYS-037, SYS-039, SYS-046, SYS-055, SYS-058, SYS-061 | The system entered the estate without ever entering a validation lifecycle, so no artefact of any kind exists against any of the four objects of 21 CFR 11.10(a). | Yes — in full | A system validation plan and an executed package addressing all four objects, the fourth stated in its own terms. | Colm Ó Braonáin
CG-02 | 21 CFR 11.10(a) | 6 | SYS-036, SYS-038, SYS-051, SYS-052, SYS-059, SYS-060 | The system was scoped into the estate as storage, backup, instrumentation on a utility or a facilities control system, and the question whether it holds a GxP record was never asked of it, so it holds no package. | Yes — in full | A system validation plan and an executed package addressing all four objects. | Colm Ó Braonáin
CG-03 | 21 CFR 11.10(a) | 3 | SYS-040, SYS-041, SYS-056 | The qualification performed for the vendor-hosted systems recorded the 21 CFR 11.30 additional measures as the whole of the control set, and 21 CFR 11.10 was never assessed. | Yes — in full | A system validation plan and an executed package for each of the three, addressing all four objects of 21 CFR 11.10(a), additive to and not in place of the 21 CFR 11.30 measures. | Joachim Reuter
CG-04 | 21 CFR 11.10(a) | 4 | SYS-012, SYS-013, SYS-014, SYS-020 | The package addresses accuracy, reliability and consistent intended performance, no artefact in it is attributable to the ability to discern invalid or altered records, and the audit trail that would supply the attribution is itself Not met. | Yes — in full | An artefact directed at the fourth object, or the audit trail control at (e) brought into place and attributed to it under ADR-0024. | Colm Ó Braonáin
CG-05 | 21 CFR 11.10(b) | 7 | SYS-023, SYS-024, SYS-027, SYS-028, SYS-034, SYS-035, SYS-045 | The only export the product offers is a static rendering that carries neither the processing context nor the audit trail, so what is produced is not a complete copy of the record. | Yes — in full | An export that carries the record with the context needed to understand it, demonstrated once per record type. | Dr Sunita Raghunathan
CG-06 | 21 CFR 11.10(b) | 4 | SYS-036, SYS-059, SYS-060, SYS-061 | No record has ever been rendered from the store as a test, retrieval having been treated as a property of the platform rather than as a thing to be demonstrated. | Yes — in full | A demonstration that a record can be rendered from the store in complete and readable form. | Amara Sissoko
CG-07 | 21 CFR 11.10(b) | 8 | SYS-011, SYS-012, SYS-013, SYS-014, SYS-015, SYS-016, SYS-021, SYS-022 | The copy function produces a screen print and the product offers no electronic export at all, so no copy suitable for inspection or for agency copying can be produced. | Yes — in full | An export route, or a documented alternative by which a complete and readable copy is produced. | Joachim Reuter
CG-08 | 21 CFR 11.10(c) | 8 | SYS-011, SYS-021, SYS-022, SYS-033, SYS-037, SYS-039, SYS-055, SYS-058 | The system's local store is the only instance of the record and no protection is applied to it beyond the workstation it sits on. | Yes — in full | The record brought into a protected store, with the protection stated against the period the record is held for. | Amara Sissoko
CG-09 | 21 CFR 11.10(c) | 4 | SYS-002, SYS-051, SYS-052, SYS-053 | The record is written to a rolling buffer that overwrites at a fixed depth, so the record is not protected for any stated period. | Yes — in full | Extraction to a protected store before the buffer turns, with the extraction evidenced. | Joachim Reuter
CG-10 | 21 CFR 11.10(c) | 5 | SYS-036, SYS-046, SYS-059, SYS-060, SYS-061 | No restore from the platform has ever been performed or evidenced, so protection through the period cannot be shown for anything the platform holds. | Yes — in full | An evidenced restore, and a statement of what the platform protects and for how long. | Amara Sissoko
CG-11 | 21 CFR 11.10(d) | 7 | SYS-003, SYS-004, SYS-005, SYS-006, SYS-007, SYS-009, SYS-010 | A shared local operator account is in use. Access is limited to a group of authorised operators; what is defeated is attribution of an entry to a named individual, which is 21 CFR 211.68(b) and 21 CFR 211.188(b)(11) on the predicate-rule side. The 21 CFR 11.10(d) determination rests on the account's credential being held by persons whose authorisation is not individually recorded, so the limiting (d) requires cannot be demonstrated for any individual. | No | Named individual accounts for every operator, with the shared account withdrawn. | Amara Sissoko
CG-12 | 21 CFR 11.10(d) | 3 | SYS-051, SYS-052, SYS-055 | One administrative account is held in common by the facilities and utilities function and by its contractor. Access is limited to a group of authorised holders; what is defeated is attribution of an entry to a named individual, which is 21 CFR 211.68(b) and 21 CFR 211.188(b)(11) on the predicate-rule side. The 21 CFR 11.10(d) determination rests on the account's credential being held by persons whose authorisation is not individually recorded, and by a contractor whose holders Helix does not record individually at all, so the limiting (d) requires cannot be demonstrated for any individual. | No | Named individual accounts, and withdrawal of the common account. | Amara Sissoko
CG-13 | 21 CFR 11.10(d) | 2 | SYS-031, SYS-032 | The workstation operating-system logon is the only access control on the instrument application, and it is shared within the laboratory. Access is limited to a group of authorised analysts; what is defeated is attribution of an entry to a named individual, which is 21 CFR 211.68(b) and 21 CFR 211.188(b)(11) on the predicate-rule side. The 21 CFR 11.10(d) determination rests on the logon's credential being held by persons whose authorisation is not individually recorded, so the limiting (d) requires cannot be demonstrated for any individual. | No | Application-level access control with named individual accounts. | Dr Sunita Raghunathan
CG-14 | 21 CFR 11.10(e) | 8 | SYS-012, SYS-013, SYS-014, SYS-015, SYS-016, SYS-017, SYS-018, SYS-020 | The audit trail's scope is configurable at administrator level and a change to that configuration is not itself recorded, so the trail cannot be relied on to record the entries and actions the paragraph names. | Yes — in full | Configuration fixed and placed under change control, with changes to it recorded. | Joachim Reuter
CG-15 | 21 CFR 11.10(e) | 6 | SYS-023, SYS-024, SYS-027, SYS-034, SYS-045, SYS-053 | A change to a stored value replaces the previous value in the record the reviewer sees, so record changes obscure previously recorded information. | Yes — in full | Retention of the previous value in a form the reviewer sees. | Dr Sunita Raghunathan
CG-16 | 21 CFR 11.10(e) | 8 | SYS-011, SYS-021, SYS-022, SYS-033, SYS-037, SYS-039, SYS-055, SYS-058 | The product has no audit trail function at all and none can be configured. | Yes — in full | An audit trail, by product change or by moving the record to a system that has one. | Joachim Reuter
CG-17 | 21 CFR 11.10(e) | 4 | SYS-035, SYS-036, SYS-051, SYS-052 | The audit trail is written to a local circular store that is overwritten well before the record it describes is superseded, so it is not retained for a period at least as long as that required for the subject records. The determination does not rest on a period having been set: the trail is overwritten while the record it describes is still live on the system, so it fails the clause on any period that could be set for that record. | Yes — in full | Audit trail data extracted and retained against the record's own period, whatever period is later set for it. | Amara Sissoko
CG-18 | 21 CFR 11.10(e) | 3 | SYS-028, SYS-046, SYS-061 | The platform records no operator entries or actions against the copies it holds, the audit trail having been treated as a property of the originating system alone. | Yes — in full | Audit trail generation on the platform, or a stated and evidenced dependency on the originating system's trail. | Amara Sissoko
CG-19 | 21 CFR 11.10(f) | 5 | SYS-003, SYS-004, SYS-005, SYS-006, SYS-007 | The product does not enforce the permitted sequencing of steps, so an operator may record a later step before an earlier one. | No | An operational system check that enforces the permitted sequencing of steps and events. 21 CFR 11.10(f) requires checks *"to enforce permitted sequencing of steps and events, as appropriate"*, and a check that detects an out-of-sequence entry after it has been made does not enforce the sequencing. | Joachim Reuter
CG-20 | 21 CFR 11.10(f) | 3 | SYS-019, SYS-044, SYS-057 | The route permits a step to be completed out of the order the process requires and the system performs no check on the order. | No | An operational system check that enforces the permitted sequencing of steps and events on the route, 21 CFR 11.10(f) requiring checks *"to enforce"* it rather than to report on it afterwards. | Bernard Kwiatkowski
CG-21 | 21 CFR 11.10(g) | 6 | SYS-011, SYS-021, SYS-022, SYS-033, SYS-055, SYS-058 | A single role holds every function the product offers, so no authority check operates on any action. | No | Distinct roles with distinct permitted actions, and an authority check on each. | Amara Sissoko
CG-22 | 21 CFR 11.10(g) | 3 | SYS-042, SYS-048, SYS-049 | Role membership is not enforced against a defined authorisation — any account may be placed in any role — so a person may use the system, sign a record or perform the operation at hand without their authority for it having been determined. | No | Role membership enforced against a defined authorisation, so that only individuals authorised for an operation can perform it. Part 11 requires no second approval of a role assignment and none is required here; a second approval is a Helix control that does not exist, and is named as one route to the condition rather than as the condition. | Amara Sissoko
CG-23 | 21 CFR 11.10(g) | 2 | SYS-002, SYS-038 | No authority check controls which individuals may access the input or output device, so an entry may be made through it by a person whose authority for the operation has not been determined. | No | An authority check controlling which individuals may access the operation or computer system input or output device, evidenced. | Joachim Reuter
CG-24 | 21 CFR 11.10(h) | 4 | SYS-025, SYS-026, SYS-029, SYS-030 | Data arriving from an interfaced instrument is accepted without any check of the validity of the source. | No | A source-validity check at the interface, evidenced. | Dr Sunita Raghunathan
CG-25 | 21 CFR 11.10(h) | 1 | SYS-044 | The handheld scanning devices feeding the warehouse route are not determined to be valid sources of data input. | No | A device check on the handheld estate, evidenced. | Bernard Kwiatkowski
CG-26 | 21 CFR 11.10(i) | 4 | SYS-011, SYS-021, SYS-022, SYS-033 | No role was ever defined for the system, so no role-based training content exists for anybody who uses it. | No | A defined role and training content against it, with completion recorded. | Amara Sissoko
CG-27 | 21 CFR 11.10(i) | 3 | SYS-046, SYS-055, SYS-058 | The system is operated by a contracted maintenance function whose education, training and experience records Helix does not hold. | No | Records held or attested by Helix for every individual who operates the system. | Bernard Kwiatkowski
CG-28 | 21 CFR 11.10(i) | 2 | SYS-036, SYS-061 | Administrative access is held by a role for which no education, training or experience has been determined against the tasks assigned to it. | No | A determination that the individuals holding the administrative role have the education, training and experience *"to perform their assigned tasks"*, with the basis recorded. 21 CFR 11.10(i) names no subject matter, and no subject matter is prescribed here. | Amara Sissoko
CG-29 | 21 CFR 11.10(j) | 3 | SYS-040, SYS-042, SYS-050 | The accountability statement for actions initiated under an electronic signature is carried in training material and is not established as a written policy. | No | A written policy holding individuals accountable and responsible for actions initiated under their electronic signatures, issued under document control. | Terrence Abbatiello
CG-30 | 21 CFR 11.10(j) | 3 | SYS-044, SYS-048, SYS-049 | The written policy that exists names no individual obligation for actions initiated under an electronic signature on these routes, so nothing on them is adhered to. | No | The policy extended to the route and adherence evidenced. | Terrence Abbatiello
CG-31 | 21 CFR 11.10(k) | 6 | SYS-011, SYS-021, SYS-022, SYS-033, SYS-037, SYS-039 | No systems documentation exists for the system at all, so nothing can be distributed, accessed or used under control. | No | Systems documentation produced and brought under document control. | Amara Sissoko
CG-32 | 21 CFR 11.10(k) | 2 | SYS-055, SYS-058 | The systems documentation is held by the maintenance contractor and is not under Helix document control. | No | Documentation brought into the document management system with a named Helix owner. | Bernard Kwiatkowski
CG-33 | 21 CFR 11.10(k) | 2 | SYS-051, SYS-052 | Configuration documentation is amended outside change control, so no audit trail documents the time-sequenced development and modification of the documentation. | In part — (k)(2) | Revision and change control procedures maintaining that audit trail. | Joachim Reuter
CG-34 | 21 CFR 11.10(k) | 1 | SYS-046 | The configuration record is a spreadsheet held outside the document management system, so its distribution, access and use are not controlled. | No | The record brought into the document management system with a named individual owner. | Bernard Kwiatkowski