## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-501 | 2026-12-01 | Open Phase 05 and fix its boundary: a control position for every paragraph of 21 CFR 11.10 on every one of the 61 systems, with no validation outcome, no deviation, no CAPA, no remediation plan, no retention rule and no chromatography-specific determination, and with Phase 03's and Phase 04's registers taken as inputs that are never re-scored or re-banded | Lydia Marchetti-Nwosu | — | Steering Committee, EV-501
DEC-502 | 2026-12-04 | Take Phase 04's eleven-paragraph evidence set as the specification the control position is assessed against, and record before any assessment opens that a rigour band is not a control position and an obligation is not evidence — ADR-0029, IS-20. A band says what evidence is required and says nothing about whether any control works | Joachim Reuter | — | Steering Committee, EV-502
DEC-503 | 2026-12-10 | The unit of a control position is a paragraph of 21 CFR 11.10 on a system — never a system alone and never a paragraph alone. 11 × 61 = 671. Every cell carries a determination; there is no *not applicable*, no blank and no hedge | Colm Ó Braonáin | ADR-0030 | GOV-21
DEC-504 | 2026-12-17 | Authorise the assessment method, fixed before the first system was looked at: the evidence to be examined for each paragraph, the two questions asked in a fixed order, and the rule that the second question is not reached unless the first is answered yes. Subject-matter coverage is not requirement, a general obligation is not a specific one, and silence is neither permission nor prohibition — Phase 04's reading rule, unrelaxed | Priyanka Venkataraman | — | GOV-21, EV-503, EV-505
DEC-505 | 2026-12-17 | A control assessment is not validation, and neither substitutes for the other. Assessing that a control is present observes a system; validating it demonstrates against a specification that it performs as intended. The evidence Phase 04's framework requires is owed in full and this phase produces none of it. Raise IS-34 | Colm Ó Braonáin | ADR-0034 | GOV-21, EV-506
DEC-506 | 2026-12-22 | Approve the control position record and the access review record as instruments, the empty forms, with the required-basis field on every determination and the rule that a record with the second question unanswered is a defective record | Amara Sissoko | — | EV-507, EV-508
DEC-507 | 2027-01-04 | Record that 21 CFR 11.10 has been assessed for SYS-040, SYS-041 and SYS-056 for the first time, on the same method as the other 58, and that the 21 CFR 11.30 additional measures on those three are additive to the 21 CFR 11.10 controls that section requires be included as appropriate and never a substitute for them. Whether those measures perform as intended is not assessed — IS-09 stays open on its second limb | Joachim Reuter | — | Steering Committee, EV-509
DEC-508 | 2027-01-06 | Met but not required is a determination in its own right. A control that is present and that no procedure requires can be withdrawn without a deviation, because no procedure would be breached — which is Phase 04's twelve procedure-gaps seen at control level. Raise IS-29 | Terrence Abbatiello | ADR-0031 | GOV-22
DEC-509 | 2027-01-08 | Refuse in advance to report a single combined figure of met control positions. The two components are held in separate columns and separate counts in control-position-register.md, so that the addition is not available to somebody working quickly. The figure itself did not exist at this date and is named nowhere in this entry — no system had been counted and neither component was known; it is stated at ../05.08-the-position.md §2. Record the standing risk that the two are added anyway — PR-35 | Priyanka Venkataraman | — | GOV-22, EV-512
DEC-510 | 2027-01-11 | Enumerate the 19 systems that execute electronic signatures, and authorise the manifestation test against every human readable form each of them produces, with the enumeration of forms completed and recorded before any form was tested | Joachim Reuter | — | EV-514, EV-515
DEC-511 | 2027-01-13 | 21 CFR 11.50 is tested against every human readable form of the electronic record, not against the electronic display. The section requires the printed name, the date and time and the meaning of the signature, and provides that these *"shall be included as part of any human readable form of the electronic record (such as electronic display or printout)."* A test confined to the display is narrower than the text it tests against. Raise IS-30 | Priyanka Venkataraman | ADR-0032 | GOV-23
DEC-512 | 2027-01-14 | Record the manifestation result: all three elements on screen on all 19; the meaning of the signature absent from the exported or printed form on 12 of the 19. 12 + 7 = 19. Record that Helix had only ever checked the screen, and that no procedure required any other form to be looked at | Priyanka Venkataraman | — | GOV-23, EV-517
DEC-513 | 2027-01-18 | Enumerate which of the 19 offer a continuous-session relaxation at all, and authorise the session test — a first signing with all components and a second signing in the same uninterrupted session, with what the system asked for the second time recorded | Amara Sissoko | — | EV-518
DEC-514 | 2027-01-20 | The continuing component under 21 CFR 11.200(a)(1)(i) is the password, and each system is tested as such. A user identification code appears in audit trails, in reports and on screens, and a thing designed to be shown is not a component *"only executable by, and designed to be used only by, the individual."* 21 CFR 11.200(a)(1) is not a multi-factor authentication requirement and is never described as one. Raise IS-31 | Amara Sissoko | ADR-0033 | GOV-23
DEC-515 | 2027-01-21 | Approve the control gap register — CG-01 to CG-34, accounting for all 151 Not met positions with none counted twice and none omitted — on the rule that a gap is one paragraph, one cause and a set of systems. Record that a control gap is not a deviation, not a CAPA, not a finding and not an inspectional observation, and that the register states a closure condition and no date, cost, sequence or priority. Approved on the reconciliation at EV-525, performed the same day and retained | Joachim Reuter | — | EV-524, EV-525, EV-526
DEC-516 | 2027-01-25 | Confirm IS-01 open and unweighted at the MS-09 gate, and record that a control position taken at this vantage is not evidence about any system's configuration at any earlier date and bears on none of the four candidate explanations. No document in this phase may be cited in support of any of them | Gideon Halvorsen | — | GOV-25, EV-539
DEC-517 | 2027-01-27 | Enforcement discretion changes what FDA said it would enforce and changes nothing about the position. It reaches 21 CFR 11.10(a), (b), (c) and (e), and (k) in part — the guidance names (k)(2), the second of (k)'s two subparagraphs, and says nothing about (k)(1) — together with the corresponding requirements in 21 CFR 11.30; it is FDA's stated intention, not an exemption and not a safe harbour, and 21 CFR 211.68 and 21 CFR 211.100(b) survive it entirely. The position is stated identically inside and outside it. Raise IS-33 | Terrence Abbatiello | ADR-0035 | GOV-24
DEC-518 | 2027-01-28 | Approve the control position register and the control gap register — 61 rows, eleven determination columns, 671 positions, and 34 gaps. IS-28 closes: the first paragraph of 21 CFR 11.10 a system is measured against has been measured, on every system in scope | Dr Marguerite Oyelaran | — | GOV-24, GOV-25, EV-522, EV-523
DEC-519 | 2027-01-28 | Part 11 requires no reason-for-change field, and holding one is never reported as compliance with anything. 23 systems hold one, which Part 11 does not require; 14 of the 23 do not meet 21 CFR 11.10(e)'s requirement that record changes not obscure previously recorded information, which it does. Raise IS-32 | Joachim Reuter | ADR-0036 | GOV-25
DEC-520 | 2027-01-29 | Publish Phase 05 at MS-09; hand the two registers and the signature position to Phase 06, and record IS-35 — the position is known for every paragraph on every system, and on 218 of them what is present is required by nothing. A position is not a control that will still be there next year | Lydia Marchetti-Nwosu | — | Steering Committee, EV-542