## Issues
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
IS-29 | 218 of the 520 controls that are present are required by nothing and can be withdrawn without a deviation. Of the 671 control positions, 302 are Met and required, 218 are Met but not required and 151 are Not met. 302 + 218 + 151 = 671. A position recorded Met but not required is a control that is in place and that no sentence in any of the 63 procedures in scope obliges anybody to keep in place, so turning it off breaches nothing, raises no deviation, fires no change control trigger and produces no record anywhere. Sixty of the sixty-one systems carry at least one such position; only SYS-001 carries none. The paragraph most affected is 21 CFR 11.10(e), where twenty-six audit trails run under no requirement against six that something requires. This is Phase 04's twelve procedure-gaps seen at control level — ADR-0028, ../../04-the-validation-framework-and-policy-architecture/04.08-where-the-obligations-land.md §5 — and the argument is cited and not restated. It does not close by the 218 being reduced. It closes when the quality system says which controls Helix requires of itself, which is a decision nobody has taken | Priyanka Venkataraman | 2027-01-06 | Open — DP-27 is the quality unit capacity that would write the sentences; none has been written, and nine SOPs approved in Phase 04 remain unapplied — PR-32, DP-22 | DEC-508, DEC-509, ADR-0031, GOV-22, ../05.09-the-controls-nothing-requires.md, control-position-register.md, IS-24, IS-35, PR-35
IS-30 | The meaning of the signature is absent from the exported or printed form on 12 of the 19 systems that execute signatures. 21 CFR 11.50 requires the printed name of the signer, the date and time when the signature was executed and the meaning associated with the signature, and requires that these *"shall be included as part of any human readable form of the electronic record (such as electronic display or printout)."* 21 CFR 11.50(b) has two conjoined limbs and this phase assessed one of them. In full, the three items *"shall be subject to the same controls as for electronic records and shall be included as part of any human readable form of the electronic record (such as electronic display or printout)."* The second limb is what was tested; the *same controls* limb was not assessed and is owed — which is material here rather than incidental, because on twelve systems the meaning is held in the signature workflow rather than on the record, and whether it is under the same controls as the record is a question nobody has asked. On the electronic display all three appear on all 19. On the exported or printed form the meaning is absent on 12. 12 + 7 = 19. The printed name and the timestamp survive the export on all nineteen; it is the meaning that drops, because the meaning is a property of the signing act held in the workflow and not a field on the record. Helix had only ever checked the screen — the vendor demonstration is a screen demonstration, the qualification script was written from it, and no procedure required any other human readable form to be tested. This is not a control position under 21 CFR 11.10 and moves no cell in control-position-register.md | Priyanka Venkataraman | 2027-01-13 | Open — the condition is the meaning included as part of every human readable form, evidenced per form; and a procedure requiring the test, so that it is required rather than remembered. DP-28 is the vendor route on four of the twelve | DEC-511, DEC-512, ADR-0032, GOV-23, ../05.06-signatures-and-the-human-readable-form.md, AS-36, IS-31, PR-37
IS-31 | 7 of the 19 re-prompt for the user identification code rather than the password. 21 CFR 11.200(a)(1) requires *"at least two distinct identification components such as an identification code and password"*, which is not multi-factor authentication and is never described as one. 21 CFR 11.200(a)(1)(i) permits subsequent signings in a single, continuous period of controlled system access to use one component, and requires that it be one *"only executable by, and designed to be used only by, the individual."* A user identification code appears in audit trails, in reports and on screens; a thing designed to be shown is not such a component. The continuing component is the password. On the seven, the second prompt asks for the identifier the audit trail is about to print. The first signing uses both components on all nineteen; it is the relaxation that is taken incorrectly. SYS-019, SYS-023, SYS-024, SYS-027, SYS-028, SYS-037 and SYS-042. The seven are not a further population. Every one of the seven is also among IS-30's twelve, so twelve of the nineteen carry at least one signature finding, seven of those twelve carry both, and seven of the nineteen — SYS-025, SYS-026, SYS-041, SYS-043, SYS-047, SYS-048 and SYS-049 — carry neither. The two identities partition the nineteen twice on different properties, and the equality of the numerals is a coincidence and not a relation | Amara Sissoko | 2027-01-20 | Open — the condition is the subsequent-signing prompt set to the password, or the relaxation withdrawn so that every signing uses all components under 21 CFR 11.200(a)(1)(ii); and a procedure requiring the continuous-session behaviour to be tested. DP-30 | DEC-513, DEC-514, ADR-0033, GOV-23, ../05.07-the-continuing-component.md, AS-36, IS-30, PR-40
IS-32 | 23 systems hold a reason-for-change field Part 11 does not require, and 14 of them fail the no-obscuring requirement it does. There is no textual requirement anywhere in Part 11 for a reason-for-change field. What 21 CFR 11.10(e) does require is that *"Record changes shall not obscure previously recorded information"* — a no-overwrite requirement. 14 of the 23 do not meet it. 14 + 9 = 23, and 14 + 15 = 29, which is (e)'s Not met column. Eight of the fourteen sit in CG-14, where the audit trail's scope is configurable and a change to that configuration is not itself recorded; six sit in CG-15, where a change to a stored value replaces the previous value in the record the reviewer sees — so the field capturing the reason for the change is retained and the value the change was made to is not. Effort spent on a control that is not required, absent on one that is. The field is Helix's own control and nothing requires its removal; what is required is that holding one is never reported as compliance with anything — ADR-0036. SYS-023 and SYS-024 are among the six and the OBS-2 link is recorded with no conclusion drawn | Joachim Reuter | 2027-01-28 | Open — CG-14 and CG-15 carry the fourteen and both are open; DP-29 is the vendor route on the six | DEC-519, ADR-0036, GOV-25, ../05.10-the-inversion.md, control-gap-register.md, IS-06, AS-38, PR-39
IS-33 | 89 of the 151 failures sit in the four paragraphs discretion reaches, and nothing about that changes the position. Enforcement discretion reaches 21 CFR 11.10(a), (b), (c) and (e), and (k) in part — the guidance names (k)(2), the second of (k)'s two subparagraphs, and says nothing about (k)(1) — together with the corresponding requirements in 21 CFR 11.30. Not met inside the four: (a) 24 · (b) 19 · (c) 17 · (e) 29 = 89. Not met outside them: 62. 89 + 62 = 151. Positions inside full discretion number 4 × 61 = 244. The paragraphs Helix is weakest on are the paragraphs FDA said it would exercise discretion over, and that is a structural fact published rather than buried. It is not a mitigation. Enforcement discretion is FDA's stated intention about what it will enforce; it is not an exemption, it is not a safe harbour, it confers no rights, and 21 CFR 211.68 and 21 CFR 211.100(b) survive it entirely. The determination inside the four is written in the same words, on the same method, as the determination outside them. This entry does not close by the 89 being reduced; it is a standing refusal to draw comfort from a cut | Terrence Abbatiello | 2027-01-27 | Open, and open by design — it records a structural property of the estate and a refusal, not a defect awaiting correction | DEC-517, ADR-0035, ADR-0003, GOV-24, ../05.11-discretion-changes-nothing.md, ../05.08-the-position.md, PR-38, PR-08
IS-34 | A control position is not validation evidence, and the evidence Phase 04 requires is owed in full. Phase 04's framework requires evidence for all eleven paragraphs of 21 CFR 11.10 for every one of the 61 systems, and none has been produced. This phase produced a determination for all 671 positions and no validation package has been executed, no protocol has been run, no test result exists and no system validation plan has been written. Assessing that a control is present observes a system; validating it demonstrates against a specification that it performs as intended, and neither substitutes for the other — ADR-0034. Not one of the 38 obligations is discharged. The available error is specific and is named so that it can be refused: 37 systems carry a Met and required position on (a), and a sentence reporting that validation is in place on 37 systems is one step from a sentence reporting that 37 systems are validated. They are different claims | Colm Ó Braonáin | 2026-12-17 | Open — DP-05 is the resource on which the plans open; IS-28 closed on the first half of its question and this entry is the second half | DEC-505, ADR-0034, GOV-21, ../05.12-what-this-does-not-establish.md, IS-22, IS-23, IS-28, DP-05, DP-21, PR-42
IS-35 | The question Phase 05 leaves open, and it is Phase 06's and Phase 07's: the position is known for every paragraph on every system, and on 218 of them what is present is required by nothing. A position is not a control that will still be there next year. Six hundred and seventy-one positions are determined, which is more than this programme has ever known about its own controls. Two hundred and eighteen of the 520 met positions rest on a configuration no sentence requires, so that on sixty of the sixty-one systems at least one paragraph is answered by something that could be withdrawn tomorrow without a deviation. And a determination is dated: every cell speaks as at 2027-01-29 and as at no other day. The register therefore describes a state and not a mechanism. A periodic review comparing the estate against it in twelve months would find differences and would have no way to say whether any of them was a change, because a change is a departure from a required state and most of these states are not required | Joachim Reuter | 2027-01-29 | Open — Phase 06 and Phase 07 own the next part of the answer and Phase 08 owns the mechanism, because periodic review is where a state either becomes a control or stays a configuration | DEC-520, GOV-25, ../05.13-phase-summary-and-transition.md, IS-29, IS-23, IS-27, AS-34, PR-35

## Assumptions
Col 1 | Col 2 | Col 3 | Col 4
AS-34 | Load-bearing on all 671 cells. The configuration and behaviour observed between 2027-01-04 and 2027-01-20 is the configuration and behaviour at the vantage, and no system was changed between its assessment and 2027-01-29 | Joachim Reuter | The register describes an estate that has already moved, and on the 218 positions requiring nothing there is no mechanism that would have recorded the move — which is IS-35 arriving early
AS-35 | The 63 procedures Phase 04 read are the whole of the procedure estate bearing on the eleven paragraphs, so that a determination of Met but not required reflects the absence of a requiring sentence rather than the absence of a search | Terrence Abbatiello | The 218 is wrong in Helix's own favour in one direction and against it in the other: controls recorded as unrequired turn out to be required, and the population IS-29 describes is not the population that exists. AS-29 is the Phase 04 form of the same assumption
AS-36 | The enumeration of human readable forms at EV-514, and of continuous-session behaviour at EV-518, is the whole of what each of the nineteen products can produce and do | Priyanka Venkataraman | IS-30 and IS-31 become statements about where somebody looked rather than about the estate, which is the failure mode ADR-0032 was written to avoid
AS-37 | A determination against 21 CFR 11.10(c) and against 21 CFR 11.10(e)'s retention clause can be made in the absence of a stated retention period for any of the 34 record types, by assessing protection and retention against the record's own life as the systems presently hold it | Priyanka Venkataraman | 17 (c) determinations and part of (e)'s 29 rest on a period nobody has set — IS-14, DP-18 — and Phase 07 changes the basis of a determination this phase published
AS-38 | The 23 reason-for-change fields at EV-527 are the whole of that population, and no further system captures a reason in a form nobody described as a field | Joachim Reuter | The inversion is larger or smaller than published, and a finding whose whole force is a comparison of two counts loses it
AS-39 | The 61 systems remain the population to MS-10: no ADR-0015 trigger and no ADR-0022 trigger fires between this vantage and 2027-02-26 that adds a system, removes one or changes which system holds a record type | Amara Sissoko | The control position register describes an estate that no longer exists, and Phase 06 inherits a position for a system that has changed
AS-40 | Those who supplied the configuration statements described the position as it is rather than as procedure says it should be | Joachim Reuter | The determination records what somebody believes about a system, which is the assumption AS-22 has carried since Phase 03 and which now sits under six hundred and seventy-one cells rather than under a risk rating
AS-27 | The three features graded in the complexity-and-reliability determination are sufficient to grade a system on the axis 21 CFR 211.68(b) names | Colm Ó Braonáin | Open, untested and untouched. No band was re-derived in this phase
AS-28 | The 61 systems and the 121 pairs remain the population to MS-09 | Amara Sissoko | Tested and holding. No trigger fired, and the 61 were assessed unchanged. Continues as AS-39
AS-29 | The 63 procedures read at EV-417 are the whole of the procedure estate bearing on the 38 obligations | Terrence Abbatiello | Open, and now load-bearing twice. AS-35 is the same assumption carrying 218 determinations rather than 17 landings
AS-30 | The 44 validation packages read at EV-421 are the whole of what Helix holds | Colm Ó Braonáin | Open, untested. The (a) column rests on it for 37 Met determinations and for CG-04
AS-31 | The nine SOPs, the policy and the framework are issued under document control and not varied outside change control | Terrence Abbatiello | Open, holding, and unexercised. None of the nine has been applied to anything — PR-32
AS-32 | The validation execution resource at DP-05 is available at the scale 61 validation plans require | Colm Ó Braonáin | Open, and not yet drawn on. No plan has been written — IS-34
AS-33 | An obligation landing in a procedure that requires the act has a remaining gap of evidence or practice and not of the sentence | Priyanka Venkataraman | Open, and now examinable from the control side. Where a control is Met and required, this is the assumption that the sentence is the right sentence
AS-20 | The 121 pairs derived on 2026-08-14 remain the population to MS-08 | Priyanka Venkataraman | Held and consumed. Continues in wider form as AS-28 and AS-39
AS-21 | Consequence is a property of the record type and travels with the class | Terrence Abbatiello | Open, holding, untouched. No consequence value has moved
AS-22 | Those who supplied the facts described the position as it is rather than as procedure says it should be | Priyanka Venkataraman | Open, and now the widest assumption in the repository. AS-40 is the same assumption under 671 determinations
AS-23 | A determination of Not determinable records the absence of evidence and not the absence of a search | Gideon Halvorsen | Open, holding, and mirrored twice. AS-35 and AS-36 are the same assumption for a control and for a form
AS-24 | FDA's five attributes are sufficient to describe the integrity position of a Helix record type | Priyanka Venkataraman | Open, unchanged. No attribute was introduced and no assessment re-run
AS-25 | The scale published in Phase 03 is applied unchanged to MS-13 | Terrence Abbatiello | Open, unchanged. Nothing was re-scored
AS-26 | Many of the 35 GxP-relevant systems holding no Part 11 record are reached by 21 CFR 211.68, and others by different provisions of Part 211 | Colm Ó Braonáin | Open, and untested. The control position register covers the 61 and not the 96. "Not in the register" does not mean "assessed and satisfactory"
AS-01 | The Steering Committee continues monthly to close-out | Lydia Marchetti-Nwosu | Open, holding. Every Phase 05 sitting is minuted and indexed
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Open, holding
AS-03 | The record-level determination can be completed in Phase 02 from existing documentation | Priyanka Venkataraman | CLOSED at the MS-06 gate, unchanged
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open, and exercised. The (e) determinations rest on it; DP-28, DP-29 and DP-30 are where it did not hold
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open. Extended by AS-15
AS-06 | No new GxP-critical platform is introduced before MS-06 | Amara Sissoko | CLOSED, tested and held
AS-07 | The 41 marketed products and the two QC laboratories remain the basis for record-type enumeration | Dr Sunita Raghunathan | Open. Extended by AS-16
AS-08 | The commitments in the written response of 2026-03-06 are not varied by Helix | Rebekah Sandquist | Open, holding
AS-09 | Thorne Delacroix Consulting's design and drafting work is complete before the third-party audit opens | Lydia Marchetti-Nwosu | Open. ADR-0004 keeps the party that designed apart from the party that will audit — PR-06
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding, and load-bearing on IS-33's discretion cut
AS-12 | Internal audit capacity is available for CAL-09 without displacing the annual audit plan | Gideon Halvorsen | Open
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage | Amara Sissoko | Open, holding. Extended to MS-10 by AS-39
AS-14 | The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable record and have no export | Dr Sunita Raghunathan | Open, unchanged. Those record types are outside the 34 and their systems outside the 61
AS-15 | Helix continues to administer every account on the three vendor-hosted systems | Joachim Reuter | Open, holding, and now exercised. All three carry (d) determinations that rest on it
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories | Priyanka Venkataraman | Open, and still under test. No record type was introduced
AS-17 | Vendors supply technical documentation sufficient to describe the seven newly in-scope record types | Joachim Reuter | CLOSED 2026-09-17, tested and FAILED, unchanged
AS-18 | The 58 record types remain a stable unit through Phase 05 | Priyanka Venkataraman | Open, holding, and consumed at this vantage. The register is specified against SYS identifiers and depends on it
AS-19 | The review trigger at ADR-0015 is operated by its named owner | Terrence Abbatiello | Open, and narrowed further. SOP-DI-05 still has not fired

## Dependencies
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6
DP-27 | Quality unit drafting and approval capacity to decide which of the 218 unrequired controls Helix intends to require of itself, and to write the sentences | Closure of IS-29 | The quality unit | Terrence Abbatiello | Open — competes with DP-07, DP-11 and DP-22 for the same capacity, and is larger than all three. No sentence has been written
DP-28 | Vendor product change or configuration route to include the meaning of the signature in every human readable form on the twelve | Closure of IS-30 | Four named vendors, and the IT organisation | Priyanka Venkataraman | Open — Helix administers the configuration on some of the twelve and not on all
DP-29 | Vendor product route to retain a previous value in the record the reviewer sees, on the six at CG-15 | Closure of IS-32's second limb | Three named vendors | Joachim Reuter | Open — AS-17 has already failed on documentation for part of this estate
DP-30 | Vendor or configuration route to set the subsequent-signing prompt to the password on the seven | Closure of IS-31 | Vendors, and account administration | Amara Sissoko | Open
DP-31 | Systems documentation for the systems that have none, and a Helix-side owner for the documentation the maintenance contractor holds | Closure of CG-31 and CG-32 | The Automation function, the engineering function and one contractor | Bernard Kwiatkowski | Open
DP-32 | A re-determination route that fires from one change record on a change to a system's configuration, so that a control position moves under change control rather than silently | The register staying true, and IS-35 | The quality system, through SOP-DI-05 | Terrence Abbatiello | Open — SOP-DI-05 exists and has not fired on any change, and its trigger set was written for the applicability determination and not for a control position

## Programme risks
Col 1 | Col 2 | Col 3 | Col 4 | Col 5
PR-35 | The 302 and the 218 are added and reported as 520 met positions out of 671, and the distinction the phase exists for disappears into a figure that sounds like progress | Priyanka Venkataraman | ADR-0031 is standing framing; control-position-register.md holds the two in separate columns and separate counts and takes no combined figure anywhere; DEC-509 records the refusal; ../05.08-the-position.md §2 names the number to resist before it states the cut; ../05.12-what-this-does-not-establish.md is a numbered chapter owned by internal audit | IS-29, ADR-0031, DEC-509, PR-20
PR-36 | The 671 are reduced to 61 system-level verdicts — a system reported as meeting or failing 21 CFR 11.10, which is a claim the register cannot support | Joachim Reuter | ADR-0030 is standing framing; the register carries eleven determination columns and no twelfth summarising them, and states that it never will; the five systems with no Not met position are named in the same sentence that says they are not five compliant systems | ADR-0030, IS-20, PR-42
PR-37 | The 21 CFR 11.50 finding is read as a 21 CFR 11.10 control position, or as a statement that twelve systems' signatures are invalid | Priyanka Venkataraman | Both chapters state the boundary before the finding rather than after it; the twelve appear in no cell of the control position register and in no row of the control gap register; the test records at EV-516 carry a form-by-form result so the claim can be tested as a claim about forms | IS-30, ADR-0032, PR-27
PR-38 | The 89 are reported as mitigated, and enforcement discretion is read inside Helix as permission | Terrence Abbatiello | ADR-0035 and ADR-0003 are standing framing — a programme that reads enforcement discretion as permission has read the wrong document; the register publishes the 62 in the same table as the 89; 21 CFR 211.68 and 21 CFR 211.100(b) are named wherever the cut appears | IS-33, ADR-0035, ADR-0003, PR-08
PR-39 | A reason-for-change field is reported as compliance with 21 CFR 11.10(e), or with Part 11 generally, in a briefing, a vendor discussion or a slide | Joachim Reuter | ADR-0036 is standing framing; the enumeration at EV-527 and the no-obscuring test records at EV-528 are kept as two separate items so that neither can stand in for the other; ../05.10-the-inversion.md states in terms that the field answers nothing in Part 11 | IS-32, ADR-0036, IS-06
PR-40 | 21 CFR 11.200 is described as a multi-factor authentication requirement, most likely by somebody outside the programme summarising IS-31 | Amara Sissoko | Standing framing since Phase 01 — Part 11 requires no multi-factor authentication; ../05.07-the-continuing-component.md §2 disposes of it before the finding; the finding is stated as *which component the system asks for* and never as *how many factors* | IS-31, ADR-0033, PR-09
PR-41 | The Not met cut by system owner is read inside a function as a criticism of the function, or of an individual | Dr Sunita Raghunathan | The cut is published with the sentence that it is a fact about where systems sit; no document in this repository assesses any individual's work; the gap register's owner column names the individual who can bring the closure condition about and is deliberately not the system owner column | PR-11, PR-25, ADR-0008
PR-42 | The control position register is treated as a compliance certificate — cited to a customer, a partner or an auditor as evidence that Helix's systems meet Part 11 | Colm Ó Braonáin | There is no Part 11 certification, no Part 11 certificate and no FDA-approved, FDA-validated or FDA-certified software, and PR-07 has carried the vendor form of this since Phase 01; the register's §6 states what it does not carry; IS-34 is published as an open issue rather than as a limitation | IS-34, PR-07, PR-20, ADR-0034