## Commitments
ID | The commitment | Observation | In scope | Named owner | Date the response gave | Completion criterion | Position | Discharged by | Owner's own tracking | Evidence
RC-01 | *"Helix will revise the cleaning validation master plan to state the acceptance criteria for each product and equipment train combination, and will requalify the affected trains against it."* | OBS-1 | No | Bernard Kwiatkowski | 2026-10-30 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-02 | *"Helix will re-establish the maximum campaign length and the dirty-hold and clean-hold times for the affected equipment trains, supported by data."* | OBS-1 | No | Bernard Kwiatkowski | 2026-12-18 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-03 | *"Helix will determine, record type by record type, which of the records generated on the chromatography data systems are records required by a predicate rule and are subject to 21 CFR Part 11."* | OBS-2 | Yes | Dr Sunita Raghunathan | 2026-07-31 | Yes | Met | The programme | Open. The laboratory's own commitment tracker records this commitment as in progress at the vantage | EV-806, EV-808 · ../../02-the-system-inventory-and-part-11-applicability/logs/record-type-register.md, GOV-09
RC-04 | *"Helix will establish what the audit trail on each chromatography data system records and what it does not, and will document the position for each system."* | OBS-2 | Yes | Dr Sunita Raghunathan | 2026-09-30 | Yes | Met | The programme | Open. The laboratory's own commitment tracker records this commitment as in progress at the vantage | EV-806, EV-808 · ../../06-the-chromatography-data-system/logs/auditable-event-register.md
RC-05 | *"Helix will revise the laboratory record review procedure to state whether the audit trail associated with a result forms part of the original record reviewed under 21 CFR 211.194(a)(8), and to state what the reviewer must examine."* | OBS-2 | Yes | Terrence Abbatiello | 2026-09-30 | Yes | Not met | — | Open, and past the date the response gave. No revision has been issued | EV-807, EV-810 · IS-06, IS-24, DP-07
RC-06 | *"Helix will train every analyst and every second-person reviewer in the revised laboratory record review procedure and will record the training."* | OBS-2 | Yes | Dr Sunita Raghunathan | 2026-10-30 | Yes | Not met | — | Open, and past the date the response gave. The content it would be delivered against depends on the revision at RC-05 | EV-807, EV-810
RC-07 | *"Helix will continue to reinforce the importance of data integrity in the quality control laboratories."* | OBS-2 | Yes | Dr Sunita Raghunathan | 2026-12-31 | No | No completion criterion | — | Recorded as ongoing, with no state at which it would be recorded otherwise | EV-809
RC-08 | *"Helix will revise the environmental monitoring programme to require trending of viable and non-viable counts by room and by shift at a stated frequency."* | OBS-3 | No | Dr Sunita Raghunathan | 2026-08-31 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-09 | *"Helix will re-establish alert and action levels for each classified area from the preceding twelve months of monitoring data."* | OBS-3 | No | Dr Sunita Raghunathan | 2026-11-30 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-10 | *"Helix will identify every system in the estate on which a user account is shared by more than one individual."* | OBS-4 | Yes | Amara Sissoko | 2026-06-30 | Yes | Met | The programme | Open. The IT organisation's own commitment tracker records this commitment as in progress at the vantage | EV-806, EV-808 · ../../05-access-audit-trails-and-electronic-signatures/logs/control-gap-register.md, CG-11, CG-12, CG-13, CG-21
RC-11 | *"Helix will record, for each packaging line system, whether system access is limited to authorised individuals and whether an authority check operates."* | OBS-4 | Yes | Amara Sissoko | 2026-09-30 | Yes | Met | The programme | Open. The IT organisation's own commitment tracker records this commitment as in progress at the vantage | EV-806, EV-808 · ../../05-access-audit-trails-and-electronic-signatures/logs/control-position-register.md, the (d) and (g) columns
RC-12 | *"Helix will withdraw the shared local operator account from the packaging line systems and will issue a named individual account to every operator who uses them."* | OBS-4 | Yes | Amara Sissoko | 2026-08-31 | Yes | Not met | — | Open, and past the date the response gave. The account was still in use at the Phase 05 vantage of 2027-01-29 | EV-816, EV-817 · CG-11, CG-13, and the (d) column of the control position register · IS-56
RC-13 | *"Helix will ensure that the identity of the person performing and the person checking each significant step on a packaging line is recorded."* | OBS-4 | Yes | Bernard Kwiatkowski | None stated | Yes | Not met | — | Open. The response stated no date and none has been set since | EV-816, EV-817 · 21 CFR 211.188(b)(11)
RC-14 | *"Helix will reinforce with packaging operators the importance of individual accountability for entries made on line systems."* | OBS-4 | Yes | Bernard Kwiatkowski | 2026-09-30 | No | No completion criterion | — | Recorded as ongoing, with no state at which it would be recorded otherwise | EV-809
RC-15 | *"Helix will requalify the affected material suppliers and will revise the supplier qualification procedure to state the requalification interval."* | OBS-5 | No | Terrence Abbatiello | 2026-11-30 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-16 | *"Helix will complete an on-site audit of the two suppliers identified during the inspection."* | OBS-5 | No | Terrence Abbatiello | 2027-02-26 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-17 | *"Helix will remove the ability to amend a value on an approved electronic batch record other than through a controlled change, and will record any such change under change control."* | OBS-6 | Yes | Joachim Reuter | 2026-06-30 | Yes | Met | The named owner | Recorded complete in the owner's own change control tracking | EV-820, EV-821 · ../../05-access-audit-trails-and-electronic-signatures/logs/control-position-register.md, SYS-001 — the state, and not the change to it · IS-53
RC-18 | *"Helix will establish, for the electronic batch record system, whether a change to a stored value obscures the value previously recorded."* | OBS-6 | Yes | Joachim Reuter | 2026-09-30 | Yes | Met | The programme | Open. The automation function's own commitment tracker records this commitment as in progress at the vantage | EV-806, EV-808 · the (e) column of the control position register, and CG-15's named systems
RC-19 | *"Helix will extend the quality unit's review of the electronic batch record to include the record of any change made after approval."* | OBS-6 | Yes | Terrence Abbatiello | 2026-11-30 | Yes | Not met | — | Open, and past the date the response gave. No procedure in the quality system requires the act | EV-807, EV-810 · IS-24, DP-07
RC-20 | *"Helix will improve the visibility of changes made to electronic batch records after approval."* | OBS-6 | Yes | Joachim Reuter | 2026-12-18 | No | No completion criterion | — | Recorded as ongoing, with no state at which it would be recorded otherwise | EV-809
RC-21 | *"Helix will reconcile the training matrix for every GxP role against the current procedure set and will close the gaps identified."* | OBS-7 | No | Terrence Abbatiello | 2026-10-30 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106
RC-22 | *"Helix will revise the training procedure to require a role-based curriculum and to state what evidence of training completion is retained."* | OBS-7 | No | Terrence Abbatiello | 2027-01-29 | Yes | Not assessed | — | Not examined by this assessment; tracked by its named owner in the quality system | EV-106