## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-801 | 2027-03-22 | Open Phase 08 and fix its boundary: the position of the three electronic-records observations, the position of the commitments the response of 2026-03-06 made, the periodic review arrangement, and the conditions the four internal audits are read against — with no closure of any observation, no representation to FDA, no compliance conclusion, no CAPA, no deviation, no remediation plan, no remediation cost, no revision of any commitment, no result of any periodic review, and no candidate explanation of IS-01 named by number or by content | Lydia Marchetti-Nwosu | — | Steering Committee, EV-801
DEC-802 | 2027-03-23 | Adopt the source pack for the provisions this phase cites, each retrieved and checked at its primary source: 21 CFR 211.194(a)(8) whole, all three of its tests; 21 CFR 211.194(a)(7); 21 CFR 211.188(b)(11); 21 CFR 211.192; 21 CFR 211.180(e) whole, and the record that it is a product review; 21 CFR 11.10(d), (e) and (g); and EU GMP Annex 11 clauses 9 and 11 in the January 2011 text, labelled EU-derived. Renew the standing framing: there is no Part 11 certification; enforcement discretion is not an exemption; 21 CFR Part 11 sets no review frequency and no reason-for-change requirement; and no Annex 11 obligation binds Helix's US-facing route | Rebekah Sandquist | — | EV-802, EV-803
DEC-803 | 2027-03-24 | An observation is disposed of by stating the condition's present position, never by stating that it is closed. Closure is a representation to FDA about the state of a matter between the firm and the agency, and this programme makes none. What a firm may state about itself is what it has found to be so at a vantage, with the evidence named | Terrence Abbatiello | ADR-0051 | GOV-36, EV-804
DEC-804 | 2027-03-25 | Authorise the disposition record form and the commitment assessment method, both fixed before EV-106 was opened and before any observation was looked at: for each commitment, read the words the response used, ask whether they name a state of the world that could be observed to obtain, and record the answer or its absence; describe the practice only after the commitment has been read, because a commitment read backwards from what happened is a description of what happened | Priyanka Venkataraman | — | GOV-36, EV-805, ../templates/commitment-assessment-record-template.md
DEC-805 | 2027-03-29 | The commitments are assessed against their own words, and a commitment with no completion criterion is recorded as having none rather than judged. A commitment written so that nobody can say whether it was met is a commitment nobody can be held to; supplying the test now would be writing a commitment Helix did not file | Rebekah Sandquist | ADR-0052 | GOV-37, EV-805
DEC-806 | 2027-03-30 | Record the read of EV-106: twenty-two commitments, RC-01 to RC-22, of which fourteen attach to OBS-2, OBS-4 or OBS-6 and are assessed, and eight attach to OBS-1, OBS-3, OBS-5 or OBS-7 and are not, because this repository has never annexed the four out-of-scope observations and does not start now — ADR-0006. Of the fourteen: Met 6, Not met 5, No completion criterion 3. Of the five not met, four are past the date the response gave and one states no date at all. Raise IS-51 | Rebekah Sandquist | — | EV-806 to EV-810
DEC-807 | 2027-03-31 | Approve the commitment register — RC-01 to RC-22 — and record the discharge analysis it computes: of the six commitments met, five were discharged by this programme and not by the commitment's named owner, and in each of the five the owner's own tracking still shows the commitment open. Raise IS-52; open AS-53, AS-54, DP-43. No commitment is rewritten and no new one is made | Terrence Abbatiello | — | GOV-37, EV-808, EV-811
DEC-808 | 2027-04-01 | Periodic review is adopted voluntarily where FDA requires none, and its EU-derived limb is labelled EU-derived at every citation. Nothing in 21 CFR Part 11 or Parts 210 and 211 requires a periodic review of a computerised system; 21 CFR 211.180(e) is a product review and is never cited as the basis for one; EU GMP Annex 11 asks for one as a *should*, on the EU-facing route Dr Anselm Ferrão owns. Helix cannot say which systems that route reaches, because no product-to-system mapping exists in any register this programme has built — so one standard is adopted across all sixty-one, not as generosity but because the subset cannot be identified, and that is recorded as the reason. Raise IS-54; open DP-44 | Dr Marguerite Oyelaran | ADR-0053 | GOV-39, EV-825, EV-826
DEC-809 | 2027-04-02 | Record the OBS-2 position: the condition the observation records is confirmed, the remediation is defined, and it is not complete. Phase 06 characterised the subject matter at depth across thirty-four auditable event classes on the two chromatography instances; RC-03 and RC-04 are met and RC-05 and RC-06 are not; and part of what remains owed cannot be completed on the current product version, because AE-08 and AE-16 cannot be enabled by any setting available to Helix. The observation is not closed and is not described as closed | Dr Sunita Raghunathan | — | GOV-38, EV-813, EV-814, EV-815
DEC-810 | 2027-04-02 | Record the OBS-4 position: the condition the observation records is confirmed and it is not corrected. At the Phase 05 vantage of 2027-01-29 the shared local operator account was still in use on the packaging line system FDA observed — the 483 was issued on 2026-02-13 and that is three hundred and fifty days — and on eight further systems: CG-11 names seven and CG-13 names two, and 7 + 2 = 9. RC-12 is not met and is past the date the response gave. No cell of the control position register is re-determined and no CAPA is stated. Raise IS-56; open AS-55, PR-61 | Amara Sissoko | — | GOV-38, EV-816 to EV-819
DEC-811 | 2027-04-05 | The review frequency defaults to the Phase 04 complexity-and-reliability band and departs from it only upward, with a reason recorded in the row. High → Annual, Medium → Two-yearly, Low → Three-yearly, applied to all sixty-one before any row was looked at individually; a departure to a longer interval is not available, because a band that can be argued away in the same document that publishes it is not a band | Colm Ó Braonáin | ADR-0054 | GOV-39, EV-827
DEC-812 | 2027-04-06 | Record the OBS-6 position: the condition the observation records is corrected. At the Phase 05 vantage SYS-001 is *Met and required* on all eleven paragraphs of 21 CFR 11.10 — the only one of the sixty-one that is — and RC-17, the commitment to remove the ability to amend an approved value other than through a controlled change, is met and was discharged by its named owner. And no register this programme built records when the condition stopped obtaining, by what act, or on whose authority. The registers record the present state and not the change to it; the change control record exists in the quality system, outside every register this programme built. ADR-0006's refusal to split the observation into its two propositions stands: the observation is disposed of whole, and the second proposition — a change not visible in the record presented for review — remains a class the estate carries at CG-15. Raise IS-53; open DP-47, PR-61 is already open | Joachim Reuter | — | GOV-38, EV-820 to EV-824
DEC-813 | 2027-04-07 | The four candidate explanations recorded at 01.09 §6 are never chosen among, and IS-01 closes on what the programme can establish rather than on what it cannot. What it establishes: the six observable features of the four audits at 01.09 §5, restated as conditions AC-01 to AC-06, and that not one of the six obtained in any of the four audits. What it does not establish and never will: why. IS-01 CLOSED, against the evidence named at raid-log.md §1.9. The refusal to choose among the four is permanent, it is not handed to Phase 09, and no candidate is named in the closure, in this phase, or ever | Gideon Halvorsen | ADR-0055 | GOV-40, EV-830 to EV-832, EV-835
DEC-814 | 2027-04-07 | Approve the audit condition register — AC-01 to AC-06 — and accept its counts: none of the six conditions obtained in any of the four audits, 0 of 24 cells; five of the six are capable of being met now and one is not; and read access for the audit function has been requested on 0 of the 61 systems and granted on 0. Raise IS-55; open AS-58, DP-46. The register states conditions and whether they obtained, and draws no inference about why any audit raised what it raised | Dr Marguerite Oyelaran | — | GOV-40, EV-830, EV-833, EV-834
DEC-815 | 2027-04-08 | A remediation the programme performed is credited to the programme and not to the commitment's owner, and the difference is recorded. Where the act that satisfied a commitment was performed by this programme, the register says so; it does not report the commitment as discharged by the individual the response named, and it does not silently correct the owner's own tracking to agree with it. A commitment tracked in one place and discharged in another is a commitment nobody is tracking | Lydia Marchetti-Nwosu | ADR-0056 | GOV-40, EV-811, EV-812
DEC-816 | 2027-04-08 | Approve the periodic review register — RV-01 to RV-61 — and the arrangement it establishes: the default from the Phase 04 band is Annual 11, Two-yearly 27, Three-yearly 23; twenty systems are moved to a shorter frequency, each for a reason recorded in its own row — eleven Medium to Annual and nine Low to Two-yearly — and none is moved to a longer one; the result is Annual 22, Two-yearly 25, Three-yearly 14, and 22 + 25 + 14 = 61. The first review due on every row falls after this vantage, no review has been performed against any row, and no result of any review is reported by this phase. Raise IS-57; open AS-56, AS-57, DP-45, PR-62 | Terrence Abbatiello | — | GOV-39, GOV-40, EV-828, EV-829
DEC-817 | 2027-04-08 | Phase 08 states no compliance conclusion, closes no observation and makes no representation to FDA. It states the present position of three conditions, the position of twenty-two commitments and the arrangement it has established, and it stops there. IS-04, IS-06 and IS-50 CLOSED against named evidence, on the papers put by their owners — Terrence Abbatiello for IS-04 and IS-50, Dr Sunita Raghunathan for IS-06. IS-01's closure of the previous day is recorded and ratified, and the permanence of the refusal is minuted | Dr Marguerite Oyelaran | ADR-0057 | GOV-40, EV-836, EV-837
DEC-818 | 2027-04-09 | Publish Phase 08 at MS-12; hand the four registers, the three dispositions, the four closures and the arrangement to Phase 09; and record IS-58 — every determination in this repository was made by the people who also own the things determined, and the one function that could have tested them independently has never been given the access to do it. The programme has assessed itself. Open PR-63 | Lydia Marchetti-Nwosu | — | Steering Committee, EV-838