## Issues
ID | Issue | Owner | Raised | Status | Related
IS-01 | Four internal audits between 2023-06 and 2025-09 covered all three systems between them, each falling inside the scope of at least two, and none raised a finding on the subject matter of OBS-2, OBS-4 or OBS-6. Why is not established | Gideon Halvorsen | 2026-05-19 | CLOSED 2027-04-07 — DEC-813, ADR-0055, ratified at GOV-40. See the closing note at §1.9 below, which is set out in full rather than compressed into this cell
IS-02 | No written record exists of which Helix records are Part 11 records | Priyanka Venkataraman | 2026-03-13 | CLOSED 2026-07-28, unchanged. It is the artefact AC-06 turns on, and AC-06 is capable of being met because of it
IS-03 | The register of computerised systems carries no predicate-rule attribute | Amara Sissoko | 2026-04-24 | Open, unchanged. The record-type register carries the predicate rule; the systems register still does not
IS-04 | CAL-06's cadence is undefined where CGMP does not specify a review frequency for the underlying data | Terrence Abbatiello | 2026-05-29 | CLOSED 2027-04-08 — DEC-817, minuted at GOV-40. Closure evidence: EV-802 the source pack, with 21 CFR 211.194(a)(8) read whole and 21 CFR 211.192 beside it · EV-803 the standing framing note · EV-810 the record of what RC-05 and RC-19 are and are not · EV-825 the position paper on what requires a periodic review · EV-837 the closure record · GOV-39, GOV-40. What closed it: the first half of the question is answered and the second half is now correctly located. The review of the audit trail associated with a record is part of the review of that record, which 21 CFR 211.192 and 21 CFR 211.194(a)(8) require on an event and not on a cycle; where CGMP specifies the review frequency for the underlying data, the audit trail review inherits that frequency, and FDA's December 2018 drug CGMP data integrity guidance names two — *"…§ 211.188(b) requires review after each significant step in manufacture, processing, packing, or holding, and § 211.22 requires data review before batch release."* Where CGMP specifies none, the same guidance states that *"…you should determine the review frequency for the audit trail using knowledge of your processes and risk assessment tools."* — a nonbinding recommendation, never described here as a requirement, and one this phase does not discharge; IS-24 and DP-07 carry it. No stand-alone periodic audit trail review frequency is named by any primary source, none is set here for any record, and none is attributed to any source — 21 CFR Part 11 names none, and EU GMP Annex 11 clause 9's expectation that audit trails *"…be available and convertible to a generally intelligible form and regularly reviewed"* is a *should* in a guideline that is not FDA's, is labelled EU-derived, and names no interval either. The periodic review established in this phase is a review of a system and is not CAL-06; RV-01 to RV-61 set nothing about when a record is reviewed. What IS-04 never asked is whether any Helix procedure requires the reviewer to open the audit trail at all — it does not, RC-05 is the commitment to make it do so and is Not met, and IS-24 and DP-07 carry the remainder. The closure names its evidence
IS-05 | Helix cannot state, for any system, how long audit trail data is retained relative to the retention period of the underlying record | Joachim Reuter | 2026-05-01 | CLOSED 2027-03-18, unchanged. The remainder is IS-44's
IS-06 | The laboratory record review procedure does not state whether the audit trail associated with a result forms part of the original record reviewed under 21 CFR 211.194(a)(8) | Dr Sunita Raghunathan | 2026-05-15 | CLOSED 2027-04-08 — DEC-817, minuted at GOV-40. Closure evidence: EV-802 the source pack, with 21 CFR 211.194(a)(8) read whole · EV-807 the two procedure reads · EV-810 the record of RC-05's position and of what it is owed against · EV-837 the closure record · GOV-40. What closed it: the question is now answered in both directions and neither answer is comfortable. What the obligation requires is established. 21 CFR 211.194(a)(8) states three tests and not one, and FDA's December 2018 drug CGMP data integrity guidance treats the audit trail as part of the record being reviewed. The provision is read in its own words at ../08.05-obs-2.md §2, which owns that argument. That is guidance, it is nonbinding, it represents FDA's current thinking, and it is never called a requirement here. What the procedure says is also established: it still does not say it. RC-05 is the commitment the response of 2026-03-06 made to revise it, its named owner is Terrence Abbatiello, the date it gave was 2026-09-30, and it is Not met. IS-06 was raised as an unanswered question and it is answered; an issue closes when it has been answered and not when the answer is the one anybody wanted. What IS-06 never asked is whether anybody would be required to do it once the procedure said so — a sentence in a procedure that nobody is obliged to follow is IS-24's subject and DP-07's route, and both are open. The closure names its evidence
IS-07 | Seven of the twelve calendar entries outlive the programme and none has a named owner after close-out | Lydia Marchetti-Nwosu | 2026-05-27 | Open — deliberately unresolved, and it is now the sharpest entry in the log. CAL-07 is one of the seven, and RV-01 to RV-61 are sixty-one commitments whose earliest first due date falls a month after close-out on 2027-04-30 and whose latest falls a year after it. The arrangement this phase established has no named owner beyond the date the programme ends, and IS-57 and this entry meet on that fact. The obvious answer — that the quality unit holds them under 21 CFR 211.22 — is probably right, is still not written down, and this log is still not going to write it down on the programme's behalf
IS-08 | Seven record types were Part 11 records throughout the period Helix treated them as outside Part 11 | Dr Sunita Raghunathan | 2026-07-10 | Open, unchanged. The OBS-2 position at ../08.05-obs-2.md is stated without drawing anything from this entry, and nothing here is offered as evidence about any audit
IS-09 | 21 CFR 11.10 has never been assessed for the three vendor-hosted systems | Joachim Reuter | 2026-07-17 | Open on its second limb, unchanged, and named in two moved rows. SYS-040 and SYS-056 are moved to Annual for this reason and SYS-041 is already Annual on its band — all three vendor-hosted systems are reviewed annually, and none has been reviewed
IS-10 | The applicability determination exists and nothing requires it to be maintained | Terrence Abbatiello | 2026-07-28 | CLOSED 2026-11-20, unchanged. SOP-DI-05 has still not fired on any change
IS-11 | Nobody has assessed whether the data in the 34 in-scope record types is any good | Priyanka Venkataraman | 2026-07-31 | CLOSED 2026-09-24, unchanged
IS-12 | Where the records of the nine removed systems now are is not established | Amara Sissoko | 2026-06-12 | Open, unchanged. The nine removed entries carry no SYS identifier and are therefore on no row of periodic-review-register.md, which is correct and is also the reason nothing will ever look for them
IS-13 | Seventeen systems entered the inventory that had never entered a validation lifecycle | Colm Ó Braonáin | 2026-06-12 | Open, unchanged, and instanced. SYS-061 is one of the seventeen and is one of the nine Low-band systems moved to a shorter review frequency, its row naming the walk among its reasons
IS-14 | No retention period is recorded against any of the 34 Part 11 record types | Priyanka Venkataraman | 2026-07-24 | CLOSED 2027-03-09, unchanged. The remainder is IS-44's
IS-15 | *"Original or a true copy"* fails or cannot be determined on a large majority of the 121 pairs | Priyanka Venkataraman | 2026-09-15 | Open, unchanged. No Phase 03 determination has moved and none can here, and no document in Phase 08 prints Phase 03's attribute figure
IS-16 | 47 pairs cannot be scored, and the programme has refused to score them low | Priyanka Venkataraman | 2026-09-25 | Open, unchanged. No ND became determinable in this phase
IS-17 | The 24 pairs from Phase 02's seven newly in-scope record types have no assessment history | Dr Sunita Raghunathan | 2026-09-17 | Open, unchanged. They now sit on systems with a review frequency, which is a future and not a history
IS-18 | The transfer between systems is assessed nowhere, for 31 of the 34 in-scope record types | Joachim Reuter | 2026-09-22 | Open, unchanged. OB-36 and SOP-DI-04 remain undischarged and unapplied
IS-19 | The scale is a written procedure Helix will be held to under 21 CFR 211.22(d) | Terrence Abbatiello | 2026-09-11 | CLOSED 2026-11-20, unchanged
IS-20 | A rating is not a control position, and nothing says whether any control works | Gideon Halvorsen | 2026-09-29 | Open on its second limb, unchanged — and it is the shape of IS-57. An arrangement to review a system is not a review of it, exactly as a backup file recorded as maintained is a file observed to exist
IS-21 | The assessment says where the data is weak; nothing in the quality system says what Helix must do | Priyanka Venkataraman | 2026-09-30 | CLOSED 2026-11-25, unchanged
IS-22 | Not one of the 44 packages evidences 21 CFR 11.10(a)'s fourth clause | Colm Ó Braonáin | 2026-11-06 | Open, unchanged. No package is withdrawn, invalidated or superseded by anything here
IS-23 | 17 of the 61 systems have no validation package at all | Colm Ó Braonáin | 2026-11-06 | Open, unchanged, and named in the register. Thirteen of the seventeen carry the validation status report EU GMP Annex 11 clause 11 names — EU-derived — as an item the review would examine and would not find; RV-36, RV-59, RV-60 and RV-61, the other four, carry it under the retention-estate item instead. 13 + 4 = 17
IS-24 | 12 obligations land in a procedure that exists and does not require the act | Terrence Abbatiello | 2026-11-17 | Open, and instanced twice more. No procedure in Helix's quality system requires the laboratory record reviewer to open an audit trail — which is RC-05, Not met — and none requires the quality unit's review of an electronic batch record to include the record of changes made after approval — which is RC-19, Not met. None of the nine SOPs has been applied to anything
IS-25 | 5 obligations land in no procedure at all | Priyanka Venkataraman | 2026-11-17 | Open, unchanged. No procedure requires a periodic review of a computerised system either, and the arrangement established here is a programme arrangement rather than a procedural requirement — IS-57, DP-45
IS-26 | The two graduations disagree on 17 of the 36 | Joachim Reuter | 2026-11-02 | Open, and open by design, unchanged. No band has moved and none can move here. Five of the twenty systems moved to a shorter review frequency are the five at Phase 04's §4 on which the record is graver than the system, which reads the disagreement rather than resolving it
IS-27 | 25 systems have no established data integrity position | Priyanka Venkataraman | 2026-10-29 | Open, unchanged. A review frequency is not a data integrity position and does not supply one
IS-28 | The framework says what evidence every system must produce and nothing has produced any of it | Colm Ó Braonáin | 2026-11-30 | CLOSED 2027-01-28, unchanged. IS-34 carries the second half
IS-29 | 218 of the 520 controls that are present are required by nothing and can be withdrawn without a deviation | Priyanka Venkataraman | 2027-01-06 | Open, unchanged, and engaged from a new direction. A periodic review that finds a control present says nothing about whether anything requires it to stay there, and RV-01 to RV-61 set what a review examines without setting what a procedure requires. DP-27 is unmoved and no sentence has been written
IS-30 | The meaning of the signature is absent from the exported or printed form on 12 of the 19 systems that execute signatures | Priyanka Venkataraman | 2027-01-13 | Open, unchanged. Nothing in this phase tested a human readable form
IS-31 | 7 of the 19 re-prompt for the user identification code rather than the password | Amara Sissoko | 2027-01-20 | Open, unchanged. No session test was performed
IS-32 | 23 systems hold a reason-for-change field Part 11 does not require, and 14 of them fail the no-obscuring requirement it does | Joachim Reuter | 2027-01-28 | Open, unchanged, and mirrored inside the programme. IS-53 is the same shape applied to the programme's own registers: a record that shows the present state and not the change to it. Holding a reason-for-change field is still never reported as compliance with anything — ADR-0036
IS-33 | 89 of the 151 failures sit in the four paragraphs discretion reaches in full, and nothing about that changes the position | Terrence Abbatiello | 2027-01-27 | Open, and open by design, unchanged. 21 CFR 11.10(d) is not inside the discretion set, and OBS-4's position is stated without reference to it. Enforcement discretion is FDA's stated intention about what it will enforce; it is not an exemption, not a safe harbour, and it confers no rights
IS-34 | A control position is not validation evidence, and the evidence Phase 04 requires is owed in full | Colm Ó Braonáin | 2026-12-17 | Open, unchanged. A review frequency is not validation evidence either, and not one of the 38 obligations is discharged
IS-35 | The position is known for every paragraph on every system, and on 218 of them what is present is required by nothing | Joachim Reuter | 2027-01-29 | CLOSED 2027-02-25, unchanged. It named the mechanism that would hold a position in place as Phase 08's; the mechanism is now established at RV-01 to RV-61 and has not been run — IS-57
IS-36 | Three of the eleven event classes recording an act capable of changing a reportable result are recorded on neither chromatography instance, and two of the three cannot be enabled on this product version | Priyanka Venkataraman | 2027-02-12 | Open on both limbs, unchanged — and it is now load-bearing on a disposition. AE-08 and AE-16 cannot be enabled by any setting available to Helix, and that is why part of what remains owed under OBS-2 cannot be completed on the current product version — ../08.05-obs-2.md. Nothing in this phase touched either configuration; DP-33 and DP-35 have not moved
IS-37 | The two chromatography instances differ in two published registers and were compared in neither | Amara Sissoko | 2027-02-25 | Open, unchanged. Both carry the same review frequency at RV-23 and RV-24 and a common frequency is not a comparison
IS-38 | Nine reportable results carry a value that differs from the first integration, and on none of the nine does the record show both | Dr Sunita Raghunathan | 2027-02-17 | Open, unchanged, and no reintegration is characterised by anything in this phase — ADR-0043
IS-39 | On SYS-024 the reportable result reaches the LIMS by manual transcription | Joachim Reuter | 2027-02-19 | Open, unchanged. No verification arrangement is stated by this phase
IS-40 | RT-12 and RT-13 are also held on SYS-036, SYS-060 and SYS-061, two owned by a different named individual, and none of the three was assessed at depth | Amara Sissoko | 2027-02-24 | Open, unchanged on the limb that matters. All three now carry a shortened review interval and none has been reviewed, and DP-17 is not discharged
IS-41 | Two of sixty-one systems were assessed at a depth unavailable for the other fifty-nine | Colm Ó Braonáin | 2027-02-18 | Open, and open by design, unchanged — and its counterpart caution runs through this phase. Phase 08 read documents. It read a commitment register, four audit records, three published registers and a set of provisions; it opened no system, executed no test and examined no record. A disposition drawn from documents is a position about documents
IS-42 | The record cannot show what happened, and the data it cannot show it about is retained somewhere | Dr Sunita Raghunathan | 2027-02-26 | CLOSED 2027-03-18, unchanged. IS-50 carried its unexamined limb and closes here
IS-43 | On thirteen systems 21 CFR 11.10(c) was determined Met against a records retention period that does not exist | Terrence Abbatiello | 2027-03-18 | Open, unchanged. No cell has moved and none can move here — ADR-0049. It closes when a period exists for the record types those thirteen systems hold, which is IS-44's and DP-38's, and nothing in Phase 08 supplies one
IS-44 | Fourteen of the thirty-four in-scope record types have a retention period set by no predicate rule, and no named individual has determined one | Priyanka Venkataraman | 2027-03-09 | Open, unchanged, and now with a periodic review beside it that will not answer it. A periodic review of a system is not a determination of a retention period for a record type, and no row of periodic-review-register.md sets, proposes or bounds one. DP-38 is unmoved and competes with DP-07, DP-11, DP-22, DP-27, DP-35 and now DP-43, DP-45 and DP-47 for the same quality unit capacity
IS-45 | The electronic master production and control record — RT-02 — has a retention period set by nothing | Priyanka Venkataraman | 2027-03-09 | Open, unchanged, and instanced. RT-02 is held on SYS-001 and SYS-059, and SYS-059 is one of the twenty systems moved to a shorter review frequency, its row naming this among its reasons — RV-59. A shorter review interval is not a period
IS-46 | A restore has been performed on four of sixty-one systems, all four as incident recovery, and on none was what came back compared with what went in | Amara Sissoko | 2027-03-12 | Open on both limbs, unchanged. No restore was performed in this phase and no carve-out determination was made. The four systems of the retention estate all carry a shortened review interval and what a review would examine is recorded at RV-36, RV-59, RV-60 and RV-61; nothing has been examined
IS-47 | Three of the four systems that constitute the retention estate are owned by the Chief Information Officer, none by the quality unit, and one entered the inventory by walk | Amara Sissoko | 2027-03-10 | Open, unchanged. It does not close by the systems being reviewed more often, and the four rows that name it say so
IS-48 | Records of Cary activities are held at the Ridgemont data centre and 21 CFR 211.180(c)'s immediate-retrieval saving has been demonstrated, timed and recorded on none of them | Joachim Reuter | 2027-03-11 | Open, unchanged. DP-39 has not moved and no retrieval has been performed
IS-49 | The four printout record types have no stated retention location, no named individual accountable, no derived period and no reproduction under 21 CFR 211.180(d) | Dr Sunita Raghunathan | 2027-03-17 | Open, unchanged. The four are outside the 61 and outside periodic-review-register.md entirely, and nothing in this phase reaches them — ADR-0046, PR-55
IS-50 | Everything now has a period, an owner or an explicit gap where one of those is missing — and not one of the arrangements has ever been examined by anybody at Helix whose job it was to look | Terrence Abbatiello | 2027-03-19 | CLOSED 2027-04-08 — DEC-817, minuted at GOV-40. Closure evidence: EV-828 the periodic review register · EV-829 the reconciliation of its counts · EV-830 the audit condition register · EV-831 and EV-832 the working papers joining the six conditions to the four audits · EV-836 the closure record · GOV-39 and GOV-40. What closed it: somebody has now looked, and an arrangement now exists for looking again. The four audits between 2023-06 and 2025-09 have been read against six conditions and not one of the six obtained in any of them, 0 of 24 cells; the commitments filed on 2026-03-06 have been read for the first time since they were filed; the three electronic-records observations have each been given a position; and an arrangement covering all sixty-one systems has been established with a frequency and a first due date on every row. What IS-50 never asked is whether the function whose job it is to look can get at the systems it would have to look inside. It assumed that the obstacle was that nobody had looked. The obstacle that remains is that the one function independent enough to test what the programme has built has read access on none of the sixty-one — IS-55 — and that every determination in the repository was made by the people who own the things determined, which is IS-58 and is Phase 09's. The closure names its evidence; *believed complete* is not a closure condition
IS-51 | Three of the fourteen commitments assessed carry no completion criterion, so no state of the world would satisfy them and none can be judged met or unmet. RC-07, RC-14 and RC-20. Each was owned by a named individual, each carried a date the response stated, and each passed that date without anything happening that could have been recorded either way — the element that is absent is not the owner and it is not the date, it is the test. A commitment written so that nobody can say whether it was met is a commitment nobody can be held to. The three are recorded as having no completion criterion and are not judged: recording them met would credit Helix with a change it cannot demonstrate, and recording them not met would manufacture a failure out of a drafting defect — ADR-0052. This entry proposes no completion criterion for any of the three, and writing one now would be writing a commitment Helix did not file | Rebekah Sandquist | 2027-03-30 | Open. It does not close by the three being rewritten, which is not available to this programme; it closes if and when a named individual states, as a new act with its own record, what would satisfy each of them | DEC-806, ADR-0052, GOV-37, ../08.03-the-commitments.md, commitment-register.md §3, AS-53, PR-59
IS-52 | Five of the six commitments met were discharged by the programme rather than by the commitment's named owner, and in each the owner's own tracking still shows the commitment open. RC-03, RC-04, RC-10, RC-11 and RC-18. The acts that satisfied them were the Phase 02 record-level determination, the Phase 06 auditable event characterisation and three Phase 05 determinations; the individuals the response named did none of them, and the trackers those individuals maintain record all five as in progress at this vantage. A commitment tracked in one place and discharged in another is a commitment nobody is tracking. This is a finding about two records that do not speak to each other and it is not an allegation that anybody acted improperly — nobody failed to do anything they were asked to do, and the work was done. The register does not correct either record to agree with the other — ADR-0056 — because two records made to agree by editing one of them are a tidier finding about nothing | Lydia Marchetti-Nwosu | 2027-03-31 | Open. DP-43 is the route. It does not close by the trackers being edited; it closes when each of the five owners has stated what their own record should now show and the reconciliation is itself recorded | DEC-807, DEC-815, ADR-0056, GOV-37, GOV-40, ../08.04-who-actually-did-it.md, commitment-register.md §4, AS-54, DP-43, PR-60
IS-53 | The correction of OBS-6's condition is evidenced by no register this programme built. At the Phase 05 vantage SYS-001 is *Met and required* on all eleven paragraphs of 21 CFR 11.10, the only one of the sixty-one that is, so the condition the observation records no longer obtained. And no register this programme built records when it stopped obtaining, by what act, or on whose authority. The control position register records the present state and not the change to it; the control gap register records what is absent and not what was closed; and the programme therefore built its own registers on the property it recorded the estate's records having: an instrument that records a state and not a transition cannot answer a question about a transition. Nothing was overwritten and no previously recorded information was obscured — 21 CFR 11.10(e), the paragraph about record changes not obscuring previously recorded information, is the analogy and not the finding, and the derivation and the disanalogy are at ../08.07-obs-6-and-the-register-that-cannot-show-it.md §4. A change control record exists in Helix's quality system and is outside every register this programme built — the programme did not build it, did not test it and does not annex it. The registers cannot evidence remediation and were not built to, and that is a statement about what the registers are, not a claim that the correction did not happen | Joachim Reuter | 2027-04-06 | Open. DP-47 is the route — a register that carries the previous position, the act, the date and the authority. It does not close by the change control record being cited; a record outside the programme's registers does not make the programme's registers able to show a change | DEC-812, GOV-38, ../08.07-obs-6-and-the-register-that-cannot-show-it.md, commitment-register.md, RC-17, DP-47, PR-61, IS-29, IS-35
IS-54 | No product-to-system mapping exists, so Helix cannot say which systems the EU-facing Annex 11 route reaches, and adopts one standard across all sixty-one because it cannot identify the subset. Nothing in 21 CFR Part 11 and nothing in Parts 210 and 211 requires a periodic review of a computerised system, and 21 CFR 211.180(e) is a product review and is not the basis for one. EU GMP Annex 11 asks for one as a *should*, in a guideline that is not FDA's, and it reaches Helix through Dr Anselm Ferrão's route for the EU-facing products — a route on which he acts for the holder of the EU manufacturing and import authorisation and not for Helix. Which of the 61 systems hold records for products on that route is not stated in any register this programme has built: Phase 02's systems register carries systems, Phase 02's record-type register carries record types, and no register joins either to a product. The coverage is therefore unnarrowed rather than generous, and the register records the absence that prevents the narrowing rather than presenting the breadth as a choice about quality | Rebekah Sandquist | 2027-04-01 | Open. DP-44 is the route. It does not close by the sixty-one-system scope being adopted, which is what the absence produced rather than what answers it | DEC-808, ADR-0053, GOV-39, ../08.08-nothing-requires-a-periodic-review.md, periodic-review-register.md §0, DP-44, PR-62, AS-10, DP-08
IS-55 | Read access for the audit function has been requested on none of the sixty-one systems and granted on none. Five of the six audit conditions can now be met and this one cannot. AC-01, AC-02, AC-03, AC-04 and AC-06 became capable of being met because this programme built the artefacts they turn on — the record-level determination, the obligation register, the control position and control gap registers, the auditable event register and the retention derivation register. AC-05 turns on a grant, and no artefact this programme could build supplies one. The programme has spent thirteen months building the determination, the registers and the evidence the audits needed, and nobody has given the auditors the key. Both halves are enquiry results and both enquiries are retained — EV-833 for the request and EV-834 for the grant — so that a nil return can be tested as a search. Nothing in this entry states that access was withheld, refused or denied, at any date, by anybody, and nothing in it explains anything about any of the four audits | Gideon Halvorsen | 2027-04-07 | Open. DP-46 is the route. It does not close by a request being made; it closes when access is granted and recorded, system by system. It is IS-58's first limb and the two are read together | DEC-814, GOV-40, ../08.10-what-would-have-had-to-be-true.md, audit-condition-register.md §4, AC-05, AS-58, DP-46, IS-58, PR-63
IS-56 | OBS-4's condition was still present at the Phase 05 vantage on the system FDA observed, and on eight further systems, three hundred and fifty days after the 483 was issued. The 483 was issued on 2026-02-13 and the Phase 05 vantage is 2027-01-29; that is three hundred and fifty days, and the counting convention is stated on the face of EV-818. CG-11 names seven systems — SYS-003, SYS-004, SYS-005, SYS-006, SYS-007, SYS-009, SYS-010 — and CG-13 names two — SYS-031, SYS-032. 7 + 2 = 9, and the packaging line system FDA observed is among the seven. RC-12, the commitment to withdraw the shared local operator account and issue a named individual account to every operator, was owned by Amara Sissoko, carried the date 2026-08-31, and is Not met. The distinction Phase 02 drew is carried and not lost: a shared account does not fail 21 CFR 11.10(d) on its face, because access is still limited to a group of authorised operators; what it defeats is attribution, which is 21 CFR 211.188(b)(11) and 21 CFR 211.194(a)(7) on the predicate-rule side. No cell of the control position register is re-determined by this entry — ADR-0049 — and no CAPA, deviation, remediation plan or cost is stated | Amara Sissoko | 2027-04-02 | Open. It does not close by the position being restated at a later vantage; it closes when the shared credential is withdrawn on each of the nine and named individual accounts are in use. Nothing in this phase read a system, and the position is Phase 05's as published — AS-55 | DEC-810, GOV-38, ../08.06-obs-4.md, CG-11, CG-13, RC-12, RC-13, AS-55, DP-20, IS-32
IS-57 | The periodic review is established and has not been run. An arrangement with a first due date is not a review, and nothing in this phase reports the result of one. RV-01 to RV-61 carry a frequency, a reason where the frequency departs from the Phase 04 band, and a first review due date; the earliest of those dates is 2027-05-31 and every one of the sixty-one falls after this vantage. Reviews performed: 0 of 61. CAL-07 has stood in the programme calendar since 2026-05-29 with a cadence of annual per system and a first occurrence of 2027-02-01, and nothing has been performed under it. No reviewer is named for any individual review, and who performs a review of a system whose owner is the person whose arrangements the review examines is a determination nobody has made — DP-45. The template at ../templates/periodic-review-record-template.md is an empty form | Colm Ó Braonáin | 2027-04-08 | Open, and open by construction. It does not close by the register being approved, which is what created it; it closes when a review has been performed against a row and recorded | DEC-816, ADR-0053, ADR-0054, GOV-39, ../08.09-the-review-established.md, periodic-review-register.md §3, CAL-07, DP-45, PR-62
IS-58 | The question Phase 08 leaves open, and it is Phase 09's: every determination in this repository was made by the people who also own the things determined, and the one function that could have tested them independently has never been given the access to do it. The programme has assessed itself. The record-level determination was made by the Data Integrity Lead and approved through Quality; the complexity-and-reliability band was determined by the validation function; the six hundred and seventy-one control positions were determined by the function that operates the systems; the backup and restore position was taken from enquiries answered by the people who operate the arrangements — AS-22, AS-40, AS-49; and the retention derivation, the auditable event characterisation, the commitment assessment and the three dispositions were all made inside the programme that had an interest in what they said. Every one of those determinations was made on a method fixed before the work and published with its assumptions, which is the whole of what the programme could do about it. What it could not do is grant itself independence. Read access for the audit function has been requested on 0 of the 61 systems and granted on 0 — IS-55 — and no determination in this repository has been tested by anybody who did not make it | Gideon Halvorsen | 2027-04-09 | Open — Phase 09 owns it, and Phase 09 is inspection readiness, continuous compliance and close-out. It is not an allegation of bias and it names no individual. It is not IS-01 in another form, it does not re-open IS-01, and no candidate explanation is named by it or reachable through it | DEC-818, ../08.13-phase-summary-and-transition.md, IS-55, AS-22, AS-40, AS-49, AS-58, DP-46, PR-63, ADR-0004

## Assumptions
ID | Assumption | Owner | Made
AS-01 | The Steering Committee continues monthly to close-out | Lydia Marchetti-Nwosu | Open, holding. The Phase 08 sitting of 2027-04-08 is minuted at GOV-40 and indexed at EV-838
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Open, holding
AS-03 | The record-level determination can be completed in Phase 02 from existing documentation | Priyanka Venkataraman | CLOSED at the MS-06 gate, unchanged
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open, and exercised again through AS-43
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open
AS-06 | No new GxP-critical platform is introduced before MS-06 | Amara Sissoko | CLOSED, tested and held
AS-07 | The 41 marketed products and the two QC laboratories remain the basis for record-type enumeration | Dr Sunita Raghunathan | Open, and engaged from a new direction. The 41 marketed products are the population a product-to-system mapping would be built from, and no such mapping exists — IS-54, DP-44
AS-08 | The commitments in the written response of 2026-03-06 are not varied by Helix | Rebekah Sandquist | Open, and this is the phase that rests on it. It has been carried untested since 2026-05-29; AS-53 is its Phase 08 form and states what fails if it is wrong
AS-09 | Thorne Delacroix Consulting's design work is complete before the third-party audit opens | Lydia Marchetti-Nwosu | Open — ADR-0004, PR-06
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding, and load-bearing for the first time. Clause 11 is the source of the nine items every row of periodic-review-register.md names, and clause 9 is quoted in IS-04's closure — both labelled EU-derived, and neither binding on the US-facing route
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding
AS-12 | Internal audit capacity is available for CAL-09 without displacing the annual audit plan | Gideon Halvorsen | Open, and drawn on. No result of CAL-09 or of CAL-10 is stated anywhere in this phase and no outcome of either is anticipated
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage | Amara Sissoko | Open, holding, and load-bearing again. Eleven of the seventeen systems the walk found carry a row on periodic-review-register.md and would carry none if the walk had not happened
AS-14 | The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable record and have no export | Dr Sunita Raghunathan | Open, unchanged. Those record types are outside the 34, outside the 61 and outside every register in this phase
AS-15 | Helix continues to administer every account on the three vendor-hosted systems | Joachim Reuter | Open, holding
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories | Priyanka Venkataraman | Open, and still under test. No record type was introduced in this phase
AS-17 | Vendors supply technical documentation sufficient to describe the seven newly in-scope record types | Joachim Reuter | CLOSED 2026-09-17, tested and FAILED, unchanged — and it is the precedent AS-43 works against
AS-18 | The 58 record types remain a stable unit through Phase 05 | Priyanka Venkataraman | Open, holding, and consumed again
AS-19 | The review trigger at ADR-0015 is operated by its named owner | Terrence Abbatiello | Open, and narrowed further. SOP-DI-05 still has not fired, and it is now asked to catch a fifth thing: a change to a system's complexity-and-reliability band, on which sixty-one review frequencies rest — AS-56
AS-20 | The 121 pairs derived on 2026-08-14 remain the population to MS-08 | Priyanka Venkataraman | Held and consumed, unchanged
AS-21 | Consequence is a property of the record type and travels with the class | Terrence Abbatiello | Open, holding, untouched
AS-22 | Those who supplied the facts described the position as it is rather than as procedure says it should be | Priyanka Venkataraman | Open, and still the widest assumption in the repository — and this is the phase that names what rests on it. IS-58 states that every determination in this repository was made by the people who own the things determined, and AS-22, AS-40 and AS-49 are the three places that was written down before anybody added them up
AS-23 | A determination of Not determinable records the absence of evidence and not the absence of a search | Gideon Halvorsen | Open, holding, and mirrored twice more. The nil returns at EV-833 and EV-834 are answers to questions that were asked, and both enquiries are retained
AS-24 | FDA's five attributes are sufficient to describe the integrity position of a Helix record type | Priyanka Venkataraman | Open, unchanged. No attribute was introduced and no assessment re-run
AS-25 | The scale published in Phase 03 is applied unchanged to MS-13 | Terrence Abbatiello | Open, unchanged. Nothing was re-scored
AS-26 | Many of the 35 GxP-relevant systems holding no Part 11 record are reached by 21 CFR 211.68, and others by different provisions of Part 211 | Colm Ó Braonáin | Open, unchanged, and engaged by an absence. The 35 are outside periodic-review-register.md entirely, and no periodic review reaches any of them
AS-27 | The three features graded in the complexity-and-reliability determination are sufficient to grade a system on the axis 21 CFR 211.68(b) names | Colm Ó Braonáin | Open, untested, and load-bearing in a new place. The default review frequency for all 61 systems is derived from that band and from nothing else — ADR-0054
AS-28 | The 61 systems and the 121 pairs remain the population to MS-09 | Amara Sissoko | Held and consumed. Continues as AS-39, AS-46, AS-52, AS-57
AS-29 | The 63 procedures read are the whole of the procedure estate bearing on the 38 obligations | Terrence Abbatiello | Open, and load-bearing a fifth time — AS-35
AS-30 | The 44 validation packages read are the whole of what Helix holds | Colm Ó Braonáin | Open, untested, untouched
AS-31 | The nine SOPs, the policy and the framework are issued under document control and not varied outside change control | Terrence Abbatiello | Open, holding, and unexercised. None of the nine has been applied to anything
AS-32 | The validation execution resource is available at the scale 61 validation plans require | Colm Ó Braonáin | Open, and not yet drawn on. No plan has been written
AS-33 | An obligation landing in a procedure that requires the act has a remaining gap of evidence or practice and not of the sentence | Priyanka Venkataraman | Open, unchanged
AS-34 | The configuration and behaviour observed between 2027-01-04 and 2027-01-20 is the configuration at the Phase 05 vantage | Joachim Reuter | Open, consumed, and now carrying OBS-4's position at seventy days' distance — AS-55
AS-35 | The 63 procedures Phase 04 read are the whole of the procedure estate bearing on the eleven paragraphs | Terrence Abbatiello | Open, untested, and load-bearing again. The claim that no Helix procedure requires the laboratory reviewer to open an audit trail rests on this assumption and on the two procedure reads at EV-807
AS-36 | The enumeration of human readable forms and of continuous-session behaviour is the whole of what each product can produce and do | Priyanka Venkataraman | Open, untested, untouched
AS-37 | A determination against 21 CFR 11.10(c) and against (e)'s retention clause can be made in the absence of a stated retention period | Priyanka Venkataraman | Open, unedited, and not tested here. IS-43 carries its consequence and no cell has moved
AS-38 | The 23 reason-for-change fields are the whole of that population | Joachim Reuter | Open, untouched
AS-39 | The 61 systems remain the population to MS-10 | Amara Sissoko | Held and consumed. Continues as AS-46, AS-52, AS-57
AS-40 | Those who supplied the configuration statements described the position as it is rather than as procedure says it should be | Joachim Reuter | Open, and one of the three assumptions IS-58 rests on — AS-22, AS-40, AS-49
AS-41 | The audit trail configuration read on 2027-02-10 on each chromatography instance is the configuration at the Phase 06 vantage | Joachim Reuter | Open, consumed, and now load-bearing on a disposition. The statement that part of OBS-2's remediation cannot be completed on this product version rests on this assumption and on AS-43
AS-42 | The enumeration of acts capable of changing a reportable result is the whole of what can change one | Priyanka Venkataraman | Open, untested, untouched
AS-43 | The vendor's statement that two classes cannot be enabled describes the product version | Joachim Reuter | Open, untested, and this is the phase in which it carries the most weight it has ever carried. ../08.05-obs-2.md states that part of what remains owed under OBS-2 cannot be completed on the current product version, and the whole of the ground for that is a vendor statement Helix has not tested
AS-44 | The 142 released results and the 38 reprocessed within them are the whole of the population | Dr Sunita Raghunathan | Open, untested, untouched
AS-45 | The first-integration values obtained from outside the record the reviewer sees are the values the first integration produced | Dr Sunita Raghunathan | Open, untested, untouched
AS-46 | The 61 systems remain the population to MS-11 | Amara Sissoko | Held and consumed. Continues as AS-52 and AS-57
AS-47 | The predicate-rule anchors Phase 02 published for each in-scope record type are the whole of what makes that record a required record | Priyanka Venkataraman | Open, untested, untouched. No provision was added to any record type here
AS-48 | The expiration date of the batch is held for every batch and is retrievable for as long as the period run from it lasts | Bernard Kwiatkowski | Open, untested, untouched
AS-49 | Those who supplied the backup and restore facts for the 61 described the arrangements as they are rather than as procedure says they should be | Amara Sissoko | Open, and now one of the three assumptions IS-58 rests on. The register's cells were taken from enquiries answered by the people who operate the arrangements, and the function that could have tested them has read access on none of the 61 — IS-55
AS-50 | The four restores at EV-719 are the whole of the restore history on the 61 | Amara Sissoko | Open, untested, untouched
AS-51 | The audit trail retention configuration read across the 61 on 2027-03-10 is the configuration at the Phase 07 vantage | Joachim Reuter | Open, consumed, and superseded in form by AS-55, which makes the same assumption about a different register at three weeks' greater distance
AS-52 | The 61 systems and the 34 record types remain the population to MS-12, and no printout instrument is replaced before it | Amara Sissoko | Held and consumed. No trigger fired, and the 61 were the population throughout. Continues as AS-57
AS-53 | Load-bearing on all fourteen assessments, and it is AS-08's Phase 08 form. EV-106 as filed on 2026-03-06 is the whole of what the response committed Helix to, so that reading its twenty-two rows is reading the whole of the commitment set, and no commitment has been varied, added to, withdrawn or superseded since by correspondence, by a meeting, or by anything else | Rebekah Sandquist | The 22 is a count of a document rather than of the company's obligations. A commitment varied outside EV-106 would be assessed nowhere and would be reported as met or unmet against words nobody is now bound by. AS-08 has been carried open and untested since 2026-05-29 and this is the first phase that has rested anything on it
AS-54 | The five owners' own commitment trackers, read on 2027-03-30, describe the position each of those owners holds — rather than a record maintained by nobody and consulted by nobody | Lydia Marchetti-Nwosu | IS-52 becomes a finding about a stale document rather than about two live records that disagree — which is a different finding and a worse one, because it would mean the commitments were not being tracked anywhere at all. The assumption was not tested and could not be tested from the papers: what was read was the tracker, not the use of it
AS-55 | The Phase 05 vantage of 2027-01-29 is the latest established position on the nine systems named at CG-11 and CG-13, and nothing on any of the nine changed between that date and 2027-04-09 | Amara Sissoko | The three hundred and fifty days is a floor rather than a figure, and OBS-4's position would be stated against an estate that has moved under it. Nothing in Phase 08 read a system, opened an account list or looked at a line; every cell behind the OBS-4 position was taken from a register published on 2027-01-29 — which is AS-40's and AS-49's pattern at one further remove, because this phase did not even put the enquiry
AS-56 | The Phase 04 complexity-and-reliability band, read across on 2027-04-05, is the band at this vantage, no ADR-0015 or ADR-0022 trigger has fired against it, and no system has been re-banded since 2026-11-30 | Colm Ó Braonáin | The default column of periodic-review-register.md moves for the affected rows and 11 / 27 / 23 is not the register's starting point — and because the departures are recorded against the default rather than against the adopted frequency, a moved band would leave a row whose reason no longer explains its move. SOP-DI-05 has fired on nothing
AS-57 | The 61 systems remain the population to MS-13 — AS-52's Phase 08 form — so that RV-01 to RV-61 name every system the arrangement must reach and no other | Amara Sissoko | The arrangement is established against a population that has moved, and a system added to the estate after this vantage has no row, no frequency and no first due date. ADR-0015's trigger is the mechanism that is supposed to catch it and it has never fired
AS-58 | The working papers of the four audits, as retained at EV-122 to EV-125, are the whole of what those audits produced, so that a condition recorded as not obtaining is recorded from the whole record and not from part of it | Gideon Halvorsen | A cell in one of the twenty-four might be answerable the other way from a paper nobody retained — and the register would then be wrong in the direction that matters most, because a *No* recorded from an incomplete record is a statement about the record and not about the audit. The assumption is stated rather than buried, because the whole force of AC-01 to AC-06 is that they are read off documents

## Dependencies
ID | Dependency | Owner | Raised | Status | Related
DP-01 | The record-level Part 11 determination, for control selection | Priyanka Venkataraman | Consumed, carried open. It is the artefact AC-06 turns on
DP-02 | The data integrity risk assessment, for the validation framework's rigour | Priyanka Venkataraman | Consumed, carried open for the 47 pairs — IS-27
DP-03 | Technical cooperation from IT and Automation | Priyanka Venkataraman | Open, and not drawn on in this phase, which read documents
DP-04 | Vendor technical documentation on audit trail generation, retention and export | Joachim Reuter | Open, and load-bearing through AS-43
DP-05 | Validation execution resource contracted and available | Colm Ó Braonáin | Open, and still not drawn on — IS-34
DP-06 | Vashti Okonjo & Partners' availability for the audit window opening 2027-03-29 | Gideon Halvorsen | Open. No result is stated anywhere in this phase and no outcome is anticipated
DP-07 | Quality unit review and approval capacity for the two record review procedure revisions | Terrence Abbatiello | Open, and now named against two unmet commitments. RC-05 and RC-19 are the response's own commitments to make those two revisions, both are Not met, and both are past the date the response gave
DP-08 | The statement of what the January 2011 Annex 11 route requires of O12 | Rebekah Sandquist | Open, and sharpened. It cannot be answered for any system until DP-44 exists, because Helix cannot say which systems the route reaches
DP-09 | The determination as the assessment population | Priyanka Venkataraman | CLOSED on its first limb; the second recorded as unmet — AS-26
DP-10 | Technical detail on how the seven newly in-scope record types are created, retained and exported | Joachim Reuter | Open, unchanged
DP-11 | Quality unit capacity to draft the procedure requiring the determination to be maintained | Terrence Abbatiello | Open, unchanged
DP-12 | Administrative configuration detail for the three vendor-hosted systems | Joachim Reuter | Open, and named in two moved rows — RV-40, RV-56
DP-13 | Confirmation and acceptance of ownership for the seventeen systems the walk found | Amara Sissoko | Open, unchanged
DP-14 | A retention period for each of the 34 Part 11 record types | Priyanka Venkataraman | Open, narrowed to the fourteen — DP-38
DP-15 | How Phase 03's two axes relate to complexity and reliability | Colm Ó Braonáin | CLOSED 2026-10-27, unchanged
DP-16 | Audit trail behaviour statements for the systems on which contemporaneity or attribution could not be determined | Joachim Reuter | Open, discharged for two systems and only two
DP-17 | A statement, per record type, of which instance Helix relies on as the original | Priyanka Venkataraman | Open, and still the single largest closure route in the programme. Not discharged
DP-18 | A retention period for each of the 34 Part 11 record types | Priyanka Venkataraman | Open, narrowed with DP-14 — DP-38
DP-19 | Quality unit capacity to write the procedure requiring the assessment to exist and be acted on | Terrence Abbatiello | Consumed in Phase 04, carried open as DP-22
DP-20 | Account administration records sufficient to say which named individual held the credential in use | Amara Sissoko | Open, unchanged, and it is OBS-4's dependency. It is what attribution on the nine systems at CG-11 and CG-13 would require and it has not moved since 2026-09
DP-21 | Validation execution capacity sized against 61 system validation plans | Colm Ó Braonáin | Open. No plan has been written
DP-22 | Quality unit capacity to take the nine SOPs from approved to applied | Terrence Abbatiello | Open, unchanged
DP-23 | The evidence named on each obligation record, for all 38 obligations | Priyanka Venkataraman | Open. Not one obligation is discharged
DP-24 | A change control route firing three triggers from one change record | Terrence Abbatiello | Open, and now carrying a seventh object — DP-47
DP-25 | Interface and failure-history statements per system | Amara Sissoko | Open, unchanged
DP-26 | A statement, per system, of what its validation package covers against each of the eleven paragraphs | Colm Ó Braonáin | Open, unchanged
DP-27 | Quality unit capacity to decide which of the 218 unrequired controls Helix intends to require of itself | Terrence Abbatiello | Open, and still larger than the rest together. No sentence has been written
DP-28 | Vendor route to include the meaning of the signature in every human readable form on the twelve | Priyanka Venkataraman | Open, unchanged
DP-29 | Vendor product route to retain a previous value in the record the reviewer sees, on the six at CG-15 | Joachim Reuter | Open, unchanged — and it is the second proposition of OBS-6, which the estate still carries
DP-30 | Vendor or configuration route to set the subsequent-signing prompt to the password on the seven | Amara Sissoko | Open, unchanged
DP-31 | Systems documentation for the systems that have none | Bernard Kwiatkowski | Open, unchanged
DP-32 | A re-determination route firing from one change record on a change to a system's configuration | Terrence Abbatiello | Open, and now carrying a fourth object. A change to a system's complexity-and-reliability band would move a review frequency, and nothing would fire — AS-56
DP-33 | A vendor product route to record two auditable event classes at all, and what a compensating control would have to do until there is one | Joachim Reuter | Open, nothing agreed — and it is now the reason a disposition cannot say what everybody wants it to say. AE-08 and AE-16 cannot be enabled by any setting available to Helix, and part of OBS-2's remediation therefore cannot be completed on the current product version
DP-34 | A vendor product route to retain the first integration's value in the record the reviewer sees | Dr Sunita Raghunathan | Open
DP-35 | A configuration decision, and a sentence in a procedure requiring it, for the classes enabled on neither instance and for those on which the two differ | Terrence Abbatiello | Open, and now competing with DP-43, DP-45 and DP-47 as well
DP-36 | A comparison instrument that fires on a change to either chromatography instance | Priyanka Venkataraman | Open — SOP-DI-05 has still not fired on any change
DP-37 | Retention, backup and archive facts for SYS-036, SYS-060 and SYS-061, and a statement of which instance is relied on as the original | Amara Sissoko | Open on its second limb only, unchanged — it is DP-17's
DP-38 | A determination, by a named individual and recorded as a decision, of a retention period for each of the fourteen record types no predicate rule supplies one for | Dr Marguerite Oyelaran | Open, and nothing is decided. No period is set, proposed or bounded by anything in Phase 08
DP-39 | A retrieval of RT-12 and RT-13 from SYS-060 initiated at Cary, performed, timed and recorded | Amara Sissoko | Open. Nothing has been performed
DP-40 | A restore performed as a test rather than as incident recovery, with the restored content compared with what went in | Amara Sissoko | Open. Nothing has been performed
DP-41 | A determination, per record type, of whether 21 CFR 211.68(b)'s carve-out reaches the data | Colm Ó Braonáin | Open, and owed since Phase 06. Made on 0 of the 61
DP-42 | A stated retention location, a named accountable individual and a medium statement — or a reproduction — for each of the four paper record types | Dr Sunita Raghunathan | Open. Nothing has been supplied
DP-43 | A statement, from each of the five owners the response named, of what their own tracking should now record for the five commitments this programme discharged — and a reconciliation of the two records that edits neither retrospectively. Five statements, not one correction | Closure of IS-52 | Dr Sunita Raghunathan, Amara Sissoko and Joachim Reuter, as the owners of RC-03, RC-04, RC-10, RC-11 and RC-18 | Lydia Marchetti-Nwosu | Open, and nothing is reconciled. It does not close by the trackers being edited to agree, which would destroy the evidence that they disagreed — ADR-0056
DP-44 | A product-to-system mapping — which of the 61 systems hold records for which of the 41 marketed products, and which of those products travel the EU-facing route Dr Anselm Ferrão acts on | Closure of IS-54, and any statement about which systems an Annex 11 obligation reaches | The quality unit, manufacturing operations, and the EU-facing route | Rebekah Sandquist | Open, and it does not exist in any form. It is the Helix-side owner of O12's dependency and it is the successor in substance to DP-08, which asked for a statement of what the Annex 11 route requires and has been open since 2026-05-29
DP-45 | A named individual reviewer for each periodic review, who is not the owner of the system being reviewed — because the owner is the person whose arrangements the review examines | The first review being performed against any row, and any movement on IS-57 | The quality unit and the validation function | Colm Ó Braonáin | Open. No reviewer is named on any of the sixty-one rows, and the register says so in its own §6. It competes with DP-07, DP-11, DP-22, DP-27, DP-35 and DP-38 for the same quality unit capacity
DP-46 | Read access for the audit function, requested and then granted, recorded system by system in the working papers | AC-05 becoming capable of being met, and closure of IS-55 | The account administration function and each of the five system owners | Amara Sissoko | Open. Requested on 0 of the 61 and granted on 0. It does not close by a policy statement that access would be granted on request, which is not a grant, and it does not close by access being granted on one system
DP-47 | A route by which a change to a published control position is recorded in the programme's registers as a change — the previous position, the act, the date and the authority — rather than the register simply carrying the new state | Closure of IS-53, and the ability of any register in this repository to evidence a remediation | The quality unit and the change control function | Terrence Abbatiello | Open. It is DP-24's and DP-32's subject matter turned on the programme's own artefacts, and the irony is recorded rather than smoothed: 21 CFR 11.10(e) is the paragraph about record changes not obscuring previously recorded information

## Programme risks
ID | Programme risk | Owner | Raised | Status | Related
PR-01 | Committed scope exceeds the envelope because remediation reveals work the estimate did not carry | Lydia Marchetti-Nwosu | Open, and live. No re-costing has been performed and none is stated, including for DP-43 to DP-47
PR-02 | The 9.2 FTE-equivalents are funded but not released | Dr Marguerite Oyelaran | Open
PR-03 | The Phase 02 determination overruns | Priyanka Venkataraman | Did not materialise. Retained for the pattern
PR-04 | The assurance tail compresses and pushes MS-12 into close-out | Lydia Marchetti-Nwosu | Open, and it did not materialise. MS-12 is met at this vantage, twenty-one days from MS-11 as planned, and MS-13 has twenty-one days
PR-05 | Determinations require technical cooperation the Data Integrity Lead cannot compel | Priyanka Venkataraman | Open, and inverted here. This phase compelled nothing because it asked nothing of a system; what it could not compel was a grant of read access to somebody else — DP-46
PR-06 | Advisory scope drifts into work the third-party auditor must later audit | Gideon Halvorsen | Open — ADR-0004, AS-09
PR-07 | A vendor is treated as supplying compliance rather than features that support it | Colm Ó Braonáin | Open, and directly engaged. A vendor statement that two event classes cannot be enabled is a statement about a product — AS-43 — and it discharges no obligation
PR-08 | Enforcement discretion is read inside Helix as permission to defer validation | Terrence Abbatiello | Open — PR-38
PR-09 | A cadence or control is adopted because a guidance suggests it, and reported internally as a requirement | Rebekah Sandquist | Open, and at its most live. EU GMP Annex 11 clauses 9 and 11 are *shoulds* in a guideline that is not FDA's, they are labelled EU-derived at every citation, and FDA's December 2018 drug CGMP data integrity guidance is cited as guidance and never as a requirement
PR-10 | Key-person concentration on the Data Integrity Lead and the CSV Lead | Dr Marguerite Oyelaran | Open. None agreed at the vantage, and the cell still says so — across eight phases
PR-11 | The seven newly in-scope record types are read as a criticism of the laboratory | Dr Sunita Raghunathan | Open, and live
PR-12 | The determination is cited as though it were an integrity statement | Priyanka Venkataraman | Open, and inverted again. A review frequency is not a statement that the system is any good
PR-13 | The determination drifts, because no procedure requires it to be maintained | Terrence Abbatiello | Open, and now the shape of PR-62. No procedure requires the periodic review arrangement to exist or be maintained — IS-25
PR-14 | Phase 03's assessment population is larger than the plan assumed | Lydia Marchetti-Nwosu | Open
PR-15 | The phrase "a Part 11 system" re-enters use | Priyanka Venkataraman | Open, and engaged. periodic-review-register.md covers 61 systems because they hold Part 11 records, not because they are Part 11 systems
PR-16 | An instrument behind one of the four surviving printout record types is replaced | Dr Sunita Raghunathan | Open, unchanged
PR-17 | The seventeen systems with no validation lifecycle absorb effort sized against systems with documentation | Colm Ó Braonáin | Open, unchanged
PR-18 | The first assessment of the three vendor-hosted systems stalls on vendor-held documentation | Joachim Reuter | Open, and live. All three are now on an annual review interval and none has been reviewed
PR-19 | The 47 unscorable pairs are read as low risk because they carry no rating | Priyanka Venkataraman | Open, and mirrored. PR-59 is the same shape: an absence read as a permission
PR-20 | A rating is cited as a compliance position | Terrence Abbatiello | Open, and now six ways — a rigour band, a control position, a signature test result, a configuration read, a retention group and a review frequency
PR-21 | The five attributes are averaged, or a single number per pair is produced | Priyanka Venkataraman | Open, unchanged
PR-22 | The published scale is elaborated under pressure to discriminate more finely | Terrence Abbatiello | Open, and engaged in a new form. A fourth review frequency, and a two-way departure from the band, were both available and both were refused — ADR-0054
PR-23 | The assessment becomes an annual exercise nobody acts on | Lydia Marchetti-Nwosu | Open, and it is now IS-57's and IS-07's shared subject matter. Sixty-one review commitments whose first due dates begin a month after the programme ends
PR-24 | Phase 04 sets rigour from the 74 scored pairs alone | Colm Ó Braonáin | Open, did not materialise. Retained
PR-25 | The "original or a true copy" finding is read inside the laboratory as a criticism | Dr Sunita Raghunathan | Open, unchanged
PR-26 | A Not determinable determination is treated as closing when somebody writes a document | Gideon Halvorsen | Open, and mirrored twice. An arrangement written down is not a review performed — IS-57 — and a completion criterion written now is not a commitment Helix filed — PR-59
PR-27 | The coverage finding at IS-22 is reported as a control position | Colm Ó Braonáin | Open, did not materialise here
PR-28 | The 25 systems with no established data integrity position acquire one by drift | Priyanka Venkataraman | Open, and directly engaged. Twenty-five systems now carry a review frequency and not one of them has acquired a data integrity position
PR-29 | The two graduations are merged, averaged or reduced to one number | Joachim Reuter | Open, and engaged. The default frequency is derived from column four alone — complexity and reliability — and column five is not consulted anywhere in periodic-review-register.md, which is why five of the twenty moves cite Phase 04's own §4 rather than a band
PR-30 | The twelve at IS-24 are folded back into a single count of procedural gaps | Terrence Abbatiello | Open
PR-31 | A later re-read of the procedure estate is scoped to look only where something is expected | Terrence Abbatiello | Open, and load-bearing again — AS-35
PR-32 | The nine SOPs are approved and never applied | Terrence Abbatiello | Open, unchanged. None of the nine has been applied to anything
PR-33 | A requirement is read as a description of the world | Gideon Halvorsen | Open, and inverted a fifth time. Phase 08's form is a frequency adopted read as a review performed — PR-62, IS-57
PR-34 | The 61 validation plans are sized against the 44 with a package | Colm Ó Braonáin | Open. No plan has been written
PR-35 | The 302 and the 218 are added and reported as 520 | Priyanka Venkataraman | Open, and mirrored — PR-52
PR-36 | The 671 are reduced to 61 system-level verdicts | Joachim Reuter | Open, and a fifth register now invites it. A system's review row is a frequency and a date and is never a verdict
PR-37 | The 21 CFR 11.50 finding is read as a 21 CFR 11.10 control position | Priyanka Venkataraman | Open, unchanged
PR-38 | The 89 are reported as mitigated, and discretion is read inside Helix as permission | Terrence Abbatiello | Open, and live. 21 CFR 11.10(d) is not inside the discretion set at all, and OBS-4's position is stated without reference to discretion
PR-39 | A reason-for-change field is reported as compliance with 21 CFR 11.10(e) | Joachim Reuter | Open, unchanged
PR-40 | 21 CFR 11.200 is described as a multi-factor authentication requirement | Amara Sissoko | Open, unchanged
PR-41 | The Not met cut by system owner is read inside a function as a criticism | Dr Sunita Raghunathan | Open, and live — PR-60 is the same pressure applied to five named commitment owners
PR-42 | The control position register is treated as a compliance certificate | Colm Ó Braonáin | Open, and now with three more candidates. A commitment register, a periodic review register and an audit condition register can each be cited that way. There is no Part 11 certification and no FDA-approved or FDA-validated software
PR-43 | The three classes recorded on neither instance are read as an excuse, and OBS-2 is reported as reduced | Terrence Abbatiello | Open, and at its most live. ../08.05-obs-2.md states that the condition is confirmed and the remediation incomplete *before* it states that part of it cannot be completed on this product version, and the order is deliberate: a product limitation is a fact about a product, not a discharge of an obligation
PR-44 | A depth finding is generalised to the estate | Colm Ó Braonáin | Open, and live — PR-61
PR-45 | The nine reintegrations are characterised, in either direction | Gideon Halvorsen | Open, unchanged. No reintegration is characterised here
PR-46 | A reason-for-change field is reported as compliance with 21 CFR 11.10(e) | Joachim Reuter | Open, unchanged
PR-47 | The two divergences are read as a criticism of one laboratory | Dr Sunita Raghunathan | Open, unchanged. RV-23 and RV-24 carry the same frequency and the same review content
PR-48 | Two configuration counts are added, averaged or reported as a single estate figure | Priyanka Venkataraman | Open, unchanged
PR-49 | The manual transcription is reported as a finding about Cary's practice | Amara Sissoko | Open, unchanged
PR-50 | The twenty record types whose period the regulation sets are reported inside Helix as *retention resolved* | Terrence Abbatiello | Open, and mirrored. PR-62 is the same shape: an arrangement reported as the thing it arranges for
PR-51 | A period is set for a Group C record type by drift rather than by a recorded decision | Amara Sissoko | Open, and mirrored again. PR-59 is the same shape applied to a completion criterion
PR-52 | Group A's pair count and Phase 03's attribute figure are read as one population because their numerals coincide | Priyanka Venkataraman | Open, and the discipline is applied again. The 22 commitments and the 22 systems reviewed annually are unrelated populations, they are joined by no document in this phase, and ../08.09-the-review-established.md and ../08.03-the-commitments.md each carry the caution beside its own figure
PR-53 | The fifty-four backup files are reported as a control, or the four incident recoveries as restore tests | Amara Sissoko | Open, unchanged
PR-54 | IS-43 is read as a criticism of the Phase 05 determinations | Terrence Abbatiello | Open, and live in a second place. IS-53 is a finding about what the Phase 05 registers were built to do and not a finding that any cell in them is wrong, and it says so
PR-55 | Phase 02's printout route is re-opened, or IS-49 is read as evidence that it was wrongly applied | Dr Sunita Raghunathan | Open, unchanged. Nothing in this phase reaches the four
PR-56 | Phase 07 is read as having stated a retention policy, a schedule or an archive design | Dr Marguerite Oyelaran | Open, unchanged. No period is set, proposed or bounded anywhere in Phase 08
PR-57 | A disposition is read as a closure — inside Helix, in a summary, in a slide, or by a reader outside the company — because three positions are harder to carry than one word | Terrence Abbatiello | ADR-0051 is standing framing and is stated in the first section of every document that touches an observation. No observation is described as closed anywhere in this phase, no register carries a status column in which the word could be entered against one, and the word appears about an issue, an action, an audit finding or a closed system and never about OBS-2, OBS-4 or OBS-6; and ../08.01-what-a-disposition-is.md is a numbered chapter whose whole business is the distinction. The three positions are deliberately not parallel — confirmed and incomplete, confirmed and not corrected, corrected and unevidenced by the programme's registers — so that no single word fits all three | GOV-36, 2027-03-24 | ADR-0051, ADR-0057, PR-42, PR-33
PR-58 | A document in this phase is treated as a communication to FDA, filed, forwarded, quoted in correspondence, or offered as evidence of the company's position to the agency | Rebekah Sandquist | Every document in this phase is an internal document and says so. ADR-0057 records that Phase 08 makes no representation to FDA; the classification line is on every file; and the response of 2026-03-06 remains the only thing Helix has said to the agency about any of this. The commitment register reads EV-106 and does not amend, supplement or supersede it | GOV-36, 2027-03-24 | ADR-0051, ADR-0057, IS-51, PR-09
PR-59 | The three commitments with no completion criterion acquire one by drift — somebody writes a test now, applies it, and reports the commitment against it as though the response had contained it | Rebekah Sandquist | ADR-0052 is standing framing: a commitment with no completion criterion is recorded as having none rather than judged. commitment-register.md §3 states the position in the register itself, names all three, and prints the position column as *No completion criterion* rather than leaving the cell blank, because a blank invites completion. IS-51 closes only if a named individual states, as a new act with its own record, what would satisfy each | GOV-37, 2027-03-31 | IS-51, ADR-0052, PR-26, PR-51
PR-60 | IS-52 is read as an allegation against the five named owners, or as a finding that somebody failed to do something they were asked to do | Lydia Marchetti-Nwosu | The entry says in terms that it is not, and so does ../08.04-who-actually-did-it.md, which states the refusal before it states the finding. Nobody failed to act: the work was done, and it was done by the programme. The register carries two columns rather than one — Discharged by, and the owner's own tracking position — so that neither can stand for the other; and ADR-0056 refuses the tidier alternative of editing the owners' trackers to agree | GOV-37, 2027-03-31 | IS-52, ADR-0056, DP-43, PR-41
PR-61 | OBS-6's corrected position is generalised — the estate is reported as having corrected the class, when what is corrected is one proposition on one system and the other proposition is a class the estate still carries | Joachim Reuter | ADR-0006's refusal to split the observation is carried and stated: the observation is disposed of whole. ../08.07-obs-6-and-the-register-that-cannot-show-it.md states in the same section that SYS-001 is the only one of the sixty-one that is *Met and required* on all eleven paragraphs, and that CG-15 records six systems on which a change to a stored value replaces the previous value in the record the reviewer sees. IS-53 is published as an open issue rather than as a caveat, and DP-29 carries the class | GOV-38, 2027-04-06 | IS-53, ADR-0006, CG-15, DP-29, PR-44
PR-62 | The arrangement is reported inside Helix as a periodic review, or the EU-derived limb is reported as binding on the US-facing route, or 21 CFR 211.180(e) is cited as its basis | Dr Marguerite Oyelaran | ADR-0053 is standing framing. periodic-review-register.md §0 states that no review has been performed before it states anything else, §3 prints reviews performed: 0 of 61 as a row of its own, and every citation of Annex 11 in this phase carries the words EU-derived in the same sentence. 21 CFR 211.180(e) is named in this phase only to say that it is a product review and is not the basis for anything | GOV-39, 2027-04-08 | IS-54, IS-57, ADR-0053, PR-09, PR-20
PR-63 | IS-01's closure is read as having chosen among the four candidate explanations, or a document in this repository is cited in support of one, or a later phase treats the question as reopenable | Gideon Halvorsen | ADR-0055 is standing framing and the closing note at §1.9 says it three ways: none chosen, none weighted, none named — not in this phase and not ever — and the refusal is permanent and is not handed to Phase 09. audit-condition-register.md §0 states that the register draws no inference and may not be cited in support of any candidate; 01.09 §5's own sentence that nothing in that section is a cause is quoted rather than paraphrased; and IS-58 is expressly distinguished from IS-01 so that the successor entry cannot become the vehicle | GOV-40, 2027-04-08 | IS-01, IS-58, ADR-0012, ADR-0055, PR-33