## Artefact decay
ID | The artefact | What it is | What makes it go out of date | How fast | Holder after 2027-04-30 | First action owed
DK-01 | The systems inventory and the record-type determination — ../../02-the-system-inventory-and-part-11-applicability/logs/systems-register.md and logs/record-type-register.md | The corrected estate of SYS-001 to SYS-222, the fifty-eight record types, and the record-level determination of which are Part 11 records | A system entering or leaving the estate; a record type coming into existence or ceasing to be maintained electronically; a product added to or withdrawn from a market; a change of the medium a record is kept in. ADR-0015 names six trigger events with an annual floor and SOP-DI-05 has fired on none of them | Continuously, and unobserved. The estate changed nine times during the programme by removal alone and the walk of June 2026 found seventeen systems nobody had entered | Priyanka Venkataraman — Data Integrity Lead | The determination read against the estate as it then is, with the entries that have no determination counted — which is what OBJ-01's measure asks and what ADR-0015's annual floor was set to force
DK-02 | The attribute determination register — ../../03-data-integrity-risk-assessment-and-the-alcoa-attributes/logs/attribute-determination-register.md | The one hundred and twenty-one record-type-and-system pairs assessed against FDA's five attributes, with the pairs that could not be determined recorded as not determinable rather than scored low | A new pair — a record type coming onto a system it was not on before; a change to how a record is created, transferred or retained; and the arrival of evidence that makes a *Not determinable* determinable | Slowly on the population, quickly on the individual pair. A single interface change moves one pair overnight and nothing reports it | Priyanka Venkataraman — Data Integrity Lead | The forty-seven pairs recorded as not determinable read again against whatever evidence now exists — IS-16. Nothing has made any of them determinable and no attribute has been re-scored anywhere
DK-03 | The validation framework and the obligation register — ../../04-the-validation-framework-and-policy-architecture/logs/system-rigour-register.md and logs/obligation-register.md | The rigour band per system, the thirty-eight obligations with their evidence, and the nine SOPs the framework specified | A version upgrade or a configuration change that moves a system's complexity-and-reliability band; a new system entering the estate with no band at all; a procedure revision that changes where an obligation lands | At the pace of the vendors' release cycles, which nothing in this repository tracks and which no Helix record reports | Colm Ó Braonáin — Computerised System Validation Lead | The seventeen systems with no package at all given one, and the evidence the framework names produced against the thirty-eight — owed in full and produced against none of them, IS-22, IS-23, IS-34
DK-04 | The control position register — ../../05-access-audit-trails-and-electronic-signatures/logs/control-position-register.md | Six hundred and seventy-one positions: eleven paragraphs of 21 CFR 11.10 against each of the sixty-one systems, taken at the Phase 05 vantage of 2027-01-29 | Any change to a system's configuration, its account set, its audit trail settings or its signature behaviour — and, because the register records a state and not a transition, a change that restores a position is as invisible as one that loses it | Fastest of the six estate-shape artefacts, and it is already ninety-one days behind. The register is a photograph and the estate is not | Joachim Reuter — Head of Automation and Manufacturing IT | The positions re-taken, and a route by which a change to a published position is recorded as a change rather than as a new state — DP-47, IS-53. ../09.11-the-position-is-ninety-one-days-old.md states the age and re-takes nothing
DK-05 | The control gap register — ../../05-access-audit-trails-and-electronic-signatures/logs/control-gap-register.md | CG-01 to CG-34: what is absent, on which systems, against which paragraph, with what would close each | The same triggers as DK-04, plus one of its own: a decision by the quality unit that Helix does or does not intend to require of itself a control that nothing requires — the two hundred and eighteen at IS-29 | As fast as DK-04, and it decays in a second direction nobody watches: a gap closed by a configuration change leaves the register reading as though it were open | The quality unit — a function, and no named individual has accepted it | A statement of which of the two hundred and eighteen unrequired controls Helix intends to require of itself. DP-27 has been open since Phase 05, is larger than the rest of the quality unit's queue together, and no sentence has been written
DK-06 | The auditable event register — ../../06-the-chromatography-data-system/logs/auditable-event-register.md | AE-01 to AE-34: the acts capable of changing a reportable result on the two chromatography instances, and whether each is recorded, on which instance, and whether it could be | A vendor version upgrade — and this is the row where an upgrade could change the finding rather than merely age it, because AE-08 and AE-16 cannot be enabled by any setting available to Helix on the version Helix runs. Also a configuration change on either instance, and a divergence between the two | On the vendor's release schedule, which Helix does not set and does not track. Between releases it is stable; at a release it is wholly unreliable | Dr Sunita Raghunathan — Head of Quality Control | The two instances compared against each other and against the register — they differ in two published registers and have been compared in neither, IS-37 — and AS-43, the untested vendor statement the whole AE-08 and AE-16 position rests on, put to a test
DK-07 | The retention derivation register — ../../07-the-data-lifecycle-backup-archive-and-the-paper-question/logs/retention-derivation-register.md | The thirty-four in-scope record types partitioned into the three groups, with the predicate-rule period where one exists and *Not set by any predicate rule* where none does | An amendment to a predicate rule that sets or changes a period; a record type joining or leaving the in-scope thirty-four; and — for the fourteen in Group C — a determination by a named individual, which would move a row from an absence to a period | Very slowly on the regulation and instantly on the determination. CAL-12's quarterly horizon scan is the instrument for the first and it reaches none of the fourteen | Terrence Abbatiello — Head of Quality Assurance | A period determined, by a named individual and recorded as a decision, for each of the fourteen record types no predicate rule supplies one for — DP-38, IS-44. No period is set, proposed or bounded by anything in this phase
DK-08 | The backup and restore register — ../../07-the-data-lifecycle-backup-archive-and-the-paper-question/logs/backup-and-restore-register.md | The backup arrangement per system across the sixty-one, the four restores that have been performed, and the fact that on none of the four was what came back compared with what went in | A change to a backup job, a schedule, a retention window, a storage platform or a data centre; a system migrating; and a personnel change in the teams that operate the jobs — the register's cells were taken from enquiries answered by the people who operate the arrangements, AS-49 | Monthly at least, because a backup arrangement is operational and operations change without a document | The IT organisation — a function, and no named individual has accepted it | A restore performed as a test rather than as incident recovery, with the restored content compared with what went in — DP-40, IS-46. Nothing has been performed
DK-09 | The commitment register — ../../08-periodic-review-internal-audit-and-the-483-response/logs/commitment-register.md | RC-01 to RC-22: the commitments the written response of 2026-03-06 made, fourteen assessed and eight not, read against their own words | An act that satisfies a commitment; a date passing; and a variation of a commitment outside EV-106 — which AS-08 and AS-53 assume has not happened and which nothing tests | Slowly, and it has already demonstrated the failure mode. It went thirteen months without being opened, and an artefact nobody reads does not go out of date so much as stop being consulted | Rebekah Sandquist — Head of Regulatory Affairs | The five owners' own tracking reconciled with the register, each as a statement of its own — DP-43; and a status read from the register at an occurrence of CAL-04, which is what OBJ-08's measure asks and what did not happen
DK-10 | The periodic review register — ../../08-periodic-review-internal-audit-and-the-483-response/logs/periodic-review-register.md | RV-01 to RV-61: a frequency, a reason where the frequency departs from the Phase 04 band, and a first review due date, for every system | A system entering or leaving the estate — a new system has no row at all; a change to a system's complexity-and-reliability band, which would move its default; and a review being performed, which no row records | At the estate's own rate, and its first due dates fall after the programme ends. The earliest is 2027-05-31, thirty-one days after this vantage | Colm Ó Braonáin — Computerised System Validation Lead | A named individual reviewer for each review who is not the owner of the system being reviewed — DP-45 — and a review performed against a row. Reviews performed: none. IS-57
DK-11 | The audit condition register — ../../08-periodic-review-internal-audit-and-the-483-response/logs/audit-condition-register.md | AC-01 to AC-06: the six conditions restated from 01.09 §5, tested against each of the four internal audits, and tested against Helix at the Phase 08 vantage | The twenty-four historical cells do not move and cannot. What decays is the second column: whether each condition is capable of being met now, which changes when the artefact it turns on changes and when read access changes | Slowly on five of the six. AC-05 turns on a grant and could change on any day somebody acts — and the grant decided at DEC-911 is recorded as decided and dated, never as performed | Gideon Halvorsen — Head of Internal Audit | Read access requested and granted, recorded system by system in the working papers — DP-46, IS-55. ../09.09-independence-cannot-be-retrofitted.md owns the arrangement, and an arrangement is not a grant performed
DK-12 | The evidence index — evidence-index.md, and EV-101 to EV-940 across the nine phases | The index of every artefact the programme produced. It is the artefact every other artefact in this register cites: each of DK-01 to DK-11 names EV identifiers, and this is where those identifiers resolve | An artefact moving, being superseded, being renamed, or ceasing to be retrievable — and the index would not know. It records where a thing was at the vantage it was indexed, and nothing fires when the thing moves | Immediately and silently. It is the fastest-decaying artefact of the twelve because it is the only one whose subject matter is other artefacts, and it is the only one with nobody to notice | None | Nothing is owed by anybody, because there is nobody the register can record as owing it. The first action a holder would take is to resolve each EV identifier against the artefact it names and record what no longer resolves. No individual and no function has accepted this artefact, and the register publishes that rather than filling the cell — ADR-0062, IS-61