## Decisions
ID | Date | Decision | Taken by | ADR | Governance
DEC-901 | 2027-04-12 | Phase 09's boundary fixed. The phase scores the eight charter objectives, states what inspection readiness is, records what the programme built and what makes each artefact go out of date, hands the open entries over, answers IS-58 and stops. Its refusals are fixed at the same moment and before any work is done: no observation closed, no representation to FDA, no compliance conclusion, no legal conclusion, no readiness claim, no forecast, no CAPA, no deviation, no remediation plan, no cost, no re-determination, no retention period, no result of any review or assessment, no access described as performed, and no candidate explanation of IS-01 | Lydia Marchetti-Nwosu | — | — | EV-901
DEC-902 | 2027-04-13 | The source pack adopted and the standing framing renewed. The eighteen standing framing positions carried unchanged from 01.00 §10, 02.00 §10 and GOV-02 §7; the two interval conventions restated — an interval between two events is the difference; a duration of an activity is inclusive of both endpoints; and the EV block for this phase fixed at EV-901 to EV-940, with EV-839 to EV-900 permanently unused and never issued | Lydia Marchetti-Nwosu | — | — | EV-902, EV-903
DEC-903 | 2027-04-14 | ADR-0058 — an objective is scored from the artefact its measure names, and from nothing else. Not from effort, not from progress, not from intent, not from an opinion and not from a consultant's assessment of maturity. Two states and no third, and the alternative of a partial score argued and refused | Lydia Marchetti-Nwosu | ADR-0058 | GOV-41 | EV-904
DEC-904 | 2027-04-14 | The objective score record form authorised — and authorised before any objective was scored. The form requires the objective, the owner, the measure verbatim, the artefact scored, the position, the artefact-or-estate classification and what would change the score. The sequence is deliberate: a form designed after the results are known is a form designed around them | Dr Marguerite Oyelaran | — | GOV-41 | EV-905, EV-906
DEC-905 | 2027-04-19 | ADR-0059 — inspection readiness is the ability to answer, and this repository never reports it as a compliance position. The two are different objects: readiness is whether a question can be answered; compliance is whether the answer is the right one. Helix can now answer the three questions it could not answer in February 2026, and many of the answers are *not met* | Terrence Abbatiello | ADR-0059 | — | EV-907, EV-908
DEC-906 | 2027-04-20 | The eight objectives scored, each against its own measure and each from the artefact that measure names. OS-01 to OS-08. Met on three, Not met on five. Four of the eight are satisfied by the programme's own artefacts and four require the estate to change, and the classification is recorded in the register rather than argued in it | Lydia Marchetti-Nwosu | — | — | EV-909, EV-910, EV-911, EV-912
DEC-907 | 2027-04-21 | The objective score register accepted — objective-score-register.md, OS-01 to OS-08. No score was softened and none was inflated, and the register produces no aggregate, no index and no percentage. IS-60 raised — the pattern in the score, and it is the finding of the whole programme | Dr Marguerite Oyelaran | — | GOV-42 | EV-913
DEC-908 | 2027-04-21 | ADR-0060 — an open entry is handed to a named individual or it is recorded as having no destination. A function is not a destination: it cannot accept, it cannot be asked a question, and it cannot be held to a date. The alternative of recording a function as the destination and treating receipt as acceptance argued and refused | Gideon Halvorsen | ADR-0060 | GOV-42 | EV-916
DEC-909 | 2027-04-22 | The envelope reported against the ten budget lines at 01.06 §5, committed and actual, monthly for fourteen months — which is what OBJ-07's measure asks and is the whole of what OS-07 is scored from. Two lines over, three under, five on plan, and the programme closes under its envelope. IS-59 raised — two of the three under-lines are under because work named in them was not done. No re-costing performed and none stated | Lydia Marchetti-Nwosu | — | — | EV-914, EV-915
DEC-910 | 2027-04-23 | The predicate-rule attribute is the record type's and is not the systems register's, and the systems register will not carry one. The unit of determination is the record type — ADR-0001 — the record-type register carries the predicate rule on all fifty-eight rows, and each row names the systems that hold the record type. IS-03 CLOSED, on the finding that what it asked for was never that register's to carry. No register is edited and no determination moves | Amara Sissoko | — | — | EV-921, EV-922, EV-923
DEC-911 | 2027-04-26 | ADR-0061 — an access grant is recorded as decided and dated, never as performed, until an artefact evidences the performance. And the read-access grant for the audit function is decided and dated here. The decision is a decision. No access is described as performed anywhere in this phase; AC-05 is not described as capable of being met; and IS-55 and DP-46 stay open and say so | Amara Sissoko | ADR-0061 | — | EV-924, EV-925
DEC-912 | 2027-04-27 | The handover register accepted — handover-register.md, HO-01 to HO-49, one row per open issue. Thirty-three to a named individual who has accepted, twelve to a function with no named individual, four with no destination at all. IS-62 raised. No entry is closed by being handed over, and no row carries a date | Dr Marguerite Oyelaran | — | GOV-43 | EV-917, EV-918, EV-919, EV-920
DEC-913 | 2027-04-28 | ADR-0062 — every artefact carries what makes it go out of date and who holds it, and an artefact with no holder is published as having none. The alternative of assigning an unheld artefact to a department so that the column reads complete argued and refused — ADR-0008, and a holder column filled for the sake of completion stops anybody looking | Priyanka Venkataraman | ADR-0062 | — | EV-926
DEC-914 | 2027-04-28 | The decay register approved — decay-register.md, DK-01 to DK-12. Nine artefacts pass to a named individual, two to a function with no named individual, and one to nobody — and the one is the evidence index, the artefact the other eleven cite. IS-61 raised. No holder is invented for DK-12 and none is proposed | Priyanka Venkataraman | — | — | EV-927, EV-928, EV-929
DEC-915 | 2027-04-29 | ADR-0063 — the programme closes with its open entries open. Nothing is closed at close-out for the sake of closing it. The alternative of a close-out sweep — closing entries whose subject matter has been superseded, absorbed or made academic — argued and refused, because an entry closed without evidence is an entry that has been tidied rather than resolved, and *believed complete* is not a closure condition | Dr Marguerite Oyelaran | ADR-0063 | GOV-45 | EV-934
DEC-916 | 2027-04-29 | The independence arrangement approved, and IS-58 CLOSED. Helix cannot make this programme independent retrospectively, and the answer is no. What is approved is the arrangement under which the next assessment is independent: read access granted to the audit function, recorded as decided and dated at DEC-911, and the periodic review owned by a function that owns no system. IS-63 raised — no independent assessment has been scheduled, and an arrangement is not one. No result of any assessment is reported and none is anticipated | Gideon Halvorsen | — | GOV-44 | EV-930, EV-931, EV-932, EV-933
DEC-917 | 2027-04-29 | ADR-0064 — close-out is not a communication to FDA, and no artefact in this phase is written to be read by one. The alternative of writing the close-out pack so that it would read well to an inspector argued and refused: a document written for a second reader acquires a second criterion, and the second criterion wins arguments the first should have won. The written response of 2026-03-06 remains the only thing Helix has said to the agency about any of this | Rebekah Sandquist | ADR-0064 | GOV-45 | EV-935
DEC-918 | 2027-04-30 | Phase 09 published, and the programme closed. IS-52 CLOSED on five statements, one from each owner across the five commitments, each a new act with its own record and no tracker edited to agree with any register — DP-43 discharged. IS-64, IS-65 and IS-66 raised. The RAID reconciliation recorded: 252 entries, 230 open, 22 closed; issues 66, of which 17 closed and 49 open. MS-13 met | Lydia Marchetti-Nwosu | — | — | EV-936, EV-937, EV-938, EV-939, EV-940