## Handover
ID | The issue | Destination | What the destination holds | Accepted | Note
HO-01 | IS-07 — seven of the twelve calendar entries outlive the programme and none has a named owner after close-out | The quality unit — *a function, no named individual* | Seven recurring commitments the programme created and cannot carry past this vantage, including CAL-07, whose sixty-one first due dates all fall after it | No | This is the entry that has been asking for a named individual since 2026-05-27 and is still asking. The obvious answer — that the quality unit holds the seven under 21 CFR 211.22 — is probably right, is still not written down, and this register is not going to write it down on anybody's behalf. IS-07 is the only entry in the repository carried as deliberately unresolved
HO-02 | IS-08 — seven record types were Part 11 records throughout the period Helix treated them as outside Part 11 | Dr Sunita Raghunathan — Head of Quality Control | The historical position of seven record types, and the fact that the determination that put them in scope was made in Phase 02 and not before it | Yes | Accepted 2027-04-23. Nothing in this row is offered as evidence about any internal audit, and it is not read together with anything in ../../01-program-foundation-and-regulatory-scoping/01.09-the-four-audits-that-found-nothing.md
HO-03 | IS-09 — 21 CFR 11.10 has never been assessed for the three vendor-hosted systems on its second limb | Joachim Reuter — Head of Automation and Manufacturing IT | The three vendor-hosted systems, their administrative configuration, and DP-12 | Yes | Accepted 2027-04-23. All three carry an annual review interval at RV-40, RV-41 and RV-56, and none has been reviewed
HO-04 | IS-12 — where the records of the nine removed register entries now are is not established | None | — | No | Nobody at Helix owns a system that is not in the estate. The nine removed entries carry no SYS identifier, are therefore on no row of any register this programme built, and fall outside RV-01 to RV-61 entirely. There is no system owner because there is no system, and no line function's remit reaches records held by an arrangement Helix no longer runs. This is not an entry nobody has been assigned; it is an entry there is nobody to assign — ../09.08-the-four-that-go-nowhere.md
HO-05 | IS-13 — seventeen systems entered the inventory that had never entered a validation lifecycle | Colm Ó Braonáin — Computerised System Validation Lead | The seventeen systems the walk of June 2026 found, and the fact that the effort they will absorb is not sized against systems that have documentation | Yes | Accepted 2027-04-22. PR-17 carries the sizing and DP-13 the ownership confirmations, open since 2026-06-12
HO-06 | IS-15 — *"Original or a true copy"* fails or cannot be determined on a large majority of the one hundred and twenty-one pairs | Priyanka Venkataraman — Data Integrity Lead | The Phase 03 attribute determination as published, and the fact that no determination in it has moved and none may be moved without a re-assessment nobody has commissioned | Yes | Accepted 2027-04-22. DK-02 is the artefact and this is the entry standing on it
HO-07 | IS-16 — forty-seven pairs cannot be scored, and the programme refused to score them low | Priyanka Venkataraman — Data Integrity Lead | Forty-seven not-determinable determinations, and the refusal that produced them — a negative that nobody can test is not a determination; it is a silence | Yes | Accepted 2027-04-22. No ND has become determinable in any phase since Phase 03, and PR-19 carries the reading of an absence as a permission
HO-08 | IS-17 — the twenty-four pairs from the seven newly in-scope record types have no assessment history | Dr Sunita Raghunathan — Head of Quality Control | Twenty-four pairs whose first assessment is their only assessment | Yes | Accepted 2027-04-23. They now sit on systems with a review frequency, which is a future and not a history
HO-09 | IS-18 — the transfer between systems is assessed nowhere, for thirty-one of the thirty-four in-scope record types | Joachim Reuter — Head of Automation and Manufacturing IT | The interfaces, and OB-36 and SOP-DI-04, both undischarged and unapplied | Yes | Accepted 2027-04-23
HO-10 | IS-20 — a rating is not a control position, and nothing says whether any control works | Gideon Halvorsen — Head of Internal Audit | The distinction between an assessment of where data is weak and a test of whether anything holds — the shape IS-57 repeats | Yes | Accepted 2027-04-26. It is the entry that anticipated the arrangement-is-not-the-act pattern, and the pattern has now recurred five times in the repository
HO-11 | IS-22 — not one of the forty-four validation packages evidences 21 CFR 11.10(a)'s fourth clause | Colm Ó Braonáin — Computerised System Validation Lead | Forty-four packages, none withdrawn, none invalidated, none superseded, and none evidencing *"…the ability to discern invalid or altered records"* | Yes | Accepted 2027-04-22. It is one of the two grounds OS-02 is scored Not met on — objective-score-register.md
HO-12 | IS-23 — seventeen of the sixty-one systems have no validation package at all | Colm Ó Braonáin — Computerised System Validation Lead | Seventeen systems with no package, 44 + 17 = 61, and the validation status report every one of their review rows names as an item the review would examine and would not find | Yes | Accepted 2027-04-22. It is the other ground OS-02 is scored Not met on
HO-13 | IS-24 — twelve obligations land in a procedure that exists and does not require the act | The quality unit — *a function, no named individual* | Twelve obligations, two unmet commitments in RC-05 and RC-19, and the quality unit's own review and approval capacity at DP-07 | No | What this entry needs is capacity, and capacity is held by a function rather than granted by a person. DP-07, DP-11, DP-22, DP-27, DP-35 and DP-38 draw on the same capacity and not one of them has moved
HO-14 | IS-25 — five obligations land in no procedure at all | The quality unit — *a function, no named individual* | Five obligations with no procedural home, and the fact that no procedure requires the periodic review arrangement to exist or be maintained either | No | The same capacity as HO-13 and the same answer. PR-13 carries the drift
HO-15 | IS-26 — the two graduations disagree on seventeen of the thirty-six | Joachim Reuter — Head of Automation and Manufacturing IT | A disagreement published as a disagreement, open by design, and the five systems on which the record is graver than the system | Yes | Accepted 2027-04-23. No band has moved and none may move; PR-29 refuses the merge
HO-16 | IS-27 — twenty-five systems have no established data integrity position | Priyanka Venkataraman — Data Integrity Lead | Twenty-five systems that now carry a review frequency and have not thereby acquired a position | Yes | Accepted 2027-04-22. PR-28 carries the acquisition of one by drift
HO-17 | IS-29 — two hundred and eighteen of the five hundred and twenty controls that are present are required by nothing | The quality unit — *a function, no named individual* | The decision of which unrequired controls Helix intends to require of itself, which is a decision about Helix's own written procedures and is nobody else's to take | No | DP-27 is larger than the rest of the quality unit's queue together and has been open since Phase 05. No sentence has been written. A control withdrawn without a deviation is withdrawn because nothing required it — and deciding that is not a programme act
HO-18 | IS-30 — the meaning of the signature is absent from the exported or printed form on twelve of the nineteen systems that execute signatures | Priyanka Venkataraman — Data Integrity Lead | Twelve systems, 21 CFR 11.50's three elements in the human readable form, and DP-28 | Yes | Accepted 2027-04-22. Nothing since Phase 05 has tested a human readable form, and PR-37 keeps the 21 CFR 11.50 finding apart from the 21 CFR 11.10 positions
HO-19 | IS-31 — seven of the nineteen re-prompt for the user identification code rather than the password on subsequent signings | Amara Sissoko — Chief Information Officer | Seven systems and DP-30, and the standing position that 21 CFR 11.200 is not a multi-factor authentication requirement and 21 CFR 11.300(b) sets no password interval | Yes | Accepted 2027-04-26. No session test has been performed since Phase 05
HO-20 | IS-32 — twenty-three systems hold a reason-for-change field Part 11 does not require, and fourteen of them fail the no-obscuring requirement it does | Joachim Reuter — Head of Automation and Manufacturing IT | Twenty-three fields, fourteen failures, and PR-39's refusal — a reason-for-change field is never reported as compliance with anything | Yes | Accepted 2027-04-23
HO-21 | IS-33 — eighty-nine of the one hundred and fifty-one failures sit in the four paragraphs enforcement discretion reaches in full, and nothing about that changes the position | Terrence Abbatiello — Head of Quality Assurance | Eighty-nine positions, and the standing framing that enforcement discretion is FDA's stated intention, is not an exemption, is not a safe harbour and confers no rights | Yes | Accepted 2027-04-26. Open by design. 21 CFR 11.10(d) is not inside the discretion set at all, and PR-38 carries the reading of discretion inside Helix as permission
HO-22 | IS-34 — a control position is not validation evidence, and the evidence Phase 04 requires is owed in full | The validation function — *a function, no named individual* | Thirty-eight obligations, not one of them discharged, and validation execution resource that has never been drawn on because no plan has been written | No | The named individual exists and the capacity does not. DP-05 and DP-21 ask for execution resource contracted and sized against sixty-one validation plans; AS-32 assumes it is available at that scale and has never been tested, because nothing has drawn on it. A lead cannot accept an entry whose discharge requires a resource nobody has released to him
HO-23 | IS-36 — three of the eleven result-changing event classes are recorded on neither chromatography instance, and two of the three cannot be enabled | Joachim Reuter — Head of Automation and Manufacturing IT | AE-08 and AE-16, which no setting available to Helix could switch on; AE-15, which is a configuration decision; and DP-33 | Yes | Accepted 2027-04-23. The whole of the ground for the product-version limb is AS-43, a vendor statement Helix has not tested
HO-24 | IS-37 — the two chromatography instances differ in two published registers and were compared in neither | Amara Sissoko — Chief Information Officer | Two instances, two divergences, and DP-36 — a comparison instrument that fires on a change to either | Yes | Accepted 2027-04-26. A common review frequency is not a comparison, and PR-47 refuses the reading of the divergence as a criticism of one laboratory
HO-25 | IS-38 — nine reportable results carry a value that differs from the first integration, and on none of the nine does the record show both | Dr Sunita Raghunathan — Head of Quality Control | Nine results, and DP-34 — a product route to retain the first integration's value in the record the reviewer sees | Yes | Accepted 2027-04-23. No reintegration is characterised, in either direction, by anything in this phase — PR-45, ADR-0043
HO-26 | IS-39 — on SYS-024 the reportable result reaches the LIMS by manual transcription | Joachim Reuter — Head of Automation and Manufacturing IT | One transfer with no verification arrangement stated | Yes | Accepted 2027-04-23. PR-49 refuses the reading of it as a finding about Cary's practice
HO-27 | IS-40 — RT-12 and RT-13 are also held on SYS-036, SYS-060 and SYS-061, two owned by a different named individual, and none of the three was assessed at depth | Amara Sissoko — Chief Information Officer | Three systems, a shortened review interval on each, none reviewed, and DP-17 undischarged | Yes | Accepted 2027-04-26. DP-17 is still the single largest closure route in the programme
HO-28 | IS-41 — two of sixty-one systems were assessed at a depth unavailable for the other fifty-nine | Colm Ó Braonáin — Computerised System Validation Lead | The depth asymmetry, open by design, and its counterpart caution: Phase 08 read documents and Phase 09 scores artefacts | Yes | Accepted 2027-04-22. PR-44 refuses the generalisation of a depth finding to the estate
HO-29 | IS-43 — on thirteen systems 21 CFR 11.10(c) was determined Met against a records retention period that does not exist | The quality unit — *a function, no named individual* | Thirteen determinations that cannot move until a period exists, and the period is DP-38's and the quality unit's | No | The entry cannot be held by anybody who cannot set a period, and the individual who can — the owner of DP-38 — has not accepted the entry. PR-54 refuses the reading of it as a criticism of any Phase 05 determination; no cell moves
HO-30 | IS-44 — fourteen of the thirty-four in-scope record types have a retention period set by no predicate rule, and no named individual has determined one | The quality unit — *a function, no named individual* | Fourteen record types with no period, and DP-38 | No | The entry's own words are that no named individual has determined one, and the handover has not produced one either. No period is set, proposed or bounded by anything in this phase, and PR-51 refuses the setting of one by drift
HO-31 | IS-45 — the electronic master production and control record, RT-02, has a retention period set by nothing | The quality unit — *a function, no named individual* | The one record type every batch at Helix is made against, with no period | No | The same absence as HO-30, instanced on the record type that matters most, and the same destination. A shorter review interval on SYS-059 is not a period
HO-32 | IS-46 — a restore has been performed on four of sixty-one systems, all four as incident recovery, and on none was what came back compared with what went in | Amara Sissoko — Chief Information Officer | Four incident recoveries that are not restore tests, and DP-40 | Yes | Accepted 2027-04-26. PR-53 refuses the reporting of the backup files as a control or of the four recoveries as tests
HO-33 | IS-47 — three of the four systems constituting the retention estate are owned by the Chief Information Officer, none by the quality unit, and one entered the inventory by walk | The quality unit — *a function, no named individual* | An ownership position the entry says is wrong-shaped, which only the quality unit could change and which no individual within it has taken | No | It does not close by the systems being reviewed more often, and the four review rows say so. The Chief Information Officer already holds the systems; what is unheld is the quality unit's side of the arrangement
HO-34 | IS-48 — records of Cary activities are held at the Ridgemont data centre and 21 CFR 211.180(c)'s immediate-retrieval saving has been demonstrated, timed and recorded on none of them | Joachim Reuter — Head of Automation and Manufacturing IT | The cross-site retrieval position, and DP-39 | Yes | Accepted 2027-04-23. No retrieval has been performed
HO-35 | IS-49 — the four printout record types have no stated retention location, no named individual accountable, no derived period and no reproduction under 21 CFR 211.180(d) | Dr Sunita Raghunathan — Head of Quality Control | Four record types that are outside the thirty-four, outside the sixty-one and outside every register in this repository | Yes | Accepted 2027-04-23, and it is the only acceptance in this register of an entry about records no register covers. PR-55 refuses the re-opening of Phase 02's printout route; PR-16 carries the replacement of an instrument
HO-36 | IS-51 — three of the fourteen commitments assessed carry no completion criterion, so none of the three can be judged met or unmet | Rebekah Sandquist — Head of Regulatory Affairs | RC-07, RC-14 and RC-20, each with an owner and a date and none with a test | Yes | Accepted 2027-04-26. It closes only if a named individual states, as a new act with its own record, what would satisfy each — and nothing in this phase writes a completion criterion for any of the three, ADR-0052, PR-59
HO-37 | IS-53 — the correction of OBS-6's condition is evidenced by no register this programme built | The change control function — *a function, no named individual* | The route by which a change to a published control position would be recorded as a change — the previous position, the act, the date and the authority — which is DP-47 and sits in change control, outside every register this programme built | No | The change control record exists and is outside the programme's registers. The programme built no instrument that records change, having spent eight phases establishing that the estate needed exactly such an instrument — and it declines itself the defence it spent seven phases refusing to accept about a record. Nothing here states that the correction did not happen, and no cell moves
HO-38 | IS-54 — no product-to-system mapping exists, so Helix cannot say which systems the EU-facing Annex 11 route reaches | The quality unit — *a function, no named individual* | DP-44 — which of the sixty-one systems hold records for which of the forty-one marketed products, and which of those products travel the route Dr Anselm Ferrão acts on | No | The mapping is owed by three places at once and by no one person: the quality unit, manufacturing operations, and the EU-facing route. Dr Anselm Ferrão is not a Helix role and cannot be a destination in this register; he acts for the holder of the EU manufacturing and import authorisation and not for Helix. The Helix-side owner of O12 is Rebekah Sandquist, and DP-08 has been open since 2026-05-29 and cannot be answered until DP-44 exists
HO-39 | IS-55 — read access for the audit function has been requested on none of the sixty-one systems and granted on none | Amara Sissoko — Chief Information Officer | The account administration function, the five system owners, and DP-46 | Yes | Accepted 2027-04-26 at DEC-911. The grant decided at DEC-911 is recorded as decided and dated and never as performed — ADR-0061 — and IS-55 therefore stays open: it closes when access is granted and recorded, system by system, and not when a decision to grant it is minuted. ../09.09-independence-cannot-be-retrofitted.md owns the arrangement
HO-40 | IS-56 — OBS-4's condition was still present at the Phase 05 vantage on the system FDA observed and on eight further systems | Amara Sissoko — Chief Information Officer | The nine systems at CG-11 and CG-13, RC-12 Not met, and DP-20 | Yes | Accepted 2027-04-26. No observation is closed by this row and none is described as closed — the position at ../../08-periodic-review-internal-audit-and-the-483-response/08.06-obs-4.md stands exactly as published, and nothing in Phase 09 read a system
HO-41 | IS-57 — the periodic review is established and has not been run | Colm Ó Braonáin — Computerised System Validation Lead | RV-01 to RV-61, reviews performed: none, and DP-45 — a named reviewer who is not the owner of the system reviewed | Yes | Accepted 2027-04-22. The earliest first due date is 2027-05-31 and every one of the sixty-one falls after this vantage. Nothing in this phase reports the result of a periodic review, because none has been performed
HO-42 | IS-59 — the programme closes under its envelope, and two of the three lines that came in under did so because work named in them was not done | Dr Marguerite Oyelaran — Vice President, Quality | The finding that an underspend on the validation execution line and the account remediation line is a scope position reported in the currency column | Yes | Accepted 2027-04-29. The sponsor is the destination because the envelope was the sponsor's to approve and the headroom is the sponsor's to release; the programme manager who reported the variance holds no budget after this vantage. No re-costing is performed or stated
HO-43 | IS-60 — three of the four objectives about the programme's own artefacts are met and not one of the four requiring the estate to change is met | None | — | No | The destination would have to be somebody with the authority and the funding to change the estate. The charter may be varied only by a further minuted decision of the sponsor and the charter ends at this vantage; no post below the Board carries authority to fund estate change on this scale, and the Board audit committee's non-executive membership is deliberately not named in this repository. This is not an entry nobody has been assigned; it is an entry nobody at Helix has the authority or the funding to take — ../09.08-the-four-that-go-nowhere.md
HO-44 | IS-61 — of the twelve artefacts the programme built, two pass to a function with no named individual and one passes to nobody | Priyanka Venkataraman — Data Integrity Lead | decay-register.md, and the fact that the Data Integrity Lead post continues when the programme does not | Yes | Accepted 2027-04-28 at DEC-914. Accepting the entry is not accepting the artefacts it is about: DK-05 and DK-08 still carry a function, and DK-12, the evidence index, still carries None
HO-45 | IS-62 — four of the forty-nine open issues have no destination | None | — | No | It is a statement about this register, and there is no destination for a fact about the absence of destinations. Handing it to a named individual would say that somebody now holds the four, which is exactly what is untrue. The entry is one of the four it counts, and that is arithmetic rather than a device — ../09.08-the-four-that-go-nowhere.md
HO-46 | IS-63 — no independent assessment has been scheduled; the arrangement exists and the assessment does not | Gideon Halvorsen — Head of Internal Audit | The arrangement approved at DEC-916 and GOV-44, and the fact that an arrangement is not an assessment | Yes | Accepted 2027-04-29. He reports to the Board's audit committee, not to Quality and not to IT, which is why he can hold it — and holding it is not scheduling it. No result of any assessment is reported anywhere in this phase, and none is anticipated
HO-47 | IS-64 — the estate-wide control position handed over is ninety-one days old at close-out and nothing has re-taken it | Joachim Reuter — Head of Automation and Manufacturing IT | DK-04 — six hundred and seventy-one positions taken on 2027-01-29 and not re-taken since | Yes | Accepted 2027-04-29. Phase 09 re-determines nothing, and ../09.11-the-position-is-ninety-one-days-old.md states the age rather than refreshing it. AS-63 is the assumption underneath and it has never been tested
HO-48 | IS-65 — every artefact whose holder is the programme rather than a line function has twenty-one days of ownership left | The quality unit — *a function, no named individual* | The artefacts the programme holds in its own right, and the twenty-one days between MS-12 and MS-13 | No | The quality unit is the only body in this repository whose existence is required by a regulation and therefore outlasts the programme — 21 CFR 211.22. No individual within it has accepted the artefacts, and HO-01 is the same absence stated about the calendar. ../09.10-what-happens-when-the-programme-stops.md owns the argument
HO-49 | IS-66 — the question the programme leaves open, and it leaves it to nobody in particular | None | — | No | It is addressed to nobody by construction, and giving it a destination would be the one act of tidying this register refuses. The entry states what Helix now knows, what knowing it has changed, what the programme was funded to do and what nobody has been funded to do. There is no post at Helix whose remit is the last of those four things — ../09.08-the-four-that-go-nowhere.md, ../09.13-close-out.md