## Objective scores
ID | Objective | Owner | The measure | The artefact scored | Position | Artefact or Estate | What would change the score
OS-01 | *"A controlled inventory of computerised systems exists, and every entry carries a determination of which of its records, if any, are Part 11 records"* | Priyanka Venkataraman | *"The inventory exists under document control; every entry carries a determination record with a named determiner and a date; entries with no determination are countable and counted"* | ../../02-the-system-inventory-and-part-11-applicability/logs/systems-register.md and logs/record-type-register.md beside it, under document control with the six review triggers and the annual floor at ADR-0015 | Met | Artefact | Nothing at this vantage. The score is a statement about the inventory as published and not about whether it is still true: ADR-0015's triggers have never fired and SOP-DI-05 has fired on nothing — AS-19, DK-01
OS-02 | *"Every GxP-critical platform holds an approved validation package covering its intended use"* | Colm Ó Braonáin | *"One approved package per platform, each carrying an intended-use statement and traceable to the obligation at 21 CFR 211.68(b)"* | ../../04-the-validation-framework-and-policy-architecture/logs/system-rigour-register.md and ../../04-the-validation-framework-and-policy-architecture/04.07-the-packages-helix-already-holds.md | Not met | Estate | Forty-four packages are held and seventeen systems hold none. 44 + 17 = 61 — 04.07 §6, IS-23. And not one of the forty-four evidences 21 CFR 11.10(a)'s fourth clause, *"…the ability to discern invalid or altered records"* — IS-22. IS-34 records that the evidence the Phase 04 framework requires is owed in full and that a control position is not validation evidence. The score changes when a package exists per platform in the state the measure describes
OS-03 | *"Every record type determined to be a Part 11 record has a named individual owner"* | Terrence Abbatiello | *"The record register contains zero entries owned by a team, a function or a job title without a name"* | ../../02-the-system-inventory-and-part-11-applicability/logs/record-type-register.md, Owner column | Met | Artefact | Nothing at this vantage. The register contains no entry owned by a team, a function or a job title without a name, and it has contained none at any of the eight vantages since 2026-07-31 — ADR-0008. The measure counts names in a column; it says nothing about whether the named individual has done anything
OS-04 | *"Audit trail functionality is configured, enabled and demonstrated on every system holding records determined to be Part 11 records, with the audit trail retained at least as long as the record"* | Joachim Reuter | *"A per-system configuration record, plus a dated retrieval demonstration witnessed by a named person not in the operating team"* | ../../05-access-audit-trails-and-electronic-signatures/logs/control-gap-register.md; ../../06-the-chromatography-data-system/logs/auditable-event-register.md; ../../07-the-data-lifecycle-backup-archive-and-the-paper-question/logs/retention-derivation-register.md | Not met | Estate | CG-14 to CG-18 are five gaps against 21 CFR 11.10(e) across the estate, CG-16's eight systems having no audit trail function at all and none configurable. AE-08 and AE-16 cannot be enabled by any setting available to Helix on the product version Helix runs — IS-36, AS-43. And the retention limb has no second term at all on sixteen systems, 21 CFR 11.10(e)'s third sentence setting a relation whose second term is the period of the subject records — 07.09, IS-43. The demonstration limb is separately unsatisfied: no dated retrieval demonstration witnessed by a named person outside the operating team exists for any system
OS-05 | *"Shared and generic accounts are removed from systems holding GxP records — or, where a technical constraint prevents removal, the constraint is documented and a named individual owns the compensating control"* | Amara Sissoko | *"The account register shows every shared account either closed with a date, or open with a documented constraint and a named compensating-control owner. No third state"* | ../../05-access-audit-trails-and-electronic-signatures/logs/control-gap-register.md — CG-11 and CG-13 | Not met | Estate | Nine systems carry a shared account: CG-11's seven and CG-13's two. 7 + 2 = 9 — and the packaging line system FDA observed is among the seven. Not one of the nine is closed with a date, and no compensating control on any of the nine has a named individual owner. The measure allows two states and the estate is in the third the measure says does not exist — IS-56, RC-12, DP-20. The score changes when each of the nine sits in one of the measure's two states
OS-06 | *"The record review procedures state whether and how the associated audit trail forms part of the record reviewed"* | Terrence Abbatiello | *"Approved revisions of the production and control record review procedure (21 CFR 211.192) and the laboratory record review procedure (21 CFR 211.194(a)(8)), each stating the position expressly rather than by omission"* | The two procedures the measure names, as read at EV-807 and reported at ../../08-periodic-review-internal-audit-and-the-483-response/logs/commitment-register.md — RC-05 and RC-19 | Not met | Estate | Neither of the two procedures the measure names has been revised. RC-05 and RC-19 are the commitments the response of 2026-03-06 made to revise them; both are Not met and both are past the date the response gave. Phase 04 specified nine SOPs and none of the nine has been applied to anything — IS-24, IS-32, DP-07, DP-22. Specification is not the issue: the measure asks for an approved revision of two named procedures and there is none
OS-07 | *"The programme is delivered within its approved envelope"* | Lydia Marchetti-Nwosu | *"Committed and actual spend reported monthly against the ten budget lines at CAL-01; variance stated as a figure, not as a narrative"* | The monthly budget report against the ten lines at 01.06 §5, reported at CAL-01 for fourteen months — EV-914, and ../09.04-the-envelope.md | Met | Artefact | Nothing at this vantage. Committed and actual were reported monthly against all ten lines for fourteen months, the variance is stated as a figure on every line, and the programme closes under its envelope. The measure asks whether the reporting happened and whether the envelope held. It does not ask what the money bought — and IS-59 records that two of the three lines that came in under did so because work named in them was not done
OS-08 | *"Every commitment in Helix's written response of 2026-03-06 has a named owner, a due date and an evidence reference, and its status is reported quarterly"* | Rebekah Sandquist | *"The response commitment register shows, per commitment, an owner, a due date, an evidence reference and a status; reported at CAL-04"* | ../../08-periodic-review-internal-audit-and-the-483-response/logs/commitment-register.md — RC-01 to RC-22 | Not met | Artefact | The register exists and the measure still fails, on both limbs. Of the fourteen commitments assessed, three carry no completion criterion and one carries no date — IS-51, and a commitment with no test has no status the register can carry. And the quarterly-reporting limb failed outright: the register was not opened between the day it was filed on 2026-03-06 and 2027-03-30, thirteen months later — so no occurrence of CAL-04 reported a status read from it. The artefact was there the whole time. Nobody read it