## Issues
ID | Issue | Owner | Raised | Status | Related
IS-01 | Four internal audits between 2023-06 and 2025-09 covered all three systems between them, each falling inside the scope of at least two, and none raised a finding on the subject matter of OBS-2, OBS-4 or OBS-6. Why is not established | Gideon Halvorsen | 2026-05-19 | CLOSED 2027-04-07, unchanged. The closing note is at the Phase 08 log's §1.9 and is not reproduced, summarised or characterised here. The refusal recorded there is permanent and was expressly not handed to this phase; Phase 09 does not inherit the question, is not asked to answer it, and names no candidate explanation by number, by content, by paraphrase or by allusion — ADR-0055, PR-63
IS-02 | No written record exists of which Helix records are Part 11 records | Priyanka Venkataraman | 2026-03-13 | CLOSED 2026-07-28, unchanged. It is the artefact OS-01 and OS-03 are scored from
IS-03 | The register of computerised systems carries no predicate-rule attribute | Amara Sissoko | 2026-04-24 | CLOSED 2027-04-23 — DEC-910. See the closing note at §1.8 below
IS-04 | CAL-06's cadence is undefined where CGMP does not specify a review frequency for the underlying data | Terrence Abbatiello | 2026-05-29 | CLOSED 2027-04-08, unchanged. No stand-alone periodic audit trail review frequency is named by any primary source, none is set here, and none is attributed to any source
IS-05 | Helix cannot state, for any system, how long audit trail data is retained relative to the retention period of the underlying record | Joachim Reuter | 2026-05-01 | CLOSED 2027-03-18, unchanged. The remainder is IS-44's and is open
IS-06 | The laboratory record review procedure does not state whether the audit trail associated with a result forms part of the original record reviewed under 21 CFR 211.194(a)(8) | Dr Sunita Raghunathan | 2026-05-15 | CLOSED 2027-04-08, unchanged. The question is answered and the procedure still does not say it — which is why OS-06 is scored Not met and RC-05 is Not met
IS-07 | Seven of the twelve calendar entries outlive the programme and none has a named owner after close-out | Lydia Marchetti-Nwosu | 2026-05-27 | Open — deliberately unresolved, and at this vantage it is the entry the whole of IS-65 stands on. The programme ends today and the seven do not. CAL-07's sixty-one first due dates all fall after it, the earliest on 2027-05-31. The obvious answer — that the quality unit holds them under 21 CFR 211.22 — is probably right, is still not written down, and this log is still not going to write it down on the programme's behalf. It is the only entry in this repository carried as deliberately unresolved, through nine phases and nine vantages — HO-01, DP-52
IS-08 | Seven record types were Part 11 records throughout the period Helix treated them as outside Part 11 | Dr Sunita Raghunathan | 2026-07-10 | Open, unchanged. Nothing in this entry is offered as evidence about any internal audit, and no document in this phase joins it to anything
IS-09 | 21 CFR 11.10 has never been assessed for the three vendor-hosted systems | Joachim Reuter | 2026-07-17 | Open on its second limb, unchanged. All three are on an annual review interval and none has been reviewed
IS-10 | The applicability determination exists and nothing requires it to be maintained | Terrence Abbatiello | 2026-11-20 | CLOSED 2026-11-20, unchanged. SOP-DI-05 has still not fired on any change, across nine phases — AS-19, DK-01
IS-11 | Nobody has assessed whether the data in the 34 in-scope record types is any good | Priyanka Venkataraman | 2026-07-31 | CLOSED 2026-09-24, unchanged
IS-12 | Where the records of the nine removed systems now are is not established | Amara Sissoko | 2026-06-12 | Open, unchanged. The nine removed entries carry no SYS identifier and are on no row of any register this programme built. HO-04 records that there is no destination for it: nobody at Helix owns a system that is not in the estate — ../09.08-the-four-that-go-nowhere.md
IS-13 | Seventeen systems entered the inventory that had never entered a validation lifecycle | Colm Ó Braonáin | 2026-06-12 | Open, unchanged. DP-13 has not moved since 2026-06-12
IS-14 | No retention period is recorded against any of the 34 Part 11 record types | Priyanka Venkataraman | 2026-07-24 | CLOSED 2027-03-09, unchanged. The remainder is IS-44's and is open
IS-15 | *"Original or a true copy"* fails or cannot be determined on a large majority of the 121 pairs | Priyanka Venkataraman | 2026-09-15 | Open, unchanged. No Phase 03 determination has moved and none can here
IS-16 | 47 pairs cannot be scored, and the programme has refused to score them low | Priyanka Venkataraman | 2026-09-25 | Open, unchanged. No ND became determinable in this phase
IS-17 | The 24 pairs from Phase 02's seven newly in-scope record types have no assessment history | Dr Sunita Raghunathan | 2026-09-17 | Open, unchanged
IS-18 | The transfer between systems is assessed nowhere, for 31 of the 34 in-scope record types | Joachim Reuter | 2026-09-22 | Open, unchanged. OB-36 and SOP-DI-04 remain undischarged and unapplied
IS-19 | The scale is a written procedure Helix will be held to under 21 CFR 211.22(d) | Terrence Abbatiello | 2026-09-11 | CLOSED 2026-11-20, unchanged
IS-20 | A rating is not a control position, and nothing says whether any control works | Gideon Halvorsen | 2026-09-29 | Open on its second limb, unchanged — and it is the shape the repository has now repeated five times. An arrangement to review a system is not a review of it; a frequency adopted is not a review performed; a completion criterion written now is not a commitment filed; a grant decided is not access performed; and an arrangement for independence is not an assessment — IS-57, PR-59, IS-55, IS-63
IS-21 | The assessment says where the data is weak; nothing in the quality system says what Helix must do | Priyanka Venkataraman | 2026-09-30 | CLOSED 2026-11-25, unchanged
IS-22 | Not one of the 44 packages evidences 21 CFR 11.10(a)'s fourth clause | Colm Ó Braonáin | 2026-11-06 | Open, unchanged, and now scored. OS-02 is Not met and this entry is one of its two grounds — objective-score-register.md. No package is withdrawn, invalidated or superseded by anything here
IS-23 | 17 of the 61 systems have no validation package at all | Colm Ó Braonáin | 2026-11-06 | Open, unchanged, and now scored. 44 + 17 = 61, and OS-02's other ground. Thirteen of the seventeen carry the validation status report EU GMP Annex 11 clause 11 names — EU-derived — as an item their review would examine and would not find; the other four carry it under the retention-estate item. 13 + 4 = 17
IS-24 | 12 obligations land in a procedure that exists and does not require the act | Terrence Abbatiello | 2026-11-17 | Open, unchanged, and it is OS-06's subject matter at one remove. Neither record review procedure has been revised, RC-05 and RC-19 are both Not met and both past date, and none of the nine SOPs has been applied to anything. Handed to the quality unit at HO-13, not accepted
IS-25 | 5 obligations land in no procedure at all | Priyanka Venkataraman | 2026-11-17 | Open, unchanged. No procedure requires the periodic review arrangement to exist or be maintained, and none requires the decay register, the handover register or the objective score register to exist either — PR-13
IS-26 | The two graduations disagree on 17 of the 36 | Joachim Reuter | 2026-11-02 | Open, and open by design, unchanged. No band has moved and none can move here
IS-27 | 25 systems have no established data integrity position | Priyanka Venkataraman | 2026-10-29 | Open, unchanged. A review frequency is not a data integrity position, and neither is a decay row
IS-28 | The framework says what evidence every system must produce and nothing has produced any of it | Colm Ó Braonáin | 2026-11-30 | CLOSED 2027-01-28, unchanged. IS-34 carries the second half and is open
IS-29 | 218 of the 520 controls that are present are required by nothing and can be withdrawn without a deviation | Priyanka Venkataraman | 2027-01-06 | Open, unchanged. DP-27 is unmoved and no sentence has been written. Handed to the quality unit at HO-17, and not accepted. DK-05 records that this decision is one of the two things that would move the control gap register
IS-30 | The meaning of the signature is absent from the exported or printed form on 12 of the 19 systems that execute signatures | Priyanka Venkataraman | 2027-01-13 | Open, unchanged. Nothing in this phase tested a human readable form. 21 CFR 11.50 requires the printed name, the date and time, and the meaning of the signature to appear in any human readable form of the record
IS-31 | 7 of the 19 re-prompt for the user identification code rather than the password | Amara Sissoko | 2027-01-20 | Open, unchanged. No session test was performed. 21 CFR 11.200 is not a multi-factor authentication requirement and 21 CFR 11.300(b) sets no password interval — PR-40
IS-32 | 23 systems hold a reason-for-change field Part 11 does not require, and 14 of them fail the no-obscuring requirement it does | Joachim Reuter | 2027-01-28 | Open, unchanged. Holding a reason-for-change field is still never reported as compliance with anything — ADR-0036, PR-39
IS-33 | 89 of the 151 failures sit in the four paragraphs discretion reaches in full, and nothing about that changes the position | Terrence Abbatiello | 2027-01-27 | Open, and open by design, unchanged. Enforcement discretion is FDA's stated intention about what it will enforce; it is not an exemption, not a safe harbour, and it confers no rights — and 21 CFR 11.10(d) is not inside the discretion set
IS-34 | A control position is not validation evidence, and the evidence Phase 04 requires is owed in full | Colm Ó Braonáin | 2026-12-17 | Open, unchanged, and it is one of the two grounds OS-02 is scored Not met on. Not one of the 38 obligations is discharged. Handed to the validation function at HO-22, and not accepted — the capacity DP-05 and DP-21 ask for has never been released
IS-35 | The position is known for every paragraph on every system, and on 218 of them what is present is required by nothing | Joachim Reuter | 2027-01-29 | CLOSED 2027-02-25, unchanged. The mechanism it named as Phase 08's is established at RV-01 to RV-61 and has not been run — IS-57
IS-36 | Three of the eleven event classes recording an act capable of changing a reportable result are recorded on neither chromatography instance, and two of the three cannot be enabled | Priyanka Venkataraman | 2027-02-12 | Open on both limbs, unchanged, and it is one of the three grounds OS-04 is scored Not met on. AE-08 and AE-16 cannot be enabled by any setting available to Helix on the product version Helix runs, and AS-43 — the untested vendor statement the whole of that rests on — is still untested. DP-33 and DP-35 have not moved
IS-37 | The two chromatography instances differ in two published registers and were compared in neither | Amara Sissoko | 2027-02-25 | Open, unchanged. No comparison has been performed and DP-36 has not moved
IS-38 | Nine reportable results carry a value that differs from the first integration, and on none of the nine does the record show both | Dr Sunita Raghunathan | 2027-02-17 | Open, unchanged, and no reintegration is characterised by anything in this phase — ADR-0043, PR-45
IS-39 | On SYS-024 the reportable result reaches the LIMS by manual transcription | Joachim Reuter | 2027-02-19 | Open, unchanged. No verification arrangement is stated by this phase
IS-40 | RT-12 and RT-13 are also held on SYS-036, SYS-060 and SYS-061, two owned by a different named individual, and none of the three was assessed at depth | Amara Sissoko | 2027-02-24 | Open, unchanged. DP-17 is still the single largest closure route in the programme and is not discharged
IS-41 | Two of sixty-one systems were assessed at a depth unavailable for the other fifty-nine | Colm Ó Braonáin | 2027-02-18 | Open, and open by design, unchanged — and its counterpart caution runs through this phase too. Phase 09 read artefacts. It scored eight objectives from documents, read a budget report and drew three registers; it opened no system, executed no test and examined no record. A score drawn from artefacts is a position about artefacts
IS-42 | The record cannot show what happened, and the data it cannot show it about is retained somewhere | Dr Sunita Raghunathan | 2027-02-26 | CLOSED 2027-03-18, unchanged
IS-43 | On thirteen systems 21 CFR 11.10(c) was determined Met against a records retention period that does not exist | Terrence Abbatiello | 2027-03-18 | Open, unchanged. No cell has moved and none can move here. It closes when a period exists, which is IS-44's and DP-38's, and nothing in Phase 09 supplies one. Handed to the quality unit at HO-29, and not accepted
IS-44 | Fourteen of the thirty-four in-scope record types have a retention period set by no predicate rule, and no named individual has determined one | Priyanka Venkataraman | 2027-03-09 | Open, unchanged. No period is set, proposed or bounded anywhere in this phase. DP-38 is unmoved and is one of ten entries handed to the quality unit at handover-register.md §2, none of which any individual has accepted. DK-07 records the decay
IS-45 | The electronic master production and control record — RT-02 — has a retention period set by nothing | Priyanka Venkataraman | 2027-03-09 | Open, unchanged. A shorter review interval on SYS-059 is not a period, and nothing in this phase reaches it. Handed at HO-31, not accepted
IS-46 | A restore has been performed on four of sixty-one systems, all four as incident recovery, and on none was what came back compared with what went in | Amara Sissoko | 2027-03-12 | Open on both limbs, unchanged. No restore was performed in this phase and no carve-out determination was made — DP-40, DP-41. DK-08 records the decay and its holder is a function
IS-47 | Three of the four systems that constitute the retention estate are owned by the Chief Information Officer, none by the quality unit, and one entered the inventory by walk | Amara Sissoko | 2027-03-10 | Open, unchanged. Handed to the quality unit at HO-33, and not accepted — which is the entry's own subject matter recurring at the handover
IS-48 | Records of Cary activities are held at the Ridgemont data centre and 21 CFR 211.180(c)'s immediate-retrieval saving has been demonstrated, timed and recorded on none of them | Joachim Reuter | 2027-03-11 | Open, unchanged. DP-39 has not moved and no retrieval has been performed
IS-49 | The four printout record types have no stated retention location, no named individual accountable, no derived period and no reproduction under 21 CFR 211.180(d) | Dr Sunita Raghunathan | 2027-03-17 | Open, unchanged. The four are outside the 61, outside the 34 and outside every register in this repository, including decay-register.md, and nothing in this phase reaches them — PR-55
IS-50 | Everything now has a period, an owner or an explicit gap where one of those is missing — and not one of the arrangements has ever been examined by anybody at Helix whose job it was to look | Terrence Abbatiello | 2027-03-19 | CLOSED 2027-04-08, unchanged. Its unasked question — whether the function whose job it is to look can get at the systems — was IS-55's and IS-58's, and IS-58 closes here
IS-51 | Three of the fourteen commitments assessed carry no completion criterion, so none can be judged met or unmet | Rebekah Sandquist | 2027-03-30 | Open, unchanged. No completion criterion has been written for RC-07, RC-14 or RC-20, and none is written here — ADR-0052, PR-59. It is one of the two grounds OS-08 is scored Not met on. Handed at HO-36
IS-52 | Five of the six commitments met were discharged by the programme rather than by the commitment's named owner, and in each the owner's own tracking still shows the commitment open | Lydia Marchetti-Nwosu | 2027-03-31 | CLOSED 2027-04-30 — DEC-918. See the closing note at §1.8 below
IS-53 | The correction of OBS-6's condition is evidenced by no register this programme built | Joachim Reuter | 2027-04-06 | Open, unchanged, and now stated about a second register. DP-47 has not moved. DK-04 records that the control position register is a photograph and that a change restoring a position is as invisible in it as one losing a position — which is this entry's subject matter carried into the decay register rather than resolved. The change control record exists and is outside every register this programme built
IS-54 | No product-to-system mapping exists, so Helix cannot say which systems the EU-facing Annex 11 route reaches | Rebekah Sandquist | 2027-04-01 | Open, unchanged. DP-44 does not exist in any form and DP-08 still cannot be answered. EU GMP Annex 11's periodic evaluation expectation is a *should* in a guideline that is not FDA's, is EU-derived, and binds nothing on the US-facing route. Handed to the quality unit at HO-38, and not accepted
IS-55 | Read access for the audit function has been requested on none of the sixty-one systems and granted on none | Gideon Halvorsen | 2027-04-07 | Open, and this is the phase that decided the grant without performing it. DEC-911 records the grant as decided and dated. It is not recorded as performed, and AC-05 is not described as capable of being met — ADR-0061, PR-68. Requested on 0 of the 61 and granted on 0 remains the position audit-condition-register.md publishes, and DP-46 is open. It is IS-58's first limb and IS-63's ground
IS-56 | OBS-4's condition was still present at the Phase 05 vantage on the system FDA observed, and on eight further systems | Amara Sissoko | 2027-04-02 | Open, unchanged, and now ninety-one days older. Nothing in Phase 09 read a system, opened an account list or looked at a line, and every cell behind the position is Phase 05's as published — AS-55, AS-63. It is the ground OS-05 is scored Not met on. No observation is closed by this entry and none is described as closed
IS-57 | The periodic review is established and has not been run | Colm Ó Braonáin | 2027-04-08 | Open, and open by construction, unchanged. Reviews performed: 0 of 61. The earliest first due date is 2027-05-31, thirty-one days after this vantage, and no reviewer is named on any of the sixty-one rows — DP-45. Nothing in this phase reports the result of a periodic review
IS-58 | Every determination in this repository was made by the people who also own the things determined, and the one function that could have tested them independently has never been given the access to do it. The programme has assessed itself | Gideon Halvorsen | 2027-04-09 | CLOSED 2027-04-29 — DEC-916, minuted at GOV-44. See the closing note at §1.8 below, which is set out in full rather than compressed into this cell
IS-59 | The programme closes under its envelope, and two of the three lines that came in under did so because work named in them was not done. Committed and actual were reported monthly against the ten budget lines for fourteen months, which is what OBJ-07's measure asks and is why OS-07 is Met. Ten lines: two over, three under, five on plan. 2 + 3 + 5 = 10. The validation execution line and the account remediation line are two of the three under-lines, and neither is under because the work cost less than the estimate: they are under because the work named in them was not performed. No validation plan has been written and no plan has drawn on the execution resource — DP-05, DP-21, AS-32; and the shared credential is still in use on nine systems at the latest established position — IS-56. A programme that comes in under its envelope because it did not do the work has not managed its budget; it has reported its scope failure in the currency column. This entry states no amount, no re-costing and no cost of anything not done, and ../09.04-the-envelope.md states the variance as line counts and directions because that is what the measure asks for | Lydia Marchetti-Nwosu | 2027-04-22 | Open. It does not close by the accounts being closed, which is what produced it; it closes if and when the work the two lines named is performed and evidenced. Handed to Dr Marguerite Oyelaran at HO-42 | DEC-909, GOV-43, ../09.04-the-envelope.md, objective-score-register.md OS-07, OS-02, OS-05, AS-60, PR-66, PR-01
IS-60 | Three of the four objectives about the programme's own artefacts are met and not one of the four requiring the estate to change is met. The fourth artefact objective fails because nobody read the register, not because it is missing. OBJ-01, OBJ-03, OBJ-07 and OBJ-08 are satisfied by artefacts the programme produces — an inventory, an ownership column, a budget report, a register — and three of the four are Met. OBJ-02, OBJ-04, OBJ-05 and OBJ-06 are satisfied only if a validation package, an audit trail configuration, an account or an approved procedure changes, and none of the four is Met. 3 + 1 = 4, 0 + 4 = 4, 4 + 4 = 8. This is not an accusation of bad faith and it names no individual. A programme that determines, registers and evidences is doing what it was funded to do; the estate changes when somebody with the authority to change it is funded to change it, and nobody was. OS-08 is the honest complication and it is not smoothed into the pattern: it is an artefact objective, it fails, and it fails because the artefact went thirteen months without being opened | Dr Marguerite Oyelaran | 2027-04-21 | Open, and it has no destination. It does not close by a successor programme being proposed, which nothing in this repository does; the condition it records holds until somebody with the authority and the funding to change the estate is given both. HO-43 records that there is nobody to hand it to | DEC-907, GOV-42, ../09.03-what-the-score-is-shaped-like.md, ../09.08-the-four-that-go-nowhere.md, objective-score-register.md, ADR-0058, DP-51, PR-65, IS-66
IS-61 | Of the twelve artefacts the programme built, two pass to a function with no named individual and one passes to nobody — and the one is the evidence index, which every other artefact cites. DK-01 to DK-12 each carry what makes them go out of date, how fast, and who holds them after 2027-04-30. Nine have a named individual holder, two have a function and no name, and one has neither. 9 + 2 + 1 = 12. The two with a function are the control gap register and the backup and restore register; the one with neither is DK-12, the evidence index, and it is the file in which every EV identifier the other eleven cite resolves. ADR-0062 requires an artefact with no holder to be published as having none rather than assigned to a department to fill the column — ADR-0008, *"It is never converted back to a department name."* This entry does not name a holder for DK-12 and does not propose one | Priyanka Venkataraman | 2027-04-28 | Open. It does not close by the column being filled, which would be the defect ADR-0062 exists to prevent; it closes when a named individual has accepted each of the three. DP-48 is the route for the two, and DP-49 for the one. Handed to Priyanka Venkataraman at HO-44 | DEC-913, DEC-914, ADR-0062, ../09.06-what-goes-out-of-date-and-how-fast.md, decay-register.md, DP-48, DP-49, IS-65, IS-07
IS-62 | Four of the forty-nine open issues have no destination. They were raised by the programme, could not be resolved by it, and cannot be handed to anybody. HO-04 (IS-12), HO-43 (IS-60), HO-45 (IS-62) and HO-49 (IS-66). Of the forty-nine: 33 transfer to a named individual who has accepted, 12 transfer to a function with no named individual and no acceptance, and 4 have no destination at all. 33 + 12 + 4 = 49. A function is not a destination: it cannot accept, it cannot be asked a question, and it cannot be held to a date — ADR-0060. The distinction the four turn on is stated rather than blurred: HO-04 and HO-43 have no destination because nobody at Helix has the remit, the authority or the funding to take them; HO-45 and HO-49 have none because of what they are. This entry is one of the four it counts, and that is arithmetic rather than a device | Gideon Halvorsen | 2027-04-27 | Open, and it has no destination. It does not close by the four being assigned to somebody, which is what it records is not available; it closes if the condition changes for each of the four separately. HO-45 records that there is nobody to hand it to | DEC-912, GOV-43, ADR-0060, ../09.07-the-handover.md, ../09.08-the-four-that-go-nowhere.md, handover-register.md, DP-48, PR-67, IS-12, IS-60, IS-66
IS-63 | No independent assessment has been scheduled. The arrangement exists; the assessment does not, and the arrangement is not one. IS-58 closed on 2027-04-29 on the answer that Helix cannot make this programme independent retrospectively. What Phase 09 established instead is the arrangement under which the next assessment is independent: read access granted to the audit function — recorded as decided and dated at DEC-911 and never as performed — and the periodic review owned by a function that owns no system. Neither limb is an assessment. No date, no scope, no party and no commissioning decision exists for a first independent assessment under the arrangement, and CAL-09 and CAL-10 are the programme's own assurance activities and are not it. Nothing in this phase reports the result of an assessment, and nothing in it anticipates one | Gideon Halvorsen | 2027-04-29 | Open, and open on the day it was raised. It does not close by the arrangement being approved, which is what created it; it closes when an assessment has been scoped, commissioned, performed and reported. DP-50 is the route and it has no date. Handed to Gideon Halvorsen at HO-46 | DEC-916, GOV-44, ADR-0061, ../09.09-independence-cannot-be-retrofitted.md, IS-58, IS-55, IS-57, DP-46, DP-50, PR-68, PR-69, AC-05
IS-64 | The estate-wide control position handed over is ninety-one days old at close-out and nothing has re-taken it. The six hundred and seventy-one control positions were taken at the Phase 05 vantage of 2027-01-29. 2027-01-29 to 2027-04-30 is ninety-one days — the difference between two dates, per the interval convention. Nothing in Phase 06, Phase 07, Phase 08 or Phase 09 has re-taken a single one of them: Phase 06 assessed two systems at depth, Phase 07 derived periods from a register, Phase 08 read documents, and Phase 09 opened no system, executed no test and examined no record. The register records a state and not a transition, so a position that has moved since 2027-01-29 — in either direction — is invisible in it, and IS-53 and DP-47 carry that. Phase 09 re-determines nothing and says plainly that what it hands over is not current | Joachim Reuter | 2027-04-30 | Open. It does not close by the age being stated, which is what this entry does; it closes when the positions are re-taken and the date of the re-taking is recorded. DK-04 carries the decay. Handed to Joachim Reuter at HO-47 | DEC-918, ../09.11-the-position-is-ninety-one-days-old.md, decay-register.md DK-04, AS-55, AS-63, IS-53, DP-47, PR-36, ADR-0049
IS-65 | Every artefact whose holder is the programme rather than a line function has twenty-one days of ownership left. Counted from MS-12 on 2027-04-09, the interval to MS-13 on 2027-04-30 is twenty-one days, and at this vantage it is spent. The Data Integrity Lead post was created by this programme — ADR-0002 — and continues; the programme does not. The registers, the calendar and the budget report are the programme manager's, and the programme manager's role in this programme ends at this vantage. Two of the twelve artefacts pass to a function with no named individual and one passes to nobody — IS-61 — and seven of the twelve calendar entries outlive the programme with no named owner beyond close-out, which is IS-07 and has stood unresolved since 2026-05-27. This entry states no successor arrangement and proposes none | Lydia Marchetti-Nwosu | 2027-04-30 | Open. It does not close by the artefacts being filed somewhere, which is storage and not ownership; it closes when each artefact whose holder is the programme has a named individual holder who is not the programme. DP-52 is the route for the calendar limb. Handed to the quality unit at HO-48, and the quality unit has not accepted it | DEC-918, ../09.10-what-happens-when-the-programme-stops.md, ADR-0002, decay-register.md, IS-07, IS-61, DP-48, DP-52, PR-10, CAL-07
IS-66 | The question the programme leaves open, and it leaves it to nobody in particular. Helix now knows what it did not know in February 2026, and knowing it has changed the estate in almost none of the ways that matter. The programme was funded to find out. Nobody has been funded to fix it. In February 2026 Helix could not say which of its records were Part 11 records, which systems held them, or what its control position was; it can now answer all three, and many of the answers are *not met* — ../09.05-readiness-is-the-ability-to-answer.md, ADR-0059. Nine systems still carry a shared account. Seventeen systems still hold no validation package. Neither record review procedure has been revised. Sixteen systems still have no second term for the retention relation. Two auditable event classes still cannot be enabled. Not one of those is a thing the programme had the authority to change, and the successor authority does not exist: no further programme is chartered, no envelope stands after 2027-04-30, and DP-51 asks for funding from a body this repository does not name. This entry is not a recommendation, not a plan, not a forecast and not a request. It is a statement of the position at the vantage | Dr Marguerite Oyelaran | 2027-04-30 | Open, and it has no destination. It does not close. No act available to anybody at Helix at this vantage would close it, and the register does not invent a closure condition in order to have written one down. HO-49 records that there is nobody to hand it to | DEC-918, ../09.13-close-out.md, ../09.08-the-four-that-go-nowhere.md, IS-60, IS-62, DP-51, handover-register.md HO-49

## Assumptions
ID | Assumption | Owner | Made
AS-01 | The Steering Committee continues monthly to close-out | Lydia Marchetti-Nwosu | Held and consumed. The final sitting is 2027-04-29, minuted at GOV-45, and the committee is dissolved at it. The assumption held for the whole of the programme
AS-02 | The 9.2 FTE-equivalents remain allocated and the named owners are not reassigned | Dr Marguerite Oyelaran | Held and consumed. No named owner was reassigned during the programme, and the allocation ends with it — IS-65
AS-03 | The record-level determination can be completed in Phase 02 from existing documentation | Priyanka Venkataraman | CLOSED at the MS-06 gate, unchanged
AS-04 | Vendors supply the technical documentation needed to assess audit trail behaviour | Joachim Reuter | Open, and exercised again through AS-43
AS-05 | Access to the vendor-hosted quality management system continues to be controlled by Helix | Priyanka Venkataraman | Open. A closed system is defined by who controls access — 21 CFR 11.3(b)(4) — and hosting is not the test
AS-06 | No new GxP-critical platform is introduced before MS-06 | Amara Sissoko | CLOSED, tested and held
AS-07 | The 41 marketed products and the two QC laboratories remain the basis for record-type enumeration | Dr Sunita Raghunathan | Open. The 41 marketed products are the population a product-to-system mapping would be built from, and no such mapping exists — IS-54, DP-44
AS-08 | The commitments in the written response of 2026-03-06 are not varied by Helix | Rebekah Sandquist | Open, untested through nine phases, and now under a score as well as under fourteen assessments — AS-53, OS-08
AS-09 | Thorne Delacroix Consulting's design work is complete before the third-party audit opens | Lydia Marchetti-Nwosu | Open — ADR-0004, PR-06
AS-10 | The January 2011 version of EU GMP Annex 11 remains in force for the programme period | Dr Anselm Ferrão | Open, holding. Every citation of Annex 11 in this phase carries the words EU-derived in the same sentence, and none binds the US-facing route
AS-11 | FDA's August 2003 Scope and Application guidance remains in force and unchanged | Rebekah Sandquist | Open, holding. Enforcement discretion is not an exemption and confers no rights
AS-12 | Internal audit capacity is available for CAL-09 without displacing the annual audit plan | Gideon Halvorsen | Open, and drawn on. No result of CAL-09 or of CAL-10 is stated anywhere in this phase and no outcome of either is anticipated
AS-13 | The estate as walked between 2026-06-08 and 2026-06-11 is the estate at the vantage | Amara Sissoko | Open, holding, and load-bearing to the last. Seventeen of the sixty-one systems would not be in any register in this repository if the walk had not happened
AS-14 | The instruments behind RT-09, RT-22, RT-23 and RT-29 retain no retrievable record and have no export | Dr Sunita Raghunathan | Open, unchanged. Those record types are outside the 34, the 61 and every register in this phase
AS-15 | Helix continues to administer every account on the three vendor-hosted systems | Joachim Reuter | Open, holding
AS-16 | The 58 record types are complete for the 41 marketed products and the two QC laboratories | Priyanka Venkataraman | Open, and still under test. No record type was introduced in this phase
AS-17 | Vendors supply technical documentation sufficient to describe the seven newly in-scope record types | Joachim Reuter | CLOSED 2026-09-17, tested and FAILED, unchanged — and it is the precedent AS-43 still works against at the last vantage
AS-18 | The 58 record types remain a stable unit through Phase 05 | Priyanka Venkataraman | Open, holding, and consumed again
AS-19 | The review trigger at ADR-0015 is operated by its named owner | Terrence Abbatiello | Open, and it is the assumption the whole of DK-01 rests on. SOP-DI-05 has still not fired, on anything, across nine phases and four hundred and twenty-five days. A determination nobody maintains is a determination that was true once
AS-20 | The 121 pairs derived on 2026-08-14 remain the population to MS-08 | Priyanka Venkataraman | Held and consumed, unchanged
AS-21 | Consequence is a property of the record type and travels with the class | Terrence Abbatiello | Open, holding, untouched
AS-22 | Those who supplied the facts described the position as it is rather than as procedure says it should be | Priyanka Venkataraman | Open, and still the widest assumption in the repository at the last vantage as at the first. It is one of the three IS-58 closed on, and the closure does not test it
AS-23 | A determination of Not determinable records the absence of evidence and not the absence of a search | Gideon Halvorsen | Open, holding, and applied again. The nil returns at EV-833 and EV-834 remain answers to questions that were asked
AS-24 | FDA's five attributes are sufficient to describe the integrity position of a Helix record type | Priyanka Venkataraman | Open, unchanged. No attribute was introduced and no assessment re-run
AS-25 | The scale published in Phase 03 is applied unchanged to MS-13 | Terrence Abbatiello | Held and consumed at this vantage. Nothing was re-scored in any phase after Phase 03
AS-26 | Many of the 35 GxP-relevant systems holding no Part 11 record are reached by 21 CFR 211.68, and others by different provisions of Part 211 | Colm Ó Braonáin | Open, unchanged, and engaged by an absence. The 35 are outside periodic-review-register.md and outside decay-register.md entirely
AS-27 | The three features graded in the complexity-and-reliability determination are sufficient to grade a system on the axis 21 CFR 211.68(b) names | Colm Ó Braonáin | Open, untested. The 21 CFR 211.68(b) graduation sentence graduates the degree and frequency of input/output verification and nothing else under that provision; where the repository borrows its axis it says so and does not claim its authority
AS-28 | The 61 systems and the 121 pairs remain the population to MS-09 | Amara Sissoko | Held and consumed. Continues as AS-39, AS-46, AS-52, AS-57, AS-64
AS-29 | The 63 procedures read are the whole of the procedure estate bearing on the 38 obligations | Terrence Abbatiello | Open, and load-bearing a sixth time — AS-35
AS-30 | The 44 validation packages read are the whole of what Helix holds | Colm Ó Braonáin | Open, untested, and load-bearing on a score. OS-02 is scored from the 44 and the 17, and this assumption is that the 44 is the whole of the numerator
AS-31 | The nine SOPs, the policy and the framework are issued under document control and not varied outside change control | Terrence Abbatiello | Open, holding, and unexercised. None of the nine has been applied to anything
AS-32 | The validation execution resource is available at the scale 61 validation plans require | Colm Ó Braonáin | Open, and never drawn on. No plan has been written, and the validation execution line is one of the two lines that came in under because the work was not done — IS-59
AS-33 | An obligation landing in a procedure that requires the act has a remaining gap of evidence or practice and not of the sentence | Priyanka Venkataraman | Open, unchanged
AS-34 | The configuration and behaviour observed between 2027-01-04 and 2027-01-20 is the configuration at the Phase 05 vantage | Joachim Reuter | Open, consumed, and it is the assumption underneath IS-64's ninety-one days — AS-63
AS-35 | The 63 procedures Phase 04 read are the whole of the procedure estate bearing on the eleven paragraphs | Terrence Abbatiello | Open, untested, and load-bearing on a score. OS-06 is Not met on the ground that neither of the two named procedures has been revised, which rests on the two procedure reads at EV-807 and on this assumption
AS-36 | The enumeration of human readable forms and of continuous-session behaviour is the whole of what each product can produce and do | Priyanka Venkataraman | Open, untested, untouched
AS-37 | A determination against 21 CFR 11.10(c) and against (e)'s retention clause can be made in the absence of a stated retention period | Priyanka Venkataraman | Open, unedited, not tested here. IS-43 carries its consequence and no cell has moved
AS-38 | The 23 reason-for-change fields are the whole of that population | Joachim Reuter | Open, untouched
AS-39 | The 61 systems remain the population to MS-10 | Amara Sissoko | Held and consumed. Continues as AS-46, AS-52, AS-57, AS-64
AS-40 | Those who supplied the configuration statements described the position as it is rather than as procedure says it should be | Joachim Reuter | Open, and one of the three assumptions IS-58 closed on — AS-22, AS-40, AS-49
AS-41 | The audit trail configuration read on 2027-02-10 on each chromatography instance is the configuration at the Phase 06 vantage | Joachim Reuter | Open, consumed, and now seventy-nine days behind
AS-42 | The enumeration of acts capable of changing a reportable result is the whole of what can change one | Priyanka Venkataraman | Open, untested, untouched
AS-43 | The vendor's statement that two classes cannot be enabled describes the product version | Joachim Reuter | Open, untested, and it carries as much weight at close-out as it has ever carried. OS-04 is scored Not met, and one of its three grounds is that AE-08 and AE-16 cannot be enabled on the product version Helix runs — the whole of the ground for which is a vendor statement Helix has not tested. DK-06 records that a vendor release could change the finding rather than merely age it — PR-07
AS-44 | The 142 released results and the 38 reprocessed within them are the whole of the population | Dr Sunita Raghunathan | Open, untested, untouched
AS-45 | The first-integration values obtained from outside the record the reviewer sees are the values the first integration produced | Dr Sunita Raghunathan | Open, untested, untouched
AS-46 | The 61 systems remain the population to MS-11 | Amara Sissoko | Held and consumed. Continues as AS-52, AS-57, AS-64
AS-47 | The predicate-rule anchors Phase 02 published for each in-scope record type are the whole of what makes that record a required record | Priyanka Venkataraman | Open, untested, and load-bearing on IS-03's closure. The closure turns on the record-type register carrying the predicate rule on all fifty-eight rows, and this assumption is that those anchors are the whole of it
AS-48 | The expiration date of the batch is held for every batch and is retrievable for as long as the period run from it lasts | Bernard Kwiatkowski | Open, untested, untouched
AS-49 | Those who supplied the backup and restore facts for the 61 described the arrangements as they are rather than as procedure says they should be | Amara Sissoko | Open, and one of the three assumptions IS-58 closed on. The closure does not test it; it records that the determinations were made by the people who own the things determined, which is what this assumption says about one register
AS-50 | The four restores at EV-719 are the whole of the restore history on the 61 | Amara Sissoko | Open, untested, untouched
AS-51 | The audit trail retention configuration read across the 61 on 2027-03-10 is the configuration at the Phase 07 vantage | Joachim Reuter | Open, consumed, and superseded in form by AS-55 and now AS-63
AS-52 | The 61 systems and the 34 record types remain the population to MS-12 | Amara Sissoko | Held and consumed. Continues as AS-57 and AS-64
AS-53 | EV-106 as filed on 2026-03-06 is the whole of what the response committed Helix to, and no commitment has been varied since | Rebekah Sandquist | Open, untested, and consumed a second time. OS-08 is scored from the commitment register, which is scored from EV-106, so this assumption sits under an objective score as well as under fourteen assessments
AS-54 | The five owners' own commitment trackers, read on 2027-03-30, describe the position each of those owners holds | Lydia Marchetti-Nwosu | Open, and now partly answered. IS-52 closed on five statements, each from an owner, each dated, and each a new act — EV-936 to EV-940. What the statements test is the tracker's content and not its use, so the assumption is narrowed rather than closed, and AS-62 is its Phase 09 form
AS-55 | The Phase 05 vantage of 2027-01-29 is the latest established position on the nine systems at CG-11 and CG-13 | Amara Sissoko | Open, untested, and now stretched to ninety-one days. Continues as AS-63
AS-56 | The Phase 04 complexity-and-reliability band read across on 2027-04-05 is the band at that vantage | Colm Ó Braonáin | Open, untested, untouched. SOP-DI-05 has fired on nothing
AS-57 | The 61 systems remain the population to MS-13 | Amara Sissoko | Held and consumed. No trigger fired, and the 61 were the population throughout. Continues as AS-64
AS-58 | The working papers of the four audits, as retained at EV-122 to EV-125, are the whole of what those audits produced | Gideon Halvorsen | Open, untested, untouched. Nothing in this phase reads an audit working paper, and no cell of audit-condition-register.md moves
AS-59 | Load-bearing on all eight scores. The eight measures published at 01.06 §3 are the whole of what each objective is scored against, and no objective, owner or measure has been varied since the charter was approved on 2026-03-06 — 01.06 §9 answering the question of who may vary an objective's measure with *"Nobody, during the programme…"*, and the assumption being that nobody did so outside the document either | Lydia Marchetti-Nwosu | An objective is scored against a measure nobody is now bound by, and a Met or a Not met is a statement about a superseded sentence. The assumption was not tested against anything except the charter as published: what was read is the document, not the question of whether anybody varied it outside it. It is AS-08's shape applied to the charter rather than to the response
AS-60 | The fourteen monthly budget reports made at CAL-01, read on 2027-04-22, are the whole of what was reported against the ten lines, and the actual column on each describes money spent rather than money committed or accrued | Lydia Marchetti-Nwosu | The direction of variance on one or more of the ten lines is a statement about a report rather than about the envelope, and the under-lines could be under for a reason other than the one IS-59 states. OS-07 is scored from the reports and from nothing else — ADR-0058 — so a defect in the reports is a defect in the score. No re-costing was performed and none is stated
AS-61 | The twelve artefacts at DK-01 to DK-12 are the whole of what the programme built and hands on, so that an artefact absent from the decay register is an artefact the programme did not produce rather than one nobody listed | Priyanka Venkataraman | An artefact goes out of date with no row recording what makes it do so and nobody looking at it — which is DK-12's condition applied to something nobody has even noticed. The four printout record types are the known instance of the pattern: IS-49 records that they are outside every register in this repository, and the decay register does not reach them either
AS-62 | The thirty-three acceptances recorded in handover-register.md describe a position each of those nine individuals holds after 2027-04-30, rather than a form returned to the programme manager in the last fortnight of a programme | Gideon Halvorsen | The handover is a record of thirty-three signatures and not of thirty-three destinations, and the 33 / 12 / 4 becomes a count of paperwork. The assumption was not tested and could not be tested from the papers: what was read is the acceptance, not the use of it. It is AS-54's shape at one further remove, and AS-54's subject matter is IS-52, which closed on five statements of the same kind
AS-63 | The Phase 05 vantage of 2027-01-29 remains the latest established estate-wide control position, and nothing on any of the sixty-one systems changed between that date and 2027-04-30 that would move any of the six hundred and seventy-one positions | Joachim Reuter | The ninety-one days is a floor and not a figure, and the position handed over is not merely old but wrong in a direction nobody can name. AS-55 made the same assumption over seventy days and this makes it over ninety-one. Nothing in Phase 06, 07, 08 or 09 read a system, and the register records a state and not a transition, so a change either way would be invisible — IS-53, DP-47
AS-64 | The 61 systems remain the population to MS-13 — AS-57's Phase 09 form, and the last in a chain running back to AS-28 — so that the eight scores, the twelve decay rows and the forty-nine handover rows all describe the same estate | Amara Sissoko | Every count in this phase describes a population that has moved, and a system added to the estate after 2027-01-29 has no determination, no control position, no review row, no decay row and no handover. ADR-0015's trigger is the mechanism that is supposed to catch it and it has never fired — AS-19, IS-10

## Dependencies
ID | Dependency | Owner | Raised | Status | Related
DP-01 | The record-level Part 11 determination, for control selection | Priyanka Venkataraman | Consumed, carried open. It is the artefact OS-01, OS-03 and AC-06 all turn on
DP-02 | The data integrity risk assessment, for the validation framework's rigour | Priyanka Venkataraman | Consumed, carried open for the 47 pairs — IS-16
DP-03 | Technical cooperation from IT and Automation | Priyanka Venkataraman | Open, and not drawn on in this phase, which read artefacts
DP-04 | Vendor technical documentation on audit trail generation, retention and export | Joachim Reuter | Open, and load-bearing through AS-43
DP-05 | Validation execution resource contracted and available | Colm Ó Braonáin | Open, and never drawn on. The validation execution line is under because the work named in it was not done — IS-59
DP-06 | Vashti Okonjo & Partners' availability for the audit window opening 2027-03-29 | Gideon Halvorsen | Open. No result is stated anywhere in this phase and no outcome is anticipated
DP-07 | Quality unit review and approval capacity for the two record review procedure revisions | Terrence Abbatiello | Open, and it is OS-06's route. RC-05 and RC-19 are Not met and both are past the date the response gave
DP-08 | The statement of what the January 2011 Annex 11 route requires of O12 | Rebekah Sandquist | Open since 2026-05-29, and it cannot be answered for any system until DP-44 exists
DP-09 | The determination as the assessment population | Priyanka Venkataraman | CLOSED on its first limb; the second recorded as unmet — AS-26
DP-10 | Technical detail on how the seven newly in-scope record types are created, retained and exported | Joachim Reuter | Open, unchanged
DP-11 | Quality unit capacity to draft the procedure requiring the determination to be maintained | Terrence Abbatiello | Open, unchanged
DP-12 | Administrative configuration detail for the three vendor-hosted systems | Joachim Reuter | Open, unchanged
DP-13 | Confirmation and acceptance of ownership for the seventeen systems the walk found | Amara Sissoko | Open, unchanged, since 2026-06-12
DP-14 | A retention period for each of the 34 Part 11 record types | Priyanka Venkataraman | Open, narrowed to the fourteen — DP-38
DP-15 | How Phase 03's two axes relate to complexity and reliability | Colm Ó Braonáin | CLOSED 2026-10-27, unchanged
DP-16 | Audit trail behaviour statements for the systems on which contemporaneity or attribution could not be determined | Joachim Reuter | Open, discharged for two systems and only two
DP-17 | A statement, per record type, of which instance Helix relies on as the original | Priyanka Venkataraman | Open, and still the single largest closure route in the programme. Not discharged, across seven phases
DP-18 | A retention period for each of the 34 Part 11 record types | Priyanka Venkataraman | Open, narrowed with DP-14 — DP-38
DP-19 | Quality unit capacity to write the procedure requiring the assessment to exist and be acted on | Terrence Abbatiello | Consumed in Phase 04, carried open as DP-22
DP-20 | Account administration records sufficient to say which named individual held the credential in use | Amara Sissoko | Open, unchanged, and it is OS-05's and OBS-4's dependency. It has not moved since 2026-09
DP-21 | Validation execution capacity sized against 61 system validation plans | Colm Ó Braonáin | Open. No plan has been written
DP-22 | Quality unit capacity to take the nine SOPs from approved to applied | Terrence Abbatiello | Open, unchanged. None of the nine has been applied to anything
DP-23 | The evidence named on each obligation record, for all 38 obligations | Priyanka Venkataraman | Open. Not one obligation is discharged — IS-34, and it is OS-02's subject matter
DP-24 | A change control route firing three triggers from one change record | Terrence Abbatiello | Open, and carrying DP-47 as a seventh object
DP-25 | Interface and failure-history statements per system | Amara Sissoko | Open, unchanged
DP-26 | A statement, per system, of what its validation package covers against each of the eleven paragraphs | Colm Ó Braonáin | Open, unchanged
DP-27 | Quality unit capacity to decide which of the 218 unrequired controls Helix intends to require of itself | Terrence Abbatiello | Open, and still larger than the rest together. No sentence has been written, across five phases
DP-28 | Vendor route to include the meaning of the signature in every human readable form on the twelve | Priyanka Venkataraman | Open, unchanged
DP-29 | Vendor product route to retain a previous value in the record the reviewer sees, on the six at CG-15 | Joachim Reuter | Open, unchanged — and it is the second proposition of OBS-6, which the estate still carries
DP-30 | Vendor or configuration route to set the subsequent-signing prompt to the password on the seven | Amara Sissoko | Open, unchanged
DP-31 | Systems documentation for the systems that have none | Bernard Kwiatkowski | Open, unchanged
DP-32 | A re-determination route firing from one change record on a change to a system's configuration | Terrence Abbatiello | Open, unchanged
DP-33 | A vendor product route to record two auditable event classes at all | Joachim Reuter | Open, nothing agreed, and it is one of the three grounds OS-04 is scored Not met on
DP-34 | A vendor product route to retain the first integration's value in the record the reviewer sees | Dr Sunita Raghunathan | Open
DP-35 | A configuration decision, and a sentence in a procedure requiring it, for the classes enabled on neither instance | Terrence Abbatiello | Open, and competing with DP-48 and DP-52 as well
DP-36 | A comparison instrument that fires on a change to either chromatography instance | Priyanka Venkataraman | Open — SOP-DI-05 has still not fired on any change
DP-37 | Retention, backup and archive facts for SYS-036, SYS-060 and SYS-061, and a statement of which instance is relied on as the original | Amara Sissoko | Open on its second limb only, unchanged — it is DP-17's
DP-38 | A determination, by a named individual and recorded as a decision, of a retention period for each of the fourteen record types no predicate rule supplies one for | Dr Marguerite Oyelaran | Open, and nothing is decided. No period is set, proposed or bounded by anything in Phase 09
DP-39 | A retrieval of RT-12 and RT-13 from SYS-060 initiated at Cary, performed, timed and recorded | Amara Sissoko | Open. Nothing has been performed
DP-40 | A restore performed as a test rather than as incident recovery, with the restored content compared with what went in | Amara Sissoko | Open. Nothing has been performed
DP-41 | A determination, per record type, of whether 21 CFR 211.68(b)'s carve-out reaches the data | Colm Ó Braonáin | Open, and owed since Phase 06. Made on 0 of the 61
DP-42 | A stated retention location, a named accountable individual and a medium statement — or a reproduction — for each of the four paper record types | Dr Sunita Raghunathan | Open. Nothing has been supplied
DP-43 | A statement, from each of the owners the response named, of what their own tracking should now record for the five commitments this programme discharged | Lydia Marchetti-Nwosu | DISCHARGED 2027-04-30. Five statements, EV-936 to EV-940, each a new act with its own record, and no tracker edited to agree with any register — ADR-0056. IS-52 closes on it, and §1.8 records what that closure never asked
DP-44 | A product-to-system mapping | Rebekah Sandquist | Open, and it does not exist in any form. DP-08 still cannot be answered, and IS-03's closing note records that no register in this repository joins a record type or a system to a product
DP-45 | A named individual reviewer for each periodic review, who is not the owner of the system being reviewed | Colm Ó Braonáin | Open. No reviewer is named on any of the sixty-one rows, and the earliest first due date falls thirty-one days after the programme ends
DP-46 | Read access for the audit function, requested and then granted, recorded system by system in the working papers | Amara Sissoko | Open, and the grant is decided. DEC-911 records a decision, dated 2027-04-26, and this log records no access as performed — ADR-0061. It does not close by a decision to grant, and it does not close by access being granted on one system. Requested 0 of 61, granted 0 of 61 remains the published position
DP-47 | A route by which a change to a published control position is recorded in the programme's registers as a change | Terrence Abbatiello | Open, and now carrying the whole of IS-64. The position handed over is ninety-one days old and the register cannot show whether any of it has moved, in either direction
DP-48 | A named individual for each of the twelve handover entries whose destination is a function, and for the two decay rows whose holder is a function — fourteen names, and a statement from each that the entry is theirs after 2027-04-30 | Closure of IS-62's function limb and of IS-61's two-artefact limb; and any statement that those entries have a destination | The quality unit for ten handover entries and one decay row, the validation function for one, the change control function for one, and the IT organisation for one decay row | Dr Marguerite Oyelaran | Open, and nothing is named. A function cannot supply a name on its own behalf — that is ADR-0060's whole point — and it does not close by a function confirming that it has received the entries, which is what a function can do and is not what is asked
DP-49 | A holder for the evidence index — a named individual who accepts DK-12 after 2027-04-30, the artefact in which every EV identifier the other eleven cite resolves | Closure of IS-61's third limb, and the ability of any artefact in this repository to have its citations checked | [NOT ESTABLISHED] — no source is identified. The programme manager holds it to this vantage and holds nothing after it; no line function's remit includes an index of programme evidence, and no post was created for it | Priyanka Venkataraman | Open, and it is the only dependency in this log with no source. A dependency on nobody is a task, and this one has neither. It does not close by the file being stored somewhere, which is storage and not a holder — ADR-0062
DP-50 | A schedule for the first independent assessment under the arrangement — a date, a scope, a commissioning decision, and a party that designed and implemented none of what it assesses | Closure of IS-63, and any statement that the arrangement has produced anything | The Board's audit committee, which established the internal audit function and to which it reports | Gideon Halvorsen | Open, and there is no date. The arrangement exists and the assessment does not — ADR-0061, ADR-0004. It does not close by the arrangement being approved, which is what created it, and no result of any assessment is anticipated anywhere
DP-51 | Funding, and an authority to commit it, for work outside the programme's own artefacts — the seventeen systems with no validation package, the nine with a shared account, the two procedures, the sixteen with no second term, the fourteen record types with no period | Any movement on OBJ-02, OBJ-04, OBJ-05 or OBJ-06, and on IS-60 | The sponsor and the Board. No successor programme is chartered, no envelope exists after 2027-04-30, and the charter may be varied only by a further minuted decision of the sponsor | Dr Marguerite Oyelaran | Open, and it is the dependency IS-60 reduces to. It states no amount, no scope of works and no cost, and it is not a proposal, a business case or a request — it records that the estate objectives require a funded authority and that none exists at this vantage
DP-52 | A statement of who holds each of the seven calendar entries that outlive the programme, after 2027-04-30 — by name, per entry, and recorded as a decision | Closure of IS-07, which has stood since 2026-05-27, and of IS-65's calendar limb | The quality unit, under 21 CFR 211.22 | Terrence Abbatiello | Open, and it is the oldest unmet ask in the repository restated at the last vantage. It does not close by the quality unit being named as the holder in a document written by this programme — IS-07 has refused that for nine phases and refuses it here

## Programme risks
ID | Programme risk | Owner | Raised | Status | Related
PR-01 | Committed scope exceeds the envelope because remediation reveals work the estimate did not carry | Lydia Marchetti-Nwosu | Open, and it did not materialise in the direction it was written for. The programme closes under its envelope — and two of the three under-lines are under because the work was not done, IS-59. No re-costing has been performed and none is stated
PR-02 | The 9.2 FTE-equivalents are funded but not released | Dr Marguerite Oyelaran | Open, and consumed. The line bought time and did not create capacity, and the capacity DP-05, DP-21 and DP-27 ask for was never released
PR-03 | The Phase 02 determination overruns | Priyanka Venkataraman | Did not materialise. Retained for the pattern
PR-04 | The assurance tail compresses and pushes MS-12 into close-out | Lydia Marchetti-Nwosu | Open, and it did not materialise. MS-13 is met at this vantage, twenty-one days from MS-12 as planned
PR-05 | Determinations require technical cooperation the Data Integrity Lead cannot compel | Priyanka Venkataraman | Open, and inverted a second time. This phase compelled nothing because it asked nothing of a system; what it could not compel was a name from a function — DP-48
PR-06 | Advisory scope drifts into work the third-party auditor must later audit | Gideon Halvorsen | Open — ADR-0004, AS-09
PR-07 | A vendor is treated as supplying compliance rather than features that support it | Colm Ó Braonáin | Open, and directly engaged. A product has features that support compliance; compliance is a property of Helix's validated system in its intended use — AS-43, DK-06
PR-08 | Enforcement discretion is read inside Helix as permission to defer validation | Terrence Abbatiello | Open — PR-38
PR-09 | A cadence or control is adopted because a guidance suggests it, and reported internally as a requirement | Rebekah Sandquist | Open, and live. A *should* in a guideline is an expectation and never a requirement, and every EU-derived citation in this phase is labelled EU-derived in the same sentence
PR-10 | Key-person concentration on the Data Integrity Lead and the CSV Lead | Dr Marguerite Oyelaran | Open. None agreed at the vantage, across nine phases and nine vantages, and the cell still says so — and at this vantage the two posts hold four of the twelve artefacts in decay-register.md between them
PR-11 | The seven newly in-scope record types are read as a criticism of the laboratory | Dr Sunita Raghunathan | Open, and live
PR-12 | The determination is cited as though it were an integrity statement | Priyanka Venkataraman | Open, and inverted again. OS-01 is Met and OS-01 says nothing whatever about whether any record is complete, consistent or accurate. Applicability is not integrity
PR-13 | The determination drifts, because no procedure requires it to be maintained | Terrence Abbatiello | Open, and it is the widest of the carried risks at close-out. No procedure requires the determination, the periodic review arrangement, the decay register, the handover register or the objective score register to be maintained — IS-25
PR-14 | Phase 03's assessment population is larger than the plan assumed | Lydia Marchetti-Nwosu | Open
PR-15 | The phrase "a Part 11 system" re-enters use | Priyanka Venkataraman | Open, and engaged. Part 11 applies to records, not to systems, and every register in this phase that names sixty-one systems names them because of the records they hold
PR-16 | An instrument behind one of the four surviving printout record types is replaced | Dr Sunita Raghunathan | Open, unchanged
PR-17 | The seventeen systems with no validation lifecycle absorb effort sized against systems with documentation | Colm Ó Braonáin | Open, unchanged
PR-18 | The first assessment of the three vendor-hosted systems stalls on vendor-held documentation | Joachim Reuter | Open, and live. None of the three has been reviewed
PR-19 | The 47 unscorable pairs are read as low risk because they carry no rating | Priyanka Venkataraman | Open, and mirrored twice more. An absence read as a permission — PR-59, and a None in a holder column read as *somebody will pick it up*
PR-20 | A rating is cited as a compliance position | Terrence Abbatiello | Open, and now seven ways — a rigour band, a control position, a signature test result, a configuration read, a retention group, a review frequency and an objective score
PR-21 | The five attributes are averaged, or a single number per pair is produced | Priyanka Venkataraman | Open, unchanged
PR-22 | The published scale is elaborated under pressure to discriminate more finely | Terrence Abbatiello | Open, and refused again. A partial score was available for OS-08 and was refused — ADR-0058, PR-64
PR-23 | The assessment becomes an annual exercise nobody acts on | Lydia Marchetti-Nwosu | Open, and it is now IS-07's, IS-57's and IS-65's shared subject matter
PR-24 | Phase 04 sets rigour from the 74 scored pairs alone | Colm Ó Braonáin | Open, did not materialise. Retained
PR-25 | The "original or a true copy" finding is read inside the laboratory as a criticism | Dr Sunita Raghunathan | Open, unchanged
PR-26 | A Not determinable determination is treated as closing when somebody writes a document | Gideon Halvorsen | Open, and mirrored a fourth and fifth time. A grant decided is not access performed — PR-68 — and an arrangement for independence is not an assessment — PR-69
PR-27 | The coverage finding at IS-22 is reported as a control position | Colm Ó Braonáin | Open, did not materialise here
PR-28 | The 25 systems with no established data integrity position acquire one by drift | Priyanka Venkataraman | Open, and directly engaged. Not one of the twenty-five has acquired one
PR-29 | The two graduations are merged, averaged or reduced to one number | Joachim Reuter | Open, and engaged. No band is merged or moved anywhere in this phase
PR-30 | The twelve at IS-24 are folded back into a single count of procedural gaps | Terrence Abbatiello | Open
PR-31 | A later re-read of the procedure estate is scoped to look only where something is expected | Terrence Abbatiello | Open, and load-bearing again — AS-35
PR-32 | The nine SOPs are approved and never applied | Terrence Abbatiello | Open, unchanged, and it materialised. None of the nine has been applied to anything, across five phases
PR-33 | A requirement is read as a description of the world | Gideon Halvorsen | Open, and inverted a sixth time. Phase 09's form is an arrangement for independence read as independence — PR-69, IS-63
PR-34 | The 61 validation plans are sized against the 44 with a package | Colm Ó Braonáin | Open. No plan has been written
PR-35 | The 302 and the 218 are added and reported as 520 | Priyanka Venkataraman | Open, and mirrored — PR-52
PR-36 | The 671 are reduced to 61 system-level verdicts | Joachim Reuter | Open, and a sixth register now invites it. A decay row is a rate and a holder and is never a verdict, and an objective score is a statement about an artefact and never about a system
PR-37 | The 21 CFR 11.50 finding is read as a 21 CFR 11.10 control position | Priyanka Venkataraman | Open, unchanged
PR-38 | The 89 are reported as mitigated, and discretion is read inside Helix as permission | Terrence Abbatiello | Open, and live. A programme that reads enforcement discretion as permission has read the wrong document
PR-39 | A reason-for-change field is reported as compliance with 21 CFR 11.10(e) | Joachim Reuter | Open, unchanged
PR-40 | 21 CFR 11.200 is described as a multi-factor authentication requirement | Amara Sissoko | Open, unchanged
PR-41 | The Not met cut by system owner is read inside a function as a criticism | Dr Sunita Raghunathan | Open, and live — PR-65 is the same pressure applied to eight objective owners
PR-42 | The control position register is treated as a compliance certificate | Colm Ó Braonáin | Open, and now with four more candidates. An objective score register, a decay register, a handover register and a close-out pack can each be cited that way. There is no Part 11 certification, no Part 11 certificate and no FDA-approved or FDA-validated software
PR-43 | The three classes recorded on neither instance are read as an excuse, and OBS-2 is reported as reduced | Terrence Abbatiello | Open, and live in OS-04's row, which states the three grounds together and does not offer the product limitation as a discharge. A product limitation is a fact about a product, not a discharge of an obligation
PR-44 | A depth finding is generalised to the estate | Colm Ó Braonáin | Open, and live — IS-41
PR-45 | The nine reintegrations are characterised, in either direction | Gideon Halvorsen | Open, unchanged. No reintegration is characterised here
PR-46 | A reason-for-change field is reported as compliance with 21 CFR 11.10(e) | Joachim Reuter | Open, unchanged
PR-47 | The two divergences are read as a criticism of one laboratory | Dr Sunita Raghunathan | Open, unchanged
PR-48 | Two configuration counts are added, averaged or reported as a single estate figure | Priyanka Venkataraman | Open, unchanged
PR-49 | The manual transcription is reported as a finding about Cary's practice | Amara Sissoko | Open, unchanged
PR-50 | The twenty record types whose period the regulation sets are reported inside Helix as *retention resolved* | Terrence Abbatiello | Open, unchanged
PR-51 | A period is set for a Group C record type by drift rather than by a recorded decision | Amara Sissoko | Open, unchanged. No period is set, proposed or bounded in this phase
PR-52 | Two populations are read as one because their numerals coincide | Priyanka Venkataraman | Open, and the discipline is applied twice more. The forty-nine open issues and the forty-four validation packages are unrelated populations. The twelve artefacts of decay-register.md and the twelve calendar entries of CAL-01 to CAL-12 are unrelated populations, and seven of the calendar entries and none of the artefacts are IS-07's subject matter. No document in this phase joins either pair
PR-53 | The fifty-four backup files are reported as a control, or the four incident recoveries as restore tests | Amara Sissoko | Open, unchanged
PR-54 | IS-43 is read as a criticism of the Phase 05 determinations | Terrence Abbatiello | Open, and live at the handover. HO-29 records that no cell moves
PR-55 | Phase 02's printout route is re-opened, or IS-49 is read as evidence that it was wrongly applied | Dr Sunita Raghunathan | Open, unchanged. Nothing in this phase reaches the four
PR-56 | Phase 07 is read as having stated a retention policy, a schedule or an archive design | Dr Marguerite Oyelaran | Open, unchanged
PR-57 | A disposition is read as a closure | Terrence Abbatiello | Open, and live to the last document. No observation is described as closed anywhere in this phase, no register in it carries a status column in which the word could be entered against one, and ADR-0051 and ADR-0064 are stated together in every file that touches the subject
PR-58 | A document in this phase is treated as a communication to FDA | Rebekah Sandquist | Open, and at its most live at close-out — PR-70 is its Phase 09 form and is opened rather than folded into it, because a close-out pack is the artefact most likely to be forwarded
PR-59 | The three commitments with no completion criterion acquire one by drift | Rebekah Sandquist | Open, unchanged. No completion criterion is written for RC-07, RC-14 or RC-20 anywhere in this phase, and OS-08's row records the absence rather than supplying the test
PR-60 | IS-52 is read as an allegation against the five named owners | Lydia Marchetti-Nwosu | Open, and it is the risk the closure of IS-52 most nearly runs. The closure records five statements and no correction; both original records stand unaltered; and nobody failed to do anything they were asked to do — the work was done, and it was done by the programme
PR-61 | OBS-6's corrected position is generalised | Joachim Reuter | Open, unchanged. The observation is disposed of whole and CG-15's six systems still carry the class — DP-29
PR-62 | The arrangement is reported inside Helix as a periodic review, or the EU-derived limb as binding on the US-facing route | Dr Marguerite Oyelaran | Open, and mirrored in a new place. PR-69 is the same shape applied to independence: an arrangement reported as the thing it arranges for. Reviews performed: 0 of 61
PR-63 | IS-01's closure is read as having chosen among the four candidate explanations | Gideon Halvorsen | Open, and the boundary holds at the last vantage. No candidate explanation is named, numbered, quoted, reproduced, summarised, characterised, paraphrased or alluded to anywhere in this phase, in this log, or in IS-58's closing note — and IS-58 is expressly distinguished from IS-01 in its own closure, so that the closing entry cannot become the vehicle
PR-64 | The scoring method is applied to something other than a charter objective — to a system, a control, a record type, a commitment or a function — or a partial score is introduced into it, so that an instrument built to read eight measures becomes a general-purpose grading scheme | Lydia Marchetti-Nwosu | ADR-0058 is standing framing and objective-score-register.md §0 states the two states and the absence of a third before it states anything else. The register carries eight rows and no ninth, prints no percentage, produces no aggregate and reaches no index. 01.12 §4's prohibition on scoring the programme registers is unchanged, and no IS, AS, DP or PR entry acquires a score from this phase | GOV-41, 2027-04-14 | ADR-0058, OS-01 to OS-08, PR-20, PR-22
PR-65 | The charter score is read as a verdict — on the programme, on a function, or on an individual — or the three Met are aggregated into a statement about Helix | Dr Marguerite Oyelaran | A score is not a verdict, and objective-score-register.md §0 says so in terms before the first row. Each objective has a named individual owner and the register is not a report on those seven people; 01.09 §2's rule holds without variation — no document in this repository assesses any individual's work. ../09.03-what-the-score-is-shaped-like.md states expressly that the pattern is not an accusation of bad faith, and the phase reaches no compliance conclusion and states no readiness claim | GOV-42, 2027-04-21 | IS-60, ADR-0058, ADR-0059, PR-41, PR-60
PR-66 | The underspend is reported inside Helix as a saving, as efficient delivery, or as headroom released — and the two lines that are under because the work was not done are not distinguished from the one that is under for any other reason | Lydia Marchetti-Nwosu | IS-59 is published as an open issue rather than as a footnote to a Met, and OS-07's row states that the measure asks whether the reporting happened and whether the envelope held, and does not ask what the money bought. ../09.04-the-envelope.md states the variance as line counts and directions and states no amount, and no re-costing is performed or stated anywhere. The contingency and the headroom are not spent in advance and no prediction is made that they will be | GOV-43, 2027-04-27 | IS-59, OS-07, PR-01, AS-60
PR-67 | A handover entry whose destination is a function is reported inside Helix as handed over — in a summary, in a slide, or in a successor document — or the four with no destination are quietly attached to somebody | Gideon Halvorsen | ADR-0060 is standing framing: a function is not a destination. handover-register.md prints the acceptance column as No on all sixteen rather than leaving it blank, because a blank invites completion; §2 names the twelve function rows and the four with none; and ../09.08-the-four-that-go-nowhere.md is a numbered chapter whose whole business is the four. DP-48 asks for fourteen names and none exists | GOV-43, 2027-04-27 | IS-61, IS-62, ADR-0060, ADR-0062, DP-48, DP-49, PR-26
PR-68 | The read-access grant is reported as access performed, or AC-05 is described as capable of being met on the strength of a decision, or the arrangement is cited as having satisfied IS-55 | Amara Sissoko | ADR-0061 is standing framing: an access grant is recorded as decided and dated, never as performed, until an artefact evidences the performance. DEC-911 carries a date and a decider and no evidence of access on any system. IS-55 stays open and says so; DP-46 stays open and says so; and the published figure remains requested on 0 of the 61 and granted on 0, which is audit-condition-register.md's and does not move here | GOV-44, 2027-04-29 | IS-55, IS-63, ADR-0061, AC-05, DP-46, PR-26, PR-33
PR-69 | The arrangement is reported as an assessment, or IS-58's closure is read as having made the repository's determinations independent retrospectively, or a later reader treats the closure as an assurance opinion | Gideon Halvorsen | ADR-0061 and §1.8's closing note say it three ways: Helix cannot make this programme independent retrospectively; what closes is the question and not the condition; and an arrangement is not an assessment. IS-63 is published as an open issue on the day IS-58 closes, and DP-50 has no date. No result of any assessment is reported and none is anticipated — ADR-0004, and an assurance opinion from the party that designed the thing being assured is not an opinion, it is a restatement | GOV-44, 2027-04-29 | IS-58, IS-63, ADR-0004, ADR-0061, DP-50, PR-33
PR-70 | A close-out document is treated as a communication to FDA — filed, forwarded, quoted in correspondence or offered as evidence of the company's position — or the close of the programme is reported as the close of its subject matter | Rebekah Sandquist | ADR-0064 records that close-out is not a communication to FDA and that no artefact in this phase is written to be read by one. Every document in this phase is an internal document and carries the classification line saying so; the response of 2026-03-06 remains the only thing Helix has said to the agency about any of this; no observation is closed or described as closed; and ../09.13-close-out.md ends on the forty-nine that stay open rather than on the three that close | GOV-45, 2027-04-29 | ADR-0057, ADR-0063, ADR-0064, IS-66, PR-57, PR-58, PR-09